## Timeline
CCDG Work Plan and interaction with Ofgem SCR milestones
| 2019 |  | 2020 | [11 empty] | 2021
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May
Code Change and Development Group activities
CCDG members confirmed | 2019 Nov: 14
CCDG Meeting 1 (Review of draft Work plan and agreed ways of working) | 2019 Dec: 5
ELEXON update work plan and draft Code Change Matrices and sends to CCDG for review | 2019 Nov: Draft Work Plan and draft CC Matrices
ELEXON provide strawman MC, CCC options. Review ISD data items. Registration and data Flow data Items. Exception reports. | 2019 Dec: Strawmen MC and data items
CCDG Meeting 2 (MCs, CCCs, Rationalisation of existing industry data items) | 2020 Jan: 15
ELEXON provide work plan to Ofgem | 2020 Jan: CCDG Work plan
ELEXON provide CC Matrices to Other Code Bodies | 2019 Dec: Codes identify impacted areas of their Codes and complete Code Change Matrices
CCDG members develop Working Document A: (Review Work Plan, discuss MCs, CCCs, ISD and Registration data requirements) | 2019 Dec: Develop transition; 2020 Jan: Working Document A
ELEXON draft strawman GSPGCF and scaling weights paper | 2020 Jan: Strawman GSPGCF options
CCDG Meeting 3 (Agree approach to calculating and applying GSP Group Correction Factors and GSP Group scaling weights) | 2020 Feb: TBC
CCDG members develop Working Document B: (GSPGCF and scaling weights) | 2020 Feb: Working Document B
ELEXON develop options for the Settlement Run off arrangements | 2020 Feb: Strawman Run-off arrangements
CCDG Meeting 4 (CCDG agree detailed approach to the Settlement Run ‘run-off’ arrangements under the new TOM) | 2020 Mar: TBC
CCDG develop Working Document C: Settlement Run off arrangements | 2020 Mar: Working Document C
CCDG Meeting 5 (Review Working Document C and CC matrices and agree consultation questions). Direct drafting of Legal text. | 2020 Apr: TBC; 2020 Jun: 21
Code bodies start drafting Legal Text for Code changes (non-dependent). | 2020 Apr: Code Bodies draft Legal Text (non-dependent)
ELEXON draft consultation on detailed areas developed by CCDG | 2020 Apr: Consultation Development
CCDG Meeting 6 (Review and publish of Consultation on detailed Areas developed) | 2020 May: TBC
Consultation on detailed design developed by the CCDG | 2020 Jun: Consultation on detailed design
CCDG Meeting 7 (CCDG Review draft Legal Text (non-dependent changes)) | 2020 Jun: TBC
ELEXON summarise consultation responses | 2020 Jul: Consultation summary
CCDG Meeting 8 (CCDG Review draft Legal Text (non-dependent changes) | 2020 Jul: TBC
CCDG Meeting 9 (CCDG reviews of Consultation Responses on detailed Areas developed). Direct drafting of legal text (dependent changes) | 2020 Aug: TBC
Code bodies update CC Matrices for dependent code changes | 2020 Aug: Update CC Matrices (dependent changes)
Code bodies start drafting Legal Text for Code changes (dependent) | 2020 Aug: Code bodies draft Legal Text (dependent)
CCDG Meeting 10 (CCDG review drafting of Legal Text (non-dependent changes)) | 2020 Sep: TBC
CCDG Meeting 11 (CCDG review drafting of Legal Text (non-dependent changes)) | 2020 Oct: TBC
CCDG Meeting 12 (CCDG Review Legal Text (non-dependent)) | 2020 Nov: TBC
CCDG Meeting 13 (CCDG Review Legal Text (dependent and non-dependent)) | 2020 Dec: TBC
ELEXON Draft Consultation on Legal Text | 2020 Dec: Draft Consultation (Legal Text)
CCDG Meeting 14 (CCDG Review and finalise consultation on Legal Text) | 2021 Jan: TBC
CCDG Meeting 15 (CCG Agree Final report structure) | 2021 Feb: TBC
Consultation on Legal Text | 2021 Feb: Consultation on Legal Text
ELEXON Summarise Consultation Responses | 2021 Mar: Consultation Summary
Code Bodies update Legal text (following consultation comments) | 2021 Mar: Code Bodies update legal text
CCDG Meeting 16 (CCDG review consultation reponses) | 2021 Mar: TBC
ELEXON draft Final report | 2021 Mar: Draft Final report
CCDG Meeting 17 (CCDG review Final Report to Ofgem) | 2021 Apr: TBC
ELEXON update final report | 2021 Apr: Update Final Report
CCDG Meeting 18 (CCDG agree Final Report to Ofgem) | 2021 May: TBC
Final Report to Ofgem | 2021 May: Final Report to Ofgem
Design Advisory Board meetings
DAB Meeting 9 | 2019 Nov: 21
Ofgem SCR milestones
TOM Board meetings | 2019 Nov: 21
Analysis of RFI Responses and draft Impact Assessment | 2019 Nov: RFI and draft IA
Consultation on Draft IA | 2020 Jan: Draft IA Consultation
Analysis of IA responses | 2020 Apr: Analysis of IA Responses
Finalise Business case and IA | 2020 Jul: Finalise Business Case and IA
Publish Full Business case and IA (Q3 2020) | 2020 Jul: Publish of FBC and IA