## Open Actions
TAMEG ACTIONS
Meeting name |  | Technical Assurance of Metering Expert Group |  |  | Meeting no. |  | TAMEG 49
Meeting date |  | 2022-04-20 |  |  | Actions from |  | TAMEG 35-49
Open Actions |  | 7 |  |  | To Be Closed (TBC) Actions |  | 2
Meeting Number | Action number Reference | Related Papers Number | Action | Owner | Most Recent Update | Next Update Due | Action Updates | Action Status
35 | 35.06 |  | A TAMEG member noted the issue may arise from P272 sites which have been transferred to HH with legacy meter technical details retained and advised Registrants to complete a data cleanse of their portfolios for target MPANs which may have experienced the issue. The TAA is to continue the audit ensuring at all cases are highlighted, monitored, and will report back. | SIW |  |  | April 2019 Update: Still ongoing, there is inconsistency between whether they are Measurement Class C or COP10. Suppliers will be contacted. A TAMEG member suggested the TAA should just audit them (or get Suppliers to carry out the audit). The TAMEG agreed to contact MOA. July 2019 Update: ELEXON to send refresh data over to MOA. October 2019 Update: Data refreshed and distributed to Parties. Progress to be monitored following SMRS refresh. Jan 2020 update: ELEXON to re-run script Q1. October 2020 Update: Script to be re-run following submission of SMRS data Q4. Jan 2021 Update: Tabled agenda item added to meeting. April 2021 Update: No further action. July 2021: Elexon added a tabled agenda item to the meeting. Action to remain open. October 2021: Action to remain open following a delay in the availability of SMRS data. January 2022: Elexon encountered problems re-running the script, but will do so as soon as possible and issue the outcome ex-Committee April: Script is available - to be run, will be placed as tabled agenda item upon script being successful. | Open
45 | 45.06 |  | A TAMEG Member asked for an update on new Metering devices awaiting approval, specifically the ProMeter100, including an estimated date for completion. Elexon stated that the protocol is currently with IMServ for testing. There was no estimated date for completion but Elexon will chase it up. | IAN |  |  | July 2021: Action to remain open as Elexon were still awaiting application forms from multiple parties. October 2021: The protocol is being tested, manufacturer is updating its meter software to make passwords compliant. January 2022: IMServ is currently testing the meter following an update to the manufacturer's software to deal with the password non-compliance. April 2022: Prometer 100 approved for use under IMServe (UKDC) HHDC and CDCA. | To be closed
46 | 46.01 |  | A TAMEG Member has asked if the failings in relation to CVA site audits were recent or historical failings (from the 1990's). The TAA noted that these sites were highlighted due to concerns from Elexon that they may be in relation to the ongoing ADR issue. The TAA have agreed to investigate and report back on this to TAMEG. | LIY |  |  | October 2021: TAA to provide update. January 2022: In progress April: There is no way for the TAA to determine the date of energisation of the sites. This action can be reassigned if there is another method to gather this information. | Open/To Be closed
46 | 46.07 |  | TAMEG agreed that there needs to be clarity on what was deemed a fault. Elexon confirmed that ‘faults’ related to the sending of a D0001 and checking to see if there was a corresponding D0002 sent. Elexon also noted that, due to the Covid-19 pandemic, it believed the data would likely be skewed and show more non-compliance in comparison to previous years. Elexon agreed to investigate what types of faults occurred and, if possible, confirm the impact they had on Settlement. | SIW |  |  | October 2021: In progress January 2022: In progress April 2022: In progress | Open
46 | 46.08 |  | The Chair recommended that Elexon email LDSOs noting Elexon’s findings and requesting further CT/VT error data for those CT/VTs identified through Action 43.03 that are not on the NMTES already | SIW |  |  | October 2021: In progress January 2022: In progress April: In Progress | Open
47 | 47.03 |  | A Member advised that as all D0268s should be held electronically they were concerned that some parties were having issues submitting D0268s. Elexon took an Action to further investigate the common issues with sending a D0268, as the root cause for this could not be determined without further investigation | SIW |  |  | January 2022: In progress April: A Root cause has been identified, this will be added for review within the TAAMT backlog. | Open
47 | 47.04 |  | The Chair suggested that the TAA provide a list of what they are picking out during a Desktop Audit that would result in a category A.5 non-compliance ("Suspect data on Commissioning evidence provided") | LIY |  |  | January 2022: The TAA will provide Elexon with some high-level examples of information that has resulted in these findings; if necessary, Elexon can consider adding examples during the review of the Desktop Audit Local Working instruction (LWI) April: Findings conclude: • Recorded voltages out with acceptable tolerance • Suspect recorded Measurement Transformer ratios • Prevailing load check error > +/-10% • Other things such as wrong MPAN/MSID or site name, no date or signature would warrant a B.11 or B.13 for further correction/investigation | Open
49 | 49.01 |  | Add data for site visits in Audit Year 2020/21 to the TAMEG Stats Report prior to publication. | SIW |  |  | April 2022 - New Action added | Open
49 | 49.02 |  | Present engagement data in the TAMEG Stats Report as stacked columns with data labels showing the percentage cancelled and/or no access rates | SIW |  |  | April 2022 - New Action added | Open
49 | 49.03 |  | Add information on resolution times for Non-compliances to TAMEG Stats Report and Non-compliance tracker | MTH |  |  | April 2022 - New Action added | Open
49 | 49.04 |  | Include the material impact of Noncompliances to the Stats Report where possible | MTH |  |  | April 2022 - New Action added | Open
49 | 49.05 |  | Explore options for reducing the frequency of TAMEG meetings. Investigate changing the Terms of Reference of the TAMEG to make the meeting more of an operational metering issues forum/workgroup and not just Technical Assurance of Metering (TAM) related issues | CHD |  |  | April 2022 - New Action added | Open
49 | 49.06 |  | Explore including TAMEG Members in any Lessons Learned exercise resulting from the recent high-volume metering errors in the CVA market | MIS |  |  | April 2022 - New Action added | Open

## Names
Mike Smith | MIS | TAMEG Chair
Mica Thomas | MTH | Technical Secretary
Jessica Davis | JED | Elexon
Christopher Day | CHD | Elexon
Simon Waltho | SIW | Elexon
Lisa Young | LIY | C&C (TAA)
Colin Gentleman | COG | SSE (LDSO)
Warren Lacey | WAL | Northern Powergrid (LDSO)
Antony Hobbs | ANH | Industry Expert
Tom Chevalier | TOC | Association of Meter Operators
Dawn Matthews | DAM | UKPN (LDSO)
Meg Wong | MEW | Stark (HHDC)
Richard Brady | RIB | WPD (LDSO)
Daniel Lewis | DAL | EDF (MOA)
Michael Messenger | MIM | IMServ (HHDC)
Stuart Jackson | STJ | C&C (TAA)
Kevin Walker. | KEW | E.ON (MOA)
Dan Rynne | DAR | IMServ (MOA)
Andy Hume | ANH | IMServ (MOA)
Paul Gregory | PAG | C&C (TAA)
Jono Liddell | JOL | Smartest Energy (Supplier)
Peter Gray | PEG | SSE (Supplier)
Holly Mills | HOM | EDF (MOA)

## Closed Actions
Meeting Number | Paper Number | Action Number | Action | Person Responsible | Month Raised | Month Closed | Actions Taken | Action Status
45 |  | 31.02 | KH agreed to investigate outstanding Non-Compliances (NCs) for CT/VTs in the Distribution Network Operator (DNO) areas to compare with RCs CT/VT data and the NMTES to see what’s missing. | SIW | 2018-01-01 | 2021-04-01 | Report obtained from TAA containing CT/VT information for outstanding non-compliances. Awaiting NMTES data. Action to remain open January 2018 Update: No data yet received from RC. Action to remain open. May 2018 Update: Waiting for data from RC. When the data was first submitted, ELEXON had asked for more data. The TAMEG advised RC to submit any data which is available so that ELEXON can make a recommendation as to whether the data can be used July 2018 Update: ELEXON will pick up this action after the completion of 31.03 (below). October 2018 Update: See below (31.03) April 2019 Update: See below (31.03) July 2019 Update: See below (31.03) Oct 2019 Update: Awaiting additional resource in order to progress this action. Jan 2020 Update: This action is dependent on Action 31.03. Oct 2020 Update: TAA to check what CTs the outstanding non-compliances are against. Jan 2021 Update: Elexon have escalated this action internally and it has been deemed low priority against current work streams. April 2021 Update: Consolidated into Action 43.03. | Closed
45 |  | 31.03 | ELEXON will take a paper to SVG to get RCs data onto NMTES so the related CT/VT NCs can be cleared. | CHD | 2018-05-01 | 2021-04-01 | Awaiting response from RC for the NMTES data. May 2018 Update: Waiting for data from RC. When the data was first submitted, ELEXON had asked for more data. The TAMEG advised RC to submit any data which is available so that ELEXON can make a recommendation as to whether the data can be used July 2018 Update: ELEXON is currently investigating data which has been made available. ELEXON to provide an update at the next meeting. October 2018 Update: Analysis of data ongoing. Lack of resource time has delayed progress. April 2019 Update: Awaiting additional resource in order to progress this action. July 2019 Update: Awaiting additional resource in order to progress this action. Oct 2019 Update: Awaiting additional resource in order to progress this action. Jan 2020 Update: Awaiting additional resource in order to progress this action. October 2020 update: Awaiting additional resource in order to progress this action. Jan 2021 Update: See 31.02. April 2021 Update: Consolidated into Action 43.03. | Closed
45 |  | 32.02 | MS noted all the issues regarding compliance certificates and agreed to set up a working group to discuss the issues in more detail to add new requirements to BSCP601. | MIS | 2021-04-01 | 2021-07-01 | On-going. Pending working group set up. May 2018 Update: No further update July 2018 Update: No further update October 2018 Update: No further update April 2019 Update: With Change Team. No update. Thanks to Antony for providing a list of Outstations which may not be supported. July 2019 Update: no further update October 2019 Update: no further update Jan 2020 Update: no update, this is still with the change team. October 2020 Update: no further update. Jan 2021 Update: to be raised at CoP review to determine whether it could be in-scope April 2021 Update: Consolidated into Action 43.03 | Closed
45 | 43.03 | 43.03 | Elexon resolved to draw up a list of risks associated with removing the SVA CoPs 3 and 5 non-compliances. Review existing data on National Measurement Transformer Error Statement (NMTES), inform future work. Make decision on whether SVG paper is required to update NMTES following analysis. | MIT/CHD |  |  | Jan 2021 Update: The TAA have extracted the required data and are in the process of reviewing. April 2021 Update: TAA submitted data to Elexon. Elexon consolidate actions 31.02 and 31.03 into 43.03. July 2021: Progress made on confirming Ron Cook’s data in NMTES. October: Closing action - Consolidated into action 46.08 | Closed
45 |  | 44.01 | A TAMEG member asked if D0215s were requested when they are not required, likely through automated processes. TAMEG members agreed to investigate this in their internal systems. | MIT |  |  | April 2021: Verbal Update to be provided in TAMEG45 meeting, following receipt of outcomes of TAMEG member investigation into internal systems. July 2021: TAMEG agreed D0215 required further investigation through an issue group, to be raised by DAM as per 44.02. | Closed
45 |  | 44.03 | Elexon took away an action to see if they could add a CVA Category to the Trading Dispute spreadsheet to make this clearer | KEP |  |  | April 2021: CVA added to Trading Disputes report where possible. Trading Disputes noted as General are GSP Disputes where the MSID is not currently known. When MSID is known, the report will be updated. | Closed
45 |  | 45.05 | A TAMEG Member stated that the huge volumes have reduced the value of D0215 flows. A TAMEG Member suggested an issue group be set up before progressing a Change Proposal. The TAMEG agreed. | DAW |  |  | July 2021: Duplicate of 44.02. | Closed
45 | 45.02 | 45.02 | A TAMEG Member added that BSCP502 does contain allowances for low load conditions. Elexon will review the Desktop Audit Local Working Instruction (LWI) to ensure low load conditions are captured. | CHD |  |  | July 2021: Document review in progress, will update once new LWI version is on the website Action Closed | Closed
45 | 44.02 | 44.02 | A TAMEG member suggested an Issue Group or a draft Change Proposal (CP), could be the best starting point for investigating the usefulness of D0215s. DM agreed to raise this, dependant on the outcome of 44.01. (TAMEG members agreed to investigate this in their internal systems.) | DAM |  |  | April 2021: Dependant on action 44.02. July 2021: Update required for DAM October: Action to be closed - Paper added to agenda | Closed
45 | 45.04 | 45.04 | A TAMEG Member noted that Single Line Diagram (SLD) non-compliance data showed Distribution Network Operators (DNOs) in a bad light, particularly as there no requirement to provided SLDs. Elexon replied that Desktop Audits are a data gathering exercise, to ascertain where data is available and its quality. Elexon added that rate of SLDs submissions continue to be low and will be reviewing whether to persist with SLDs to be included in the evidence submission. | SIW |  |  | July 2021: SLD evidence submission to be suspended, until such time that the issue is discussed at Issue Group 93 (CoP Review). Action to remain open October 2021: TAA has been instructed to stop raising Non-Compliances related to SLDs until a requirement is placed in the CoPs (Issue 93). November 2021: | Closed
46 | 46.02 | 46.02 | A TAMEG member noted that they were raising an Issue Group, with the Issue form currently going through internal review. The next steps would be to go out for external review. Elexon took an action to circulate this to all TAMEG members, when it was complete. | MIS |  |  | October 2021: Issue form circulated to TAMEG members, agenda item has been added to TAMEG 47. | Closed
46 | 46.04 | 46.04 | A TAMEG member identified that this issue would be ongoing but the National Measurement Transformer Error Statement (NMTES) that was under development would help identify the average errors on these measurement transformers. Elexon also noted that they would accept NMTES data as evidence for the Overall Accuracy check. The Chair suggested a BSC Party (or Elexon) could raise a Change Proposal to remove the requirement to confirm Overall Accuracy. TAMEG noted that Issue 93 Group had been considering this approach. There was some discussion around burdens that TAMEG felt would be better discussed at Issue 93 Group. Elexon agreed to raise this with the Issue 93 Group. | MIS |  |  | October 2021: Overall accuracy and appropriate burden covered under issue 93 group actions, CP raised to help MOAs confirm overall accracy. Sub group to be held to discuss CT ratio and minimum burden. | Closed
46 | 46.06 | 46.06 | Elexon highlighted that the TAA received inaccurate data, and required the data in kWh but some parties were data sending in MWh and had to convert data to kWh. A TAMEG member suggested that the TAA should do this as there is more room for error when the parties are asked to manipulate data. The Chair agreed that in the future the TAA could perform this task, given that the party informs them of the granularity of the data, and Elexon could consider this change. | MIS |  |  | October 2021: Elexon has considered this, MOAs should be able to covert data to correct granularity. | Closed
47 | 47.01 | 47.01 | Elexon suggested adding an indication or caveat on the report and slides to show the proportion of errors found against the number of Desktop Audits completed per participant. This would be a fairer way to have the stats presented, and prevent an impression of bad performance where a large number of Desktop Audits had been completed by one participant. | SIW |  |  | January 2022 - Duplicate of 45.01, can be closed. | Closed
45 | 45.01 |  | TAMEG stats showed the trend of non-compliances over time, and that stats need proportionality to be meaningful. Elexon stated that it would review the stats ahead of the July TAMEG meeting | SIW |  |  | July 2021: Action on hold until release of TAAMT2 (on 5 July), due to changes to reporting. Elexon noted they had a meeting with C & C (the TAA) about the reporting tool in the Technical Assurance Agent Management Tool 2 (TAAMT2), they also noted a ‘drop-in session’ to discuss the new tool that Elexon were intending to organise for the beginning of August 2021. October 2021: The TAAMT2 system is now live, and a Stats Report has been produced. Elexon would welcome further input from TAMEG members on what they would like to see in future reports January 2022: The TAMEG Stats report has been updated in line with these requests. | Closed
45 | 45.03 |  | The TAA added whether a newscast could be issued to ensure HH data is in line with the three days of data. Elexon responded that a newscast may not be the most appropriate step but would investigate how it could best be communicated. | SIW |  |  | July 2021: New three day Settlement Data functionality in TAAMT2, will monitor success rate to determine if further action required. October 2021: Elexon and the TAA continue to explore the best way to engage with certain parties that may not be able to provide data for the required period. January 2022: Elexon propose closing this action and dealing with any issues on an individual participant basis. | Closed
45 | 45.07 |  | A TAMEG Member referenced the GSP group disputes and if the root cause will turn into CVA metering category if it is a metering issue identified. Elexon stated that it can only be changed once information is available. Elexon agreed to change the status for closed disputes. | MTH |  |  | July 2021: Update required October 2021: This will be changed on future reports. January 2022: The requested amendments have now been made. | Closed
46 | 46.03 |  | TAMEG discussed if the responsibility to perform the Overall Accuracy calculation was with the MOA or the TAA. The consensus was that the MOA should have the capability of doing the calculation and that the TAA should check these calculations. A TAMEG member noted that there may be some value in knowing the breakdown between the records not being available and the failure to do the calculation. The TAA agreed to investigate. | LIY |  |  | October 2021: Elexon do not believe that non-compliance data does not allow for a breakdown between the records not being available and the failure to do the calculation. The TAA will investigate further. January 2022: The TAA have confirmed that non-compliance data does not allow for a breakdown between the records not being available and the failure to do the calculation. | Closed
46 | 46.05 |  | It was proposed that Elexon could notify Licensed Distribution System Operators (LDSOs) of how they have performed in comparison to their peers. This would allow these Parties to put into place action plans to improve their Commissioning, and proactively improve, rather than to be notified by PAB and have to act reactively. Elexon agreed to look into how they would action this. TAMEG agreed with this informal action plan route, as opposed to formal Error and Failure Resolution (EFR) plans. | SIW |  |  | October 2021: Under consideration January 2022: If the TAMEG agree with the methodology used, this can be progressed using the proportional figures used for peer comparison in the January TAMEG Stats Report. | Closed
47 | 47.02 |  | A Member asked how they could know which party reference belonged to their organisation: when looking at the chart they were not able to easily detect which party member was which. Elexon advised that this was something that can be notified to individual parties upon request, and agreed to send the Member their information. | SIW |  |  | January 2022: The participant has been provided with the requested data. | Closed