## Summary
Cross Code Engagement Spreadsheet As part of Ofgem’s Code Governance Review (CGR) the Code Administration Code of Practice (CACoP), was established. The CACoP is a cross energy industry code document and aims to provide consistency in the approach and level of service associated with industry codes modification processes. It contains 13 principles to facilitate convergence and transparency in code Modification processes. One of these principles (Principle 13) seeks to ensure cross Code coordination to aid the progression of changes efficiently where modifications impact multiple Codes. As part of meeting Principle 13, this Action Log was created and is populated by each Code Administrator to detail current and forthcoming changes within their codes. Gemserv publish this updated spreadsheet accordingly on the MRASCo every second Wednesday of the month, following updates from other Code Administrators. If you have any queries regarding the changes provided in this spreadsheet, please contact the relevant Code Administrator.

## SPAA
Code | Change Reference | Title of Change | Description | Cross Code Meeting Date | Status of Change within the Process | Link to CP | System Impacts | Implementation Date | Impact on BSC? | Impact on MRA? | Impact on DCUSA? | Impact on SPAA? | Impact on UNC? | Impact on iGT UNC? | Impact on CUSC | Impact on Dcode | Impact on STC | Impact on Grid Code | Impact on SECAS
SPAA | CP 14/283 | ‘Record Presence of AMR and Provider (Transitional Change)’ | This change was raised to help identify the presence of Advanced Metering at customer sites by to prefixing organisations acting in an AMR capacity with a specific value included in the three-character Organisation Short Code. This is a temporary solution until CP14/284 introduces a new Asset Class Code to record such devices at project Nexus implementation. | 2015-05-06 | Final | CP14/283 |  | 2015-02-23 | [5 empty] | UNC Mod 0487S
SPAA | CP 15/301 | 'Changes to the Change of Supplier Meter Reading Process for Smart Meters' | This CP seeks to introduce new processes to enable the Old and New Supplier to communicate the readings for Cumulative and Time of Use Registers directly with each other for DCC serviced Smart Meters. | 2016-02-03 | Rejected by industry and Ofgem; Smart COS sub-committee reconvened in June 2016 look at alternative options; Smart COS meetings to be held 27 and 28 June with the view of identifying options, drafting a consultation and agreeing consultation questions | CP15/301 | DTN or IX | Indicative date June 2017 but yet TBC | BSC P302 implemented | A consequential change will be required to the MRA. | No | N/A | Yes - level of impact depending on solution | No | No | No | No | No | No
SPAA | CP 16/334 | Introduction of Smart Prepayment Change of Supplier Exceptions Process | This CP seeks to set out a number of Supplier obligations in relation to the Smart Prepayment Change of Supplier Exceptions Process. |  | Impact Assessment |  |  | 2016-11-03 | No | Raised concurrently with MAP CP 0275 | No | N/A | No | No | No | No | No | No | No

## DCUSA
Code | Change Reference | Title of Change | Description | Cross Code Meeting Date | Status of Change within the Process | Link to CP | System Impacts | Implementation Date | Impact on BSC? | Impact on MRA? | Impact on DCUSA? | Impact on SPAA? | Impact on UNC? | Impact on iGT UNC? | Impact on CUSC | Impact on Dcode | Impact on STC | Impact on Grid Code | Impact on SECAS
DCUSA | DCP 239 | Alignment of DCP 195A Smart Meter Installation Forecasts submission dates with DECC reporting | In light of DCP 195A Suppliers are obligated to provide a forecast of Smart Meter installations to distribution businesses on a quarterly basis.The intent of this proposal is to amend the date that suppliers are required to submit their Smart Meter Installation Forecast Report to align with date that suppliers submit their forecasts to DECC. | 2015-06-03 | Implemented | DCP 239 | This change builds on DTC CP 3336 | Implemented on 01/06/2015
DCUSA | DCP 179 | ‘Amending the CDCM tariff structure’ | This change amends the CDCM tariff structure by introducing half hourly metered tariffs for current transformer (CT) metered customers and whole current (WC) metered customers. | 2015-07-08 | Implemented | DCP 179 |  | 2015-04-01 | P300 & P272
DCUSA | DCP 259 | CMP223 - Enduring Generation User Commitment | To incorporate changes in the CCCM to reflect the changes resultant from CUSC Modification Proposal CMP223, approved by the Authority on 16th July 2015. |  | Implemented | DCP 259 |  | 2016-04-01 | [6 empty] | Aligns the DCUSA with CMP223
DCUSA | DCP 235 | ‘Provision of Meter Asset Installation Information’ | This change proposes to place obligations on Suppliers and Distributors so that Suppliers procure their Meter Operator Agents to provide service termination equipment information to Distributors, unless the Distributor has already informed the Meter Operator Agent that the information is not required. | 2015-09-02 | This CP has been withdrawn | DCP 235 |  | 2015-11-03 |  | SPF0084
DCUSA | DCP 209 | 'Resolving Unregistered Customers' | This change seeks to introduce an industry wide unregistered consumers process through the improvement of communications with unregistered customers, placing obligations on Suppliers and Distributors and setting out processes for managing unregistered customers. | 2016-01-06 | Voting | DCP 209 |  | 2016-11-03 |  | Proposed addition of a note to the MRA dataflows.
DCUSA | DCP 268 | DUoS Charging Using HH Settlement Data | To facilitate a transition to half-hourly (HH) settlement for non-half hourly (NHH) customers by moving to a time band charging basis, based on the HH (profiled) data used in settlement. |  | Consultation | DCP 268 |  | 2018-04-01 | P339
DCUSA | DCP 251 / DCP 252 | Clarification And Extension Of The Application Of LDNO Tariffs Under The CDCM and EDCM | These changes seek to determine whether the current applicability of the CDCM and EDCM is set out clearly enough in respect of licenced DNOs who operate outside their distribution services area and whether LDNO tariffs should also apply to networks owned and operated under licence exemption. |  | Consultation | DCP 251 DCP 252 |  |  | Change of arrangements to how Unlicensed Customers are charged could have an impact upon both the MRA and BSC in relation to data flows or arrangements for operation

## GRID CODE
Code | Change Reference | Title of Change | Description | Cross Code Meeting Date | Status of Change within the Process | Link to CP | System Impacts | Implementation Date | Impact on BSC? | Impact on MRA? | Impact on DCUSA? | Impact on SPAA? | Impact on iGT UNC? | Impact on CUSC | Impact on Dcode | Impact on STC | Impact on Grid Code | Impact on SECAS
Grid Code | GC0036 | Review of Harmonics Assessment Standards and Processes | The Review of Harmonics Assessment Standards and Processes Workgroup was established to examine and make recommendations to review the standards and processes employed by electricity transmission and distribution network owners to assess harmonics and, in particular, produce a report describing any changes that are considered necessary to Engineering Recommendation G5/4-1 (Planning Levels for harmonic Voltage Distortion and the Connection of Non-Linear Equipment to Transmission Systems and Distribution Networks in the UK) | 2015-09-02 | At Workgroup | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0036/ | [8 empty] | Yes
Grid Code | GC0048 | Joint GCRP/DCRP Workgroup on GB Application of RfG | This workgroup will set those parameters left to national interpretation in the Requirements for Generators European Network Code and make sure that the GB codes align with it - so making necessary changes to the Grid Code, Distribution Code and supporting documents or Engineering Recommendations | 2015-09-02 | At Workgroup | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0048/ | [8 empty] | Yes
Grid Code | GC0075 | Hybrid Static Compensators | Power Park Module developers have been installing Hybrid STATCOM / SVC’s, which provide a portion (typically 50% to 75%) of their reactive capability from switched reactors and capacitors. Some of these devices have restrictions preventing repeated switching in a short period which can be seen as inconsistent with the concept of "continuously-acting" control which is required by the Grid Code. Interested parties believe clarification is required of the Grid Code requirements on these devices and that it would be beneficial to form a Workgroup to develop proposals for clearer and more appropriate requirements on Hybrid STATCOM / SVC performance | 2015-09-02 | At Workgroup - report being drafted | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0075/ |  | Not known | [7 empty] | Yes
Grid Code | GC0035/79 | Frequency Changes during Large Disturbances and their effect on the total system | The proposal is looking at 1) whether there is still a need for RoCoF based Loss of Mains protection, 2) the costs, benefits and risks of change to recommend RoCoF settings; and 3) the need for a requirement for equipment to withstand a specified Rate of Change of Frequency | 2015-09-02 | At Workgroup | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0035-GC0079/ |  | Not known | [6 empty] | Yes
Grid Code | GC0087 | Development of Grid Code Frequency Response Provisions | Proposals to develop the Frequency Response provisions of the Grid Code under GC0022 did not reach a conclusion. National Grid believes that there are a number of outstanding defects with the Frequency Response provisions of the Grid Code which should be addressed in a new Workgroup | 2015-09-02 | At Workgroup | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0087/ |  | Not known | [5 empty] | Yes
Grid Code | GC0090 | GB Implementation of the HVDC European Network Code | European Network Codes (ENCs) are being developed as one of the requirements of the Third Energy Package, which sets directives and regulations obligating member states to co-ordinate European electricity networks. Their purpose is to encourage connection of new renewable generation, support a co-ordinated approach to system stability and security, and encourage greater market competition to reduce consumer costs. HVDC – sets functional requirements for HVDC connections including offshore HVDC networks which connect Offshore generation schemes. | 2015-09-02 | At Worksgroup | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0090/ | [9 empty] | Yes
Grid Code | GC0091 | GB Implementation of the DCC European Network Code | European Network Codes (ENCs) are being developed as one of the requirements of the Third Energy Package, which sets directives and regulations obligating member states to co-ordinate European electricity networks. Their purpose is to encourage connection of new renewable generation, support a co-ordinated approach to system stability and security, and encourage greater market competition to reduce consumer costs. Demand Connection (DCC) – sets functional requirements for new demand Users and Distribution Network connections to the Transmission System and includes Demand Side Response capabilities, as well as responsibilities on TSOs/DNOs. | 2015-09-02 | At Workgroup | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0091/ | [8 empty] | Yes
Grid Code | GC0092 | Using National Grid Network Models for Long Term Planning | This proposal seeks to modify the Grid Code to allow the Distribution Network Operators (DNO) to use National Electricity Transmission Study Network Data Files for planning purposes | 2015-09-03 | With Authority for decision | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0092/
Grid Code | GC0093 | Assessment of System Warnings | This proposal seeks to modify the Grid Code to make a change to the name of a Notice of Inadequate System Margin (NISM) as part of a wider work package (outside the Grid Code) designed to provide clarity to system warning hierarchy and protocols |  | At Consultation | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0093/
Grid Code | GC0095 | GB Implementation of the TSOG European Network Code | This is a GB workgroup to progress the implementation of the Transmission System Operation Guideline (TSOG) European Network Code |  | At Workgroup | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0095/ |  |  | Yes |  |  |  |  | Yes | Yes | Yes

## BSC
Code | Change Reference | Title of Change | Description | Cross Code Meeting Date | Status of Change within the Process | Link to CP | System Impacts | Implementation Date | Impact on BSC? | Impact on MRA? | Impact on DCUSA? | Impact on SPAA? | Impact on UNC? | Impact on iGT UNC? | Impact on CUSC | Impact on Dcode | Impact on STC | Impact on Grid Code | Impact on SECAS
BSC | P302 | Improve the Change of Supplier Meter read and Settlement process for smart Meters | The existing Non Half Hourly (NHH) Change of Supplier (CoS) process is complicated, relying on multiple information flows being sent between new and old Suppliers and Supplier Agents. Due to the number of flows of data being sent the process is prone to error. When the data flows are not sent or cannot be processed by the recipient, delays occur which can result in inaccurate data entering Settlement. The costs of resolving these delays and process errors are borne by Suppliers, Supplier Agents and ultimately the consumer. P302 proposes changes to the Code and BSCPs to amend the CoS process to make use of the enhanced functionality that smart Meters will provide and improve the passing of timely and accurate consumption data into Settlement. | 2016-01-06 | Approved - Awaiting Implementation | https://www.elexon.co.uk/mod-proposal/p302/ | DTC | 2016-06-30 |  | DTC CP 3469 DTC CP 3470 MRA SPF 0089 |  | CP 15/301
BSC | P318 | Change of Party ID/Company Number Through Enabling Assignment | P318 seeks to enable a BSC Party to change its its Company Number in order to reassign its rights and obligations under the BSC without going through the full Market Exit and Market Entry procedures. The intention of this Modification is for this to apply when such a change is of an administrative nature only. | 2016-01-06 | Approved - Awaiting Implementation | https://www.elexon.co.uk/mod-proposal/p318/ |  | 2016-02-25 |  | MRA may need a consequental change to their processes to support the P318 solution.
BSC | P320 | Reporting on Profile Classes 5 – 8 Metering Systems after the implementation of P272 | The implementation of P272 would require changes to the existing PARMS Serials to report any non-compliance. The Proposer believes that a Committee report would be a more suitable reporting tool than PARMS Serials and proposes to remove the PARMS Serial reporting requirements introduced by P272. Reporting P272 non-compliance using a Committee report would also remove the proposed Supplier Charge under P272. | 2016-01-06 | Approved - Awaiting Implementation | https://www.elexon.co.uk/mod-proposal/p320/ |  | 2017-04-01 | P272 | The solution requires provision of ad-hoc ECOES data on a monthly basis. MEC has approved the data licence. More details on the delivery of service still need to be agreed
BSC | CP1434 | Amend the three digit numeric Line Loss Factor Class Code to an alphanumeric Code | CP1434 proposes to change the three-digit numeric LLFC code to a three-character alphanumeric code (digits 0-9 and capital letters A-Z excluding I and O), increasing the number of LLFCs per DSO to 39,303. | 2016-01-06 | Approved - Awaiting Implementation | https://www.elexon.co.uk/change-proposal/cp1434/ | DTC, SVAA, MDD, NHHDA s/w, Pool Reporting tool of PARMS | 2016-06-30 | P300 | DTC CP 3472
BSC | CP1446 | Allow smart CoS agreed Disputed Reads to be entered into Settlement | CP1446 proposes to amend the process for correcting disputed Change of Supplier (CoS) reads for smart Meters that will be introduced by P302 ‘Improve the Change of Supplier Meter read and Settlement process for smart Meters’. These changes will allow each Supplier (old and new) and its Supplier Agents to be able to process any corrections independently of the other. This will remove the risk of flows failing validation due to the two Suppliers using different configurations for the Meter. | 2016-01-06 | Approved - Awaiting Implementation | https://www.elexon.co.uk/change-proposal/cp1446/ |  | 2016-06-30 | P302 | MRA SPF 0089
BSC | Issue 62 | Amending the BSC arrangements to allow ELEXON to tender for the Uniform Network Code Gas Performance Assurance Framework Administrator (PAFA) role | Under the gas Uniform Network Code (UNC) there are two Modifications which are seeking to introduce performance assurance arrangements into the gas market for the first time. The Issue 62 Proposer believes that ELEXON has significant experience and understanding of performance assurance techniques in the energy industry and has transferable skills and knowledge that would potentially meet the criteria for the appointment of the PAFA, should Ofgem approve MOD506. The Proposer would therefore like to explore the potential for the BSC arrangements to be changed to allow ELEXON to bid for the gas PAFA contract. | 2016-01-06 | Assessment | https://www.elexon.co.uk/smg-issue/issue-62/ |  | N/A | P330 |  |  |  | MOD506/506A | MOD506/506A
BSC | P330 | Allowing ELEXON to tender for the Uniform Network Code Gas Performance Assurance Framework Administrator (PAFA) role | Approved Uniform Network Code (UNC) Modification 0506V will introduce performance assurance arrangements into the gas market for the first time, and will require a competitive tender exercise to appoint an independent Gas Performance Assurance Framework Administrator (PAFA)The P330 Proposer believes that ELEXON has significant experience and understanding of performance assurance techniques in the energy industry, and has transferable skills and knowledge that potentially meet the criteria for the appointment of the PAFA. This Modification therefore seeks to amend the BSC arrangements to allow ELEXON to bid for the Gas PAFA contract.. | 2016-01-06 | Assessment | https://www.elexon.co.uk/mod-proposal/p330/ |  | TBC |  |  |  |  | MOD506/506A | MOD506/506A
BSC | CP1464 | Requiring HH consumption data to be processed to appropriate precision | The existing data flows for Half Hourly (HH) site data only provide for consumption data to be sent to BSC Parties and Supplier Agents to the nearest 100 Watt hours (Wh). However, smart Meters that meet the requirements of the Smart Metering Equipment Technical Specifications (SMETS) are capable of providing data to the nearest Wh, and the HH consumption data of smaller customers will need to be processed to the nearest Wh. CP1464 proposes to introduce an obligation on Suppliers and Half-Hourly Data Collectors (HHDCs) to process data to the nearest Wh where data to that granularity can be obtained from the Meter. |  | Committee Decision | https://www.elexon.co.uk/change-proposal/cp1464/ | DTC | 2017-06-29 |  | DTC CP 3492

## MRA
Code | Change Reference | Title of Change | Description | Cross Code Meeting Date | Status of Change within the Process | Link to CP | System Impacts | Implementation Date | Impact on BSC? | Impact on MRA? | Impact on DCUSA? | Impact on SPAA? | Impact on UNC? | Impact on iGT UNC? | Impact on CUSC | Impact on Dcode | Impact on STC | Impact on Grid Code | Impact on SEC
MRA | DTC CP 3472 | Amending the LLFC ID to an alphanumeric format | The approved BSC CP1434 will amend the format of the Line Loss Factor Class (LLFC) Identifier (ID) to a three-character alphanumeric format. Consequential changes are required to the J0147 ‘Line Loss Factor Class Id’ within the DTC to deliver this solution | 2015-10-07 | DTC CP 3472 was accepted | DTC CP 3472 | DTC | 2016-06-30 | Consequential change from BSC CP1434 | DTC
MRA | MRA CP 0241 | Removal of references to the UPRN from the MRA | This CP forms part of a suite of changes to remove the Unique Property Reference Number (UPRN) from the Master Registration Agreement (MRA) and its products. | 2016-02-03 | Accepted at MDB_16_0128 | N/A |  | 2016-06-30 |  | MRA/MAP/DTC
MRA | MAP CP 0275 | Introduction of Smart Prepayment Change of Supplier Exceptions Process | This CP seeks to set out a number of Supplier obligations in relation to the Smart Prepayment Change of Supplier Exceptions Process. |  |  |  | MAP14 |  |  | MAP |  | Corresponding change raised under SPAA
MRA | DTC CP 3491 | Conventions for Meter Register IDs on smart meters | This CP seeks to standardise use of Meter Register IDs on Data and Communications Company (DCC) serviced smart meters to ensure time of use register readings are correctly recorded. |  | Impact Assessment - Vote at MDB_16_0630 | DTC CP 3491 | DTC | 30/06/2016 (to be amended at MDB_16_0630) | Consequential change from BSC P302 | DTC
MRA | DTC CP 3491A | Conventions for Meter Register IDs on smart meters (Alternate) | DTC CP 3491A provides and alternate change to DTC CP 3491 and seeks to standardise use of Meter Register IDs on Data and Communication Company (DCC) service smart meters to ensure time of use register readings are recorded correctly. It also specifies standardised conventions for register IDs against time pattern regimes. |  | Impact Assessment - Vote at MDB_16_0630 | DTC CP 3491A | DTC | 30/06/2016 (to be amended at MDB_16_0630) | Consequential change from BSC P302 | DTC
MRA | DTC CP 3492 | Increasing the precision of data items relating to Half-Hourly (HH) Advances | Meters compliant with the Smart Metering Equipment Technical Specifications (SMETS) can collect HH consumption data to the Watt hour (Wh). The existing data items relating to HH consumption data need to be increased to allow for three decimal places to ensure Settlement accuracy. |  | Impact Assessment - Vote at MDB_16_0728 |  | DTC | 29th June 2017 | BSCCP 1464 | DTC

## UNC
Code | Change Reference | Title of Change | Description | Cross Code Meeting Date | Status of Change within the Process | Link to CP | System Impacts | Implementation Date | Impact on BSC? | Impact on MRA? | Impact on DCUSA? | Impact on SPAA? | Impact on UNC? | Impact on iGT UNC? | Impact on CUSC | Impact on Dcode | Impact on STC | Impact on Grid Code | Impact on SECAS
UNC | 526 | Identification of Supply Meter Point pressure tier | Aims to improve the communication of the Supply Meter Point Pressure Tier by the Gas Transporter (GT) to the Shipper/Supplier/MAM |  | Workgroup assessment | Modification | No | To be considered | [5 empty] | Similar scope to Modifcation iGT 075
UNC | 532 | Implementation of Non Effective Days (Project Nexus transitional modification) | This Modification Proposal identifies arrangements relating to the requirement for ‘non-effective days’ to enable an orderly and efficient transition from current UNC arrangements to the UNC regime identified with UNC Modifications 0432, 0434 and 0440 |  | Ofgem decision pending | Modification | Transitional arrangements to support Nexus implementation | To be considered | [5 empty] | Similar scope to Modifcation iGT 072
UNC | 565 | Central Data Service Provider: General framework and obligations | This Modification Proposal identifies the framework and principal obligations and terms under which the Central Data Service Provider (CDSP) will operate under the UNC. It also provides for the creation of a Data Services Contract (DSC) as a UNC ‘code referenced document’. |  | Workgroup assessment | Modification | To be considered | To be considered | [5 empty] | Potentially impacts iGT UNC governance arrangements for Central Agency
UNC | 574 | Creating the permission to release supply point data to the Theft Risk Assessment Service (TRAS) | This is an enabling modification, which seeks to create the necessary permissions in UNC for supply point data to be provided to the Theft Risk Assessment Service (TRAS) to increase the accuracy of the service. |  | Workgroup assessment | Modification | To be considered | To be considered |  |  |  | May have an indirect impact on SPAA
UNC | 582 | Amendments to reflect separation in legal ownership of NTS and National Grid owned LDZs to facilitate the sale of National Grid's Gas Distribution Business | National Grid Gas plc intends to sell a majority stake in its Gas Distribution Business. The new business would no longer be known as National Grid Gas Distribution. It is necessary to modify the UNC to reflect the separation in ownership of the NTS and the 4 LDZs currently comprising National Grid Gas Distribution prior to completion of the sale process. |  | Workgroup assessment | Modification | To be considered | To be considered |  |  |  | May have an indirect impact on SPAA |  | Potentially impacts iGT UNC governance arrangements for Central Agency

## CUSC
Code | Change Reference | Title of Change | Description | Cross Code Meeting Date | Status of Change within the Process | Link to CP | System Impacts | Implementation Date | Impact on BSC? | Impact on MRA? | Impact on DCUSA? | Impact on SPAA? | Impact on UNC? | Impact on iGT UNC? | Impact on CUSC | Impact on Dcode | Impact on STC | Impact on Grid Code | Impact on SECAS
CUSC | CMP244 | Set final TNUoS tariffs at least 15 months ahead of each charging year' | Extending period for setting TNUoS tariffs to 15 months |  | FMR due to be issued to the Authority - awaiting a decision | CMP244 |  | Not known | [8 empty] | Yes - STC-P 4-1
CUSC | CMP249 | Clarification of Other Charges (CUSC 14.4) - Charging arranngements for customer requested delay and backfeed' | Aims to include the principles underpinning the CEC before TEC policy within Section 14 of the CUSC | 2016-06-22 | Post Workgroup Consultation stage | CMP249 |  | Not Known
CUSC | CMP250 | Stabilising BSUoS with at lesat a twelve month notice period' | Aims to eliminate BSUoS volatility and unpredicatablilty by propsing to fix the value of BSUoS over the course of a season | 2016-06-08 | Post Workgroup Consultation stage | CMP250 |  | Not Known | Potentially - to be confirmed by workgroup
CUSC | CMP251 | Removing the error margin in the cap on total TNUoS recovered by generation and introducing a new charging element to TNUoS to ensure compliance with EU Commission Regulation 838/2010' | Aims to ensure that these is no risk of non-compliance with EU Regualtion 838/2010 by removing the error margin introduced by CMP224 | tbc | Post Workgroup Consultation stage | CMP251 |  | Not Known
CUSC | CMP255 | Revised definition of the upper limit of Generation Charges in the charging methodology with removal of the reference to the 27% charging cap | aims to remove the requirement for the generation allocation of costs to revert to 27% if the limits to generation charges imposed by European Commission Regulation no longer apply | 2016-06-24 | CA Consultation Stage | CMP255 |  | Not known
CUSC | CMP256 | Potential consequential changes to the CUSC as a result of CMP244 | Proposes that any sections of the CUSC outside of Section 14 are modified to reflect any changes to Section 14 deemed appropriate by the CMP244 Workgroup |  | FMR due to be issued to the Authority - awaiting a decision | CMP256 |  | Not known | [6 empty] | Being progressed alongside CMP244 |  | Yes - STC-P 4-1 with CMP244
CUSC | CMP259 | Clarification of decrease in TEC as a Modification | seeks to allow for a User to request both a TEC reduction and a TEC increase in the form of a single modification application | tbc | Post Workgroup Consultation stage | CMP259 |  | Not known
CUSC | CMP260 | TNUoS Demand charges for 2016/17 during the implementation of P272 following approval of P322 and CMP247 | aims to give the option for metering systems that are registered on Measurement Class E-G on or before 01/04/2016 to be treated as HH for the purposes of calculating the actual annual liability |  | FMR issued to the Authority - awaiting a decision | CMP260 |  | Not Known
CUSC | CMP261 | Ensuring the TNUoS paid by Generators in GB in Charging Year 2015/16 is in compliance with the €2.5/MWh annual average limit set in EU Regulation 838/2010 Part B (3) | aims to ensure that there is an ex post reconciliation of the TNUoS paid by GB generators during charging year 2015/16 which will take place in Spring 2016 with any amount in excess of the €2.5/MWh upper limit being paid back, via a negative generator residual levied on all GB generators who have paid TNUoS during the period 1st April 2015 to 31st March 2016 inclusive. | 2016-06-21 | Workgroup development stage | CMP261 |  | Not Known
CUSC | CMP262 | Removal of SBR/DSBR Costs from BSUoS into a “Demand Security Charge | aims to create a new cost recovery mechanism, a “Demand Security Charge” specifically for recovery of all SBR/DSBR costs, which is only levied on demand side Balancing Mechanism Units (BMUs). | 2016-06-09 | Post Workgroup Consultation stage | CMP262 |  |  | Potentially - to be confirmed by workgroup
CUSC | CMP264 | Embedded Generation Triad Avoidance Standstill | seeks to make changes to the Transport and Tariff Model and billing arrangements to remove the netting of output from New Embedded Generators until Ofgem has completed its consideration of the current electricity transmission Charging Arrangements (and any review which ensues) and any resulting changes have been fully implemented. | tbc | Workgroup development stage | CMP264 |  |  | Potentially - to be confirmed by workgroup
CUSC | CMP265 | Gross charging of TNUoS for HH demand where embedded generation is in Capacity Market | specifically seeks to address the issue that half hourly metered (HH) demand for TNUoS purposes is currently charged net of embedded generation. CMP265 has been proposed as urgent, we are awaiting a decision from Ofgem on this. | tbc | Workgroup development stage | CMP265 |  |  | Potentially - to be confirmed by workgroup

## DCODE
Code | Change Reference | Title of Change | Description | Cross Code Meeting Date | Status of Change within the Process | Link to CP | System Impacts | Implementation Date | Impact on BSC? | Impact on MRA? | Impact on DCUSA? | Impact on SPAA? | Impact on UNC? | Impact on iGT UNC? | Impact on CUSC | Impact on Dcode | Impact on STC | Impact on Grid Code | Impact on SECAS
DCode |  | Engineering Recommendation G81 (parts 1-7) | Framework for new LV housing development installations, for new Industrial and Commercial underground connections and for contestable, diversionary and reinforcement works not exceeding 33kV | 2016-03-10 | Published | http://www.energynetworks.org/electricity/engineering/engineering-documents/engineering-documents-overview.html |  | 28/04/16 | No | No | No | No |  | No | No | Yes | No | No | No
DCode |  | The ENA DG Connection Guides | Annual Revision to the Guides. There are four separate Distributed Generation Connection Guides. The Guides are intended to help owners or developers of Distributed Generation, to connect their generating plant to one of the UK's electricity distribution networks. | 2016-03-10 | Published | http://www.energynetworks.org/electricity/engineering/distributed-generation/dg-connection-guides.html |  | 2016-05-05 | No | No | No | No |  | No | No | Yes | No | No | No

## STC
Code | Change Reference | Title of Change | Description | Cross Code Meeting Date | Status of Change within the Process | Link to CP | System Impacts | Implementation Date | Impact on BSC? | Impact on MRA? | Impact on DCUSA? | Impact on SPAA? | Impact on iGT UNC? | Impact on CUSC | Impact on Dcode | Impact on STC | Impact on Grid Code | Impact on SECAS
STC

## iGT UNC
Code | Change Reference | Title of Change | Description | Cross Code Meeting Date | Status of Change within the Process | Link to CP | System Impacts | Implementation Date | Impact on BSC? | Impact on MRA? | Impact on DCUSA? | Impact on SPAA? | Impact on UNC? | Impact on iGT UNC? | Impact on CUSC | Impact on Dcode | Impact on STC | Impact on Grid Code | Impact on SECAS
iGT UNC | iGT039 | Use of a Single Gas Transporter Agency (Project Nexus) | All iGTs will be required to use the GDNs’ agent for the delivery of the common processes as detailed in the iGT UNC and the large transporters Agency Services Agreement. | 2015-11-09 | Authority Consent Received | Link | UK Link | 2016-10-01 |  |  |  |  | Yes
iGT UNC | iGT056 | Provision of the UPRN | Pipeline Operators will be required to include the UPRN as part of the premise address details for each supply point. | 2015-11-09 | Workgroup Development | Link | UK Link | TBC
iGT UNC | iGT075 | Identification of Supply Meter Point Pressure Tiers | To improve communication of the Supply Meter Point Pressure Tier by the iGT to Shipper/Supplier/MAM | 2015-11-09 | Workgroup Development | Link |  | TBC
iGT UNC | iGT072 | Non-effective Days for Cutover to Single Service Provision | This modification creates six non-effective to enable data preparation and cutover to the arrangements created by iGT039 - Use of a single Gas Transporter agency for the common services and systems and processes required by the iGT UNC | 2015-11-09 | Authority Consent Received - Implementation Indefinitely Deferred | Link | UK Link | TBC
iGT UNC | iGT082 | iGT Single Service Provision, noneffective Days for cutover in 2016 | This modification creates [seven] non-effective Days from [24th September 2016 to 30th September 2016] inclusive, to enable data preparation and cutover to the arrangements created by modification 039 - Use of a single Gas Transporter agency for the common services and systems and processes required by the iGT UNC. The proposal seeks to replace IGT072 which originally anticipated modification 039 being implemented on October 1st 2015. | 2015-11-09 | Workgroup Development | Link | UK Link | TBC |  |  |  |  | Yes

## SEC
Code | Change Reference | Title of Change | Description | Cross Code Meeting Date | Status of Change within the Process | Link to CP | System Impacts | Implementation Date | Impact on BSC? | Impact on MRA? | Impact on DCUSA? | Impact on SPAA? | Impact on UNC? | Impact on iGT UNC? | Impact on CUSC | Impact on Dcode | Impact on STC | Impact on Grid Code | Impact on SECAS
SEC | SECMP 0001 | Updating the SEC to reflect abolition of the National Consumer Council (NCC) | This Modification seeks to update the Code to: - Reflect the transferral of powers from the National Council to Citizens Advice and Citizens Advice Scotland; and - Correct the erroneous reference to the Panel Consumer Member being the Change Board Member. |  | Closed | https://www.smartenergycodecompany.co.uk/docs/default-source/modifications/modification-proposals/secmp-0001---updating-the-sec-to-reflect-abolition-of-the-national-consumer-council-(ncc)-v1-1.pdf?sfvrsn=2 |  | 2014-05-27
SEC | SECMP 0002 | Add New Command to Reset Debt Registers | This proposal seeks to add a new command to allow users to reset any of the debt registers on a meter. |  | Open | https://www.smartenergycodecompany.co.uk/docs/default-source/modificationfiles/secmp0002---modification-proposal-form.pdf?sfvrsn=0 |  | Refinement
SEC | SECMP 0003 | Deficiencies in the Service Request for setting Maximum Demand Configurable Time | Amendments to the DCC User Interface Specification (DUIS) service request 6.18.1 to align with the Great Britain Companion Specification (GBCS). |  | Open | https://www.smartenergycodecompany.co.uk/docs/default-source/modificationfiles/secmp0003---modification-proposal-form.pdf?sfvrsn=0 |  | Refinement
SEC | SECMP 0004 | Inclusion of Meter Serial Number data item in the Smart Metering Inventory | Addition of Meter Serial Number to the Smart Metering Inventory to enable mapping between data held in the DCC systems, and industry dataflows. |  | Open | https://www.smartenergycodecompany.co.uk/docs/default-source/modificationfiles/secmp0004---modification-proposal-form.pdf?sfvrsn=0 |  | Refinement
SEC | SECMP 0005 | Include Tariff and Register Labels in SMETS2 Devices | Include Tariff Label and Register Labels in smart metering devices and to allow them to be published on the HAN for display to the customer via HAN devices (e.g. IHD). |  | Open | https://www.smartenergycodecompany.co.uk/docs/default-source/modificationfiles/secmp0005---modification-proposal-form.pdf?sfvrsn=0 |  | Refinement
SEC | SECMP 0006 | Specifying the number of digits for device display | Include a specification for the number of digits for devices’ display of meter registers in SMETS2 in relation to the provision of energy measurement information. |  | Open | https://www.smartenergycodecompany.co.uk/docs/default-source/modificationfiles/secmp0006---modification-proposal-form.pdf?sfvrsn=0 |  | Refinement
SEC | SECMP 0007 | Firmware updates to mandated HAN devices | This Modification Proposal proposes including the capability to update firmware Over-The-Air (OTA) for mandated HAN devices (IHD / PPMID / HCALCS) via the DCC’s infrastructure. |  | Open | https://www.smartenergycodecompany.co.uk/docs/default-source/modificationfiles/secmp0007---modification-proposal-form.pdf?sfvrsn=0 |  | Refinement
SEC | SECMP 0008 | Provision of a Service Request error response for quarantined Service Requests | Provide a new DUIS Service Request error response to give DCC Service Users visibility of quarantined Service Requests following a breach of the DCC’s Anomaly Detection Threshold and / or the individual DCC Service User’s Anomaly Detection Threshold. |  | Open | https://www.smartenergycodecompany.co.uk/docs/default-source/modificationfiles/secmp0008---modification-proposal-form.pdf?sfvrsn=0 |  | Refinement
SEC | SECMP 0009 | Centralised Firmware Library | Establishment of a repository of firmware images, with access provided to all Parties responsible for the management of SMETS1 and/or SMETS2 meters. |  | Open | https://www.smartenergycodecompany.co.uk/docs/default-source/modificationfiles/secmp0009---modification-proposal-form.pdf?sfvrsn=0 |  | Refinement
SEC | SECMP 0010 | Introduction of triage arrangements for Communication Hubs | SEC Supplier parties should be permitted to carry out basic ‘triage’ checks on Communications Hubs following their removal from a consumer’s property. |  | Open | https://www.smartenergycodecompany.co.uk/docs/default-source/modificationfiles/secmp0010---modification-proposal-form.pdf?sfvrsn=0 |  | Refinement
SEC | SECMP 0011 | Inclusion of Meter Asset Provider Participant Code (MAP ID), and Registered Supplier Agents – MOP & MAM Participant Codes in the Smart Metering Inventory | Addition of Meter Asset Provider Participant Code and Registered Supplier Agents – MOP & MAM Participant Codes to the Smart Metering Inventory to enable the efficient management of electricity and gas meters by: a) tracking energy suppliers use of meters; b) tracking the firmware upgrade of meters; c) tracking the removal of meters |  | Open | https://www.smartenergycodecompany.co.uk/docs/default-source/modificationfiles/secmp0010---modification-proposal-form.pdf?sfvrsn=1 |  | Refinement
SEC | SECMP 0012 | Channel selection to support Shared HAN solutions | The proposed modification seeks to amend the SEC and related SEC Subsidiary documents to enable channel selection/masking at the mandated 2.4GHz frequency. |  | Open | https://www.smartenergycodecompany.co.uk/modifications/modification/SECMP-12 |  | Refinement
SEC | SECMP 0013 | Smart meter device diagnostics and triage | The proposal seeks to amend the SEC and DCC’s systems to provide Suppliers with a means of performing quality assurance and fault diagnostics on SMETS2 devices returned by meter operatives. |  | Open | https://www.smartenergycodecompany.co.uk/modifications/modification/SECMP-13 |  | Refinement
SEC | SECMP 0014 | Standardise Formatting of Device ID | Device ID to be formatted to a common standard so that the type of device is included within the EUI-64 identifier. With the EUI-64 identifier provided in EAN 128 barcode format, this allows the installer and supply chain logistic solutions to derive the device type when scanned, and so automate workflow and triggering service requests, removing risk of human error. |  | Open | https://smartenergycodecompany.co.uk/modifications/modification/SECMP-14 |  | Refinement
SEC | SECMP 0015 | GPF timestamp for reading instantaneous Gas values | Instantaneous GSME register values can be read from the Gas Proxy Function. These will not normally be in-line with the readings on the GSME, since the GSME only provides intermittent updates to the GPF, typically once every 30 minutes. Without a timestamp to know when the GSME last updated the GPF, the Supplier cannot know how up to date the information is. |  | Open | https://smartenergycodecompany.co.uk/modifications/modification/SECMP-15 |  | Refinement
SEC | SECMP 0016 | Consideration of "Maximum Credit" value in credit cover calculation | This Modification Proposal seeks to make changes to the SEC Credit Cover Requirement calculation so that it takes into account the credit value specified by an independent credit assessor, which is similar to the approach taken for the Uniform Network Code (UNC). |  | Open | https://smartenergycodecompany.co.uk/modifications/modification/SECMP-16 |  | Refinement
SEC | SECMP 0017 | CGR Phase 3 outcomes: Code Administrator to chair modification Working Groups | The Modification Proposal seeks to amend SEC Section D 'Modification Process' to align it with the outcomes of the Ofgem Code Governance Review (CGR) Phase 3, in that the Code Administrator (SECAS) will chair all Modification Proposal Working Groups, unless the Panel identifies that there is a conflict of interest preventing this from occurring. |  | Open | https://smartenergycodecompany.co.uk/modifications/modification/SECMP-17 |  | Industry Consultation
SEC | SECMP 0018 | Standard Electricity Distributor Configuration Settings | Amendments to the Great Britain Companion Specification (GBCS) to specify the standard Electricity Distributor configuration settings to be applied to an electricity smart meter by the Manufacturer. Application of default configuration settings will reduce the need for Electricity Distributors to apply settings immediately after commissioning. |  | Open | https://smartenergycodecompany.co.uk/modifications/modification/SECMP-18 |  | Submitted to July Panel for approval

## Response
2016
Area | April | May | June | July | August | September | October | November | December | January | February | March
SPAA |  | Changed
DCUSA |  | Changed
GRID CODE
BSC |  | Responded no change
MRA |  | Changed
UNC |  | Changed
CUSC
DCODE
STC
IGT UNC
SEC |  | Changed