## Introduction
Forward Work Plan
Background
Ofgem published its final proposals for the Code Governance Review Phase 3 (CGR3) in March 2016. One of the proposals makes recommendations for Code Administrators to develop a forward work plan, to enable code administrators to manage change at a strategic level.
The objective of this Forward Work Plan is to coordinate the project management of ‘major’ industry change, through on-going oversight of the end-to-end delivery of significant programmes and central systems changes.
Scope
The scope of the Forward Work Plan is based on the annually agreed areas. The areas for 2017 are listed below: * Smart metering * Half Hourly Settlement * European harmonisation * Faster and more reliable switching
Disclosure
The information has been provided by Code Administratrators, to help inform Code Panels and the energy industry, and does not necessarily reflect the view of specific Code Panels. Note the version history below for details of Code Administrators who were not able to provide data for this plan.
Need more information?
For more information regarding a specific change, please contact the responsible Code Administrator:
Code Administrator | Code
ElectraLink Ltd | Distribution Connection Use of System Agreement (DCUSA)
Supply Point Administrator Agreement (SPAA)
ELEXON | Balancing and Settlement Code (BSC)
Energy Networks Association | Distribution Code
Gemserv | iGT Uniform Network Code (IGT UNC)
Master Registration Agreement (MRA)
Smart Energy Code (SEC)
Joint Office of Gas Transporters | Uniform Network Code (UNC)
National Grid | Connection and Use of System Code (CUSC)
Grid Code
System Operator – Transmission Owner Code (STC)
Version History: Forward Work Plan V1.0
This Forward Work Plan contains change updates for Febuary 2017 and offers a best view as of 16 March 2017.
Please be aware that as the previous Forward Work Plan is currently being consulted on by Code Panels, ELEXON have produced this Forward Work Plan for the interim period. The updates have been drawn from publically available information, provided in each Code's Change Registers and the cross-Code Centralised Modification Register that was published on 13 March 2017.

## Headlines
Headlines
The Forward Work Plan headlines provide an overview of the key updates around the priority areas. The headlines are provided when and as they arise.
Area timelines and status
| Code | Change Ref | Title | A1 | A2 | A3 | A4 | A5 | Timeline Ref | S | Raised | S | Imp Decision | S | Imp Date | Assessment Duration | Implementation Duration | Progression State | RAG Status | Commentary | Drivers
Milestones
| Status | Smart Metering status | Smart metering timeline and status | [5 empty] | A1. Smart metering | C | 2011-04-01 | E | 2020-12-31 |  |  | 3562 | -44196 |  | AT RISK | 22 out of 32 live changes are at risk, as well as four milestones due to the DCC go-live delay. This gives smart metering an overall 'at risk' status. | Government policy
| Status | Elective HH Settlement status | Elective Half Hourly Settlement timeline and status | [5 empty] | A2. Elective HH Settlement | C | 2014-04-04 | C | 2017-06-29 |  |  | 1182 | -42915 |  | AT RISK | 7 out of 18 live changes are at risk. This gives elective HH Settlement an overall 'at risk' status. | Ofgem
| Status | Mandatory Half Hourly Settlement status | Mandatory Half Hourly Settlement timeline | [5 empty] | A2. Mandatory HH Settlement | C | 2016-11-11 | E | 2018-06-30 |  |  | 596 | -43281 |  | AT RISK | All changes to enable mandatory HH Settlement should be in place by the first half of 2018. Currently there is only one change planned to enable mandatory HH Settlement. This gives mandatory HH Settlement an overall 'at risk' status. ACTION: Code bodies to consider when to raise changes to enable mandatory HH Settlement. | Ofgem
| Overall Status | European Harmonisation status | European Harmonisation timeline and status | [5 empty] | A3. European harmonisation |  |  | E | 401769 |  |  | 401769 | -401769 |  | AT RISK
| Status | Faster switching status | Faster switching timeline and status | [5 empty] | A4. Faster and more reliable switching | C | 2014-06-16 | E | 2019-01-01 |  |  | 1660 | -43466 |  | ON TRACK | 1 out of 4 live changes are 'on track', this gives faster switching an overall 'on track' status. Ofgem view is for new arrangements to go live in 2019. | -
Area 1. Smart Metering
* The overall status of smart metering is 'on track'. This is because all 32 live changes are on track. * Ofgem published 'DCC Price Control Decision: Regulatory Year 2015/16'. The document sets out Ofgem’s decisions on the costs reported by the Data Communications Company (DCC) under its price control for 2015/16 and on the DCC’s latest cost forecasts.
Area 2. Half Hourly Settlement
* The overall status of Half Hourly Settlement is 'on track'. This is because 15 of the 16 live changes are on track. * DCUSA CP (DCP) 268 'DUoS Charging Using HH Settlement Data' was issued for consultation on 17 February 2017. This is the second consultion by the DCUSA Workgroup. There is a potential cross code impact on the BSC.
Area 3. European Harmonisation
* The overall status of European Harmonisation is 'on track'. This is because of the 13 live changes under European Harmonsiation, 12 are 'on track' and one has been identified as 'at risk'. * Discussions continue on how required changes will be coordinated and implemented within the codes. To facilitate coordination, upcoming European Network Code (ENC) changes have been identified within the BSC, CUSC, DCode, Grid Code and STC * Code Administrators presented their plans for ENC implementation to Ofgem on 14 March 2017. In the meeting, Code Administrators agreed for this project plan to be the sinlge view on ENC implementation. * The European Member States’ formally voted to approve the text of the Electricity Balancing Guideline on 16 March 2017.
Area 4. Faster Switching
* The overall status of Faster Switching is 'on track'. This is because all 7 milestones are 'on track'. * The Switching Programme is in the planning phase, as such there are currently no live changes being progressed under Faster Switching. * Ofgem provided notice of the upcoming consultation 'Switching Programme - Blueprint Phase consultation'.
Area 5. Code Specific
* The CMA published its updated guidance on the CMA’s approach to market investigations. * Ofgem published "The Futures of Domestic Energy Consumption". The paper outlines some of the key changes to the energy landscape for domestic consumers over the coming decade. These include the growth of smart technology within homes, new business models and the role of third party intermediaries in the retail market.
All changes to enable mandatory HH Settlement should be in place by the first half of 2018. Currently there is only one change planned to enable mandatory HH Settlement. However, it is anticpated that a SGR will be adopted to facilitate mandatory HH Settlement.

## Horizon (All)
Horizon Scanning
Horizon scanning provides provides a high level snap shot of the key legislative and regulatory changes expected to impact the industry. The changes are represented in terms of impact, certainty and anticipated implementation.
1 -2 years
2- 5 years
5 years +
Firm deliverables
Deliverables in definitition
Deliverables undefined
Policy undefined
Ones to watch
BREXIT
(L) (Medium)
UK General Election (2020)
(L) (Medium)
Smart meter roll out complete
(I) (Medium)
Faster Switching and Centralised Registration
(I) (High)
NEXUS Ph2
(I) (High)
FGO Ph2 Imp. (Q2 17)
(I) (Medium)
EU CAM (Am & Inc)
(R) (Medium)
Priority Svs Register
(R) (Medium)
EU Tariff Code
(R) (High)
Alternative Sources of Gas
(I) (Low)
Gemini Rewrite
(I) (High)
Gas Settlement Evolution
(R) (High)
RAASP
(I) (High)
Pan-EU harmonisation complete
(I) (HIgh)
EU Reform
(R) (High)
CMA
(R) (High)
KEY
Industry impacted:
Industry-wide change
Electricity
Gas
Driver of change:
(I) - Industry
(L) - Legislation
(R) - Regulatory
Level of impact:
(High)
(Medium)
(Low)
Mandatory HH Settlement
(R) (High)

## Commentary 2+ yrs
This sheet sets out the changes identified in the 2-5 years timescale on the Horizon
Horizon item | What is it? | Which Codes might be affected? | What happens next? | For more information
Nexus Phase 2 | During specification and build of the new UK Link systems under Project Nexus, a number of 'further requirements' were identified by the UNC Workgroup that participants believed would add value if made available. These were too late to be included in the inital release and were therefore compiled into a Requirements Log that was to be subject to more detailed assessment in due course. | UNC iGT UNC | It is anticipated that further UNC modifications would be required to enable the changes identified. No work is anticipated on this until after the current Nexus deliverables - Phase 1 and RAASP - are more certain in H1 2017. | The Requirements Log can be viewed here: http://www.gasgovernance.co.uk/nexus/090816 A diagram showing how the various UNC modifications interact to form Project Nexus is available here: http://www.gasgovernance.co.uk/sites/default/files/Nexus%20Modification%20interactions%20v2.0_0.pdf
Alternative Sources of Gas | This is an early-planning placeholder to focus some thinking about how the various future sources - e.g. shale, LNG, biomethane - might impact on the operation of GB's gas networks. | UNC iGT UNC | tbc | http://www2.nationalgrid.com/UK/Industry-information/Future-of-Energy/Gas/
Gemini Rewrite | Gemini provides GB's gas nominations, trades, energy balancing and entry/exit capacity processes and invoicing. The operating system behind the central Gemini system (operated by Xoserve on behalf of National Grid Gas) has been in use since 2005 and will require replacement or refreshing. | UNC | tbc | http://www.xoserve.com/index.php/our-systems/gemini/
UK General Election 2020 | Potential change of emphasis in Energy Policy leading to strengthening of Retail reform, acceleration of alternative sources of energy, penetration of electric vehicles etc | ALL | tbc
Brexit | UK exit from the EU is not currently expected to have a significant impact on GB Codes. Working assumption for the industry is that GB will continue to access the Single Energy Market, meaning that existing interconnection point arrangements will remain. In the near term, GB is legally obliged to comply with EU Regulations and subsequent Codes and work to adapt GB Codes continues. | ALL | Awaiting clear direction from central government via BEIS and Ofgem. | tbc
Smart Meter Roll-out complete | As roll-out of Smart meters approaches completion, the availability of reliable and frequent data items should permit the industry to improve many processes, such as Settlement, Forecasting, Balancing and capacity management | ALL | Ofgem are leading work under the "Future Energy Insights" banner that should inform direction on these matters. | https://www.ofgem.gov.uk/publications-and-updates/ofgem-s-future-insights-series-overview-paper
Gas Settlement Evolution | Currently a placeholder for a piece of work that is only just starting - essentially to think about how Settlement could be further improved. | UNC iGT UNC | Initial discussions are taking place at the Change Overview Board | http://www.gasgovernance.co.uk/COB
All changes to enable mandatory HH Settlement should be in place by the first half of 2018. Currently there is only one change planned to enable mandatory HH Settlement. However, it is anticpated that a SGR will be adopted to facilitate mandatory HH Settlement.

## Horizon (Gas)
Horizon Scanning - Gas
Horizon scanning provides provides a high level snap shot of the key legislative and regulatory changes expected to impact the industry. The changes are represented in terms of impact, certainty and anticipated implementation.
1 -2 years
2- 5 years
5 years +
Firm deliverables
Deliverables in definitition
Deliverables undefined
Policy undefined
Ones to watch
RAASP
(I) (High)
EU CAM (Am & Inc)
(R) (Medium)
Gemini Rewrite
(I) (High)
EU Tariff Code
(R) (High)
Alternative Sources of Gas
(I) (Low)
Gas Settlement Evolution
(R) (High)
NEXUS Ph2
(I) (High)
FGO Ph2 Imp. (Q2 17)
(I) (Medium)
KEY
Industry impacted:
Industry-wide change
Electricity
Gas
Driver of change:
(I) - Industry
(L) - Legislation
(R) - Regulatory
Level of impact:
(High)
(Medium)
(Low)

## Horizon (Elec)
Horizon Scanning - Electricity
Horizon scanning provides provides a high level snap shot of the key legislative and regulatory changes expected to impact the industry. The changes are represented in terms of impact, certainty and anticipated implementation.
1 -2 years
2- 5 years
5 years +
Firm deliverables
Deliverables in definitition
Deliverables undefined
Policy undefined
Ones to watch
EU Reform
(R) (High)
CMA
(R) (High)
Pan-EU harmonisation complete
(I) (HIgh)
Mandatory HH Settlement
(R) (High)
KEY
Industry impacted:
Industry-wide change
Electricity
Gas
Driver of change:
(I) - Industry
(L) - Legislation
(R) - Regulatory
Level of impact:
(High)
(Medium)
(Low)

## A1. Smart metering
Area 1. Smart Metering
Smart Metering aims to faciliate the roll out electricity and gas smart Meters across Great Britain.
Headlines
* The overall status of smart metering is 'on track'. This is because all 32 live changes are on track. * Ofgem published 'DCC Price Control Decision: Regulatory Year 2015/16'. The document sets out Ofgem’s decisions on the costs reported by the Data Communications Company (DCC) under its price control for 2015/16 and on the DCC’s latest cost forecasts.
Code | Change Ref | Title | A1 | A2 | A3 | A4 | A5 | Timeline Ref | S | Raised | S | Imp Decision | S | Imp Date | Assessment Duration | Implementation Duration | Progression State | RAG Status | Commentary | Drivers
Status | Smart metering status | Smart metering timeline and status | [5 empty] | Smart metering status | C | 2011-04-01 | E | 2020-12-31 |  |  | 3562 | -44196 |  | ON TRACK | The overall status of smart metering is 'on track'. This is because all 21 live change are on track. | Government policy
Today | Today | Today's date | [5 empty] | Today | C | 2017-03-23 | C | 2017-03-24 | - | N/A | 1 |  |  | ON TRACK | - | -
BSC | P272 | Mandatory Hlaf Hourly Settlement for Profle Classes 5-8 | Yes | Yes | No | No | No | BSC-P272 | C | 2011-05-20 | C | 2014-10-29 | C | 2017-04-01 | 1258 | 2143 | Awaiting Implementation | On Track | - | -
Milestone | SMETS1 | SMETS1 published | [5 empty] | SMETS1 published | C | 2012-12-18 | C | 2012-12-19 | - | N/A | 1 |  |  | ON TRACK | Smart Metering Equipment Technical Specifications published by DECC on 18/12/2012. | -
Milestone | SMETS2 | SMETS2 published | [5 empty] | SMETS2 published | C | 2013-01-24 | C | 2013-01-25 | - | N/A | 1 |  |  | ON TRACK | Smart Metering Equipment Technical Specifications 2 (draft) published by DECC on 24/01/2013. | -
DCUSA | DCP 204 | Smart Metering Related Amendments to Schedule 8 | Yes | No | No | No | No | DCUSA-DCP 204 | C | 2014-02-27 | C | 2016-02-23 | C | 2016-09-01 | 726 | 917 | Implemented | On Track | - | -
Milestone | Rollout consultation | Government consultation on the smart metering rollout strategy | [5 empty] | Rollout consultation | C | 2015-03-24 | C | 2015-05-19 | - | N/A | 56 |  |  | ON TRACK | - | -
Milestone | Rollout consultation response | Government conclusions and response to the smart metering rollout strategy consultation | [5 empty] | Rollout consultation response | C | 2015-07-31 | C | 2015-08-01 | - | N/A | 1 |  |  | ON TRACK | - | -
SEC | SECMP0002 | Add New Command to Reset Debt Registers | Yes | No | No | No | Yes | SEC-SECMP0002 | C | 2016-02-19 | E | TBD | E | 2018-06-01 | 1 | 833 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0004 | Inclusion of Device Serial Number data item in the Smart Metering Inventory | Yes | No | No | No | Yes | SEC-SECMP0004 | C | 2016-02-19 | E | TBD | E | 2018-06-01 | 1 | 833 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0005 | Include Tariff and Register Labels in SMETS2 Devices | Yes | No | No | No | Yes | SEC-SECMP0005 | C | 2016-03-01 | E | TBD | E | 2018-06-01 | 1 | 822 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0006 | Specifying the number of digits for device display | Yes | No | No | No | Yes | SEC-SECMP0006 | C | 2016-03-01 | E | TBD | E | 2018-06-01 | 1 | 822 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0007 | Firmware updates to mandated HAN devices | Yes | No | No | No | Yes | SEC-SECMP0007 | C | 2016-03-01 | E | TBD | E | 2018-06-01 | 1 | 822 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0008 | Provision of a Service Request error response for quarantined Service Requests | Yes | No | No | No | Yes | SEC-SECMP0008 | C | 2016-03-01 | E | TBD | E | 2018-06-01 | 1 | 822 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0009 | Centralised Firmware Library | Yes | No | No | No | Yes | SEC-SECMP0009 | C | 2016-03-01 | E | TBD | E | 2018-06-01 | 1 | 822 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0010 | Introduction of triage arrangements for Communication Hubs | Yes | No | No | No | Yes | SEC-SECMP0010 | C | 2016-03-02 | E | TBD | E | 2018-06-01 | 1 | 821 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0011 | Inclusion of Meter Asset Provider Participant Code (MAP ID) Participant Codes in the Smart Metering Inventory | Yes | No | No | No | Yes | SEC-SECMP0011 | C | 2016-03-22 | E | TBD | E | 2018-06-01 | 1 | 801 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SPAA | CP 16/334 | Introduction of Smart Prepayment Change of Supplier Exceptions Process | Yes | No | No | No | No | SPAA-CP 16/334 | C | 2016-05-01 | C | 2016-10-20 | E | TBD | 172 |  | Awaiting implementation | On Track | Confirmation of authority approval 1 WD after Authority Consent received | n/a
SEC | SECMP0013 | Smart meter device diagnostics and triage | Yes | No | No | No | Yes | SEC-SECMP0013 | C | 2016-05-04 | E | TBD | E | 2018-06-01 | 1 | 758 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0012 | Channel selection to support Shared HAN solutions | Yes | No | No | No | Yes | SEC-SECMP0012 | C | 2016-05-05 | E | TBD | E | 2018-06-01 | 1 | 757 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0015 | GPF timestamp for reading instantaneous Gas values | Yes | No | No | No | Yes | SEC-SECMP0015 | C | 2016-05-31 | E | TBD | E | 2018-06-01 | 1 | 731 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0016 | Consideration of "Maximum Credit" value in credit cover calculation | Yes | No | No | No | Yes | SEC-SECMP0016 | C | 2016-06-03 | E | TBD | E | 2017-06-01 | 1 | 363 | Awaiting Authority Determination | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0018 | Standard Electricity Distributor Configuration Settings | Yes | No | No | No | Yes | SEC-SECMP0018 | C | 2016-06-23 | E | TBD | E | 2018-06-01 | 1 | 708 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
BSC | P347 | Reduction in R1 Read Threshold | Yes | Yes | No | No | No | BSC-P347 | C | 2016-07-01 | E | 2017-02-10 | C | 2017-04-01 | 224 | 274 | Awaiting Implementation | On Track | On 19 January the Panel considered the Sendback Direction from the Authority and approved the revised Final Modification Report for P347. The Panel maintained its recomendation to the Authority that P347 should be rejected. The revised Final Modification Report was submitted to the Authority for decision on 19 January 2017. On 30 January 2017 the Authority determined that P347 should be Approved and implemented on 1 April 2017. | -
SEC | SECMP0019 | ALCS Description Labels | Yes | No | No | No | Yes | SEC-SECMP0019 | C | 2016-07-14 | E | TBD | E | 2017-11-02 | 1 | 476 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
UNC | 0594R | Meter Reading Submission for Advanced & Smart Metering | Yes | No | No | No | No | UNC-0594R | C | 2016-09-02 | 0 | TBD | E | TBD | 1 |  | Request | On Track | This is a UNC Request - to review the arrangements for meter reading submission. A modification is one possible output. | None- Review
SEC | SECMP0021 | Increase Other SEC Party representation for TABASC and SSC | Yes | No | No | No | Yes | SEC-SECMP0021 | C | 2016-10-04 | E | TBD | E | 2017-06-29 | 1 | 268 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0023 | Correct Units of Measure for Uncontrolled Gas Flow Rate | Yes | No | No | No | Yes | SEC-SECMP0023 | C | 2016-10-26 | E | TBD | E | 2018-06-01 | 1 | 583 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0024 | Enduring Approach to Communication Hub Firmware Management | Yes | No | No | No | Yes | SEC-SECMP0024 | C | 2016-10-27 | E | TBD | E | 2018-06-01 | 1 | 582 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0025 | Electricity Network Party Access to Load Switching Information | Yes | No | No | No | Yes | SEC-SECMP0025 | C | 2016-11-18 | E | TBD | E | 2018-06-01 | 1 | 560 | Modification Proposal Submitted | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0028 | Prioritising Service Requests | Yes | No | No | No | Yes | SEC-SECMP0028 | C | 2016-12-07 | E | TBD | E | TBD | 1 |  | Modification Proposal Submitted | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0026 | Changes to the Security Sub-Committee Nomination Process | Yes | No | No | No | Yes | SEC-SECMP0026 | C | 2016-12-12 | E | TBD | E | 2017-03-16 | 1 | 94 | Modification Proposal Submitted | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0027 | Amending Service Request Forecasting | Yes | No | No | No | Yes | SEC-SECMP0027 | C | 2016-12-16 | E | TBD | E | TBD | 1 |  | Modification Proposal Submitted | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0029 | Business Continuity and Disaster Recovery Testing Amendments | Yes | No | No | No | Yes | SEC-SECMP0029 | C | 2016-12-19 | E | TBD | E | TBD | 1 |  | Modification Proposal Submitted | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0030 | Demand Management of DCC Systems | Yes | No | No | No | Yes | SEC-SECMP0030 | C | 2017-01-04 | E | TBD | E | TBD | 1 |  | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0031 | Adding UTRN Functionality to SMETS | Yes | No | No | No | Yes | SEC-SECMP0031 | C | 2017-02-20 | E | TBD | E | TBD | 1 |  | Initial Modification Report | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0032 | Prioritising Prepayment Customers in No WAN Situations | Yes | No | No | No | Yes | SEC-SECMP0032 | C | 2017-02-20 | E | TBD | E | TBD | 1 |  | Initial Modification Report | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0033 | Update to CH Handover Support Materials | Yes | No | No | No | Yes | SEC-SECMP0033 | C | 2017-02-22 | E | TBD | E | TBD | 1 |  | Initial Modification Report | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
Milestone | Large Supplier User Mandate | Large Supplier User Mandate | [5 empty] | All Suppliers use DCC | E | 2017-05-25 | E | 2017-05-26 | - | N/A | 1 |  |  | ON TRACK | - | -
Milestone | Distribution Network Operator User Mandate | Distribution Network Operator User Mandate | [5 empty] | All Suppliers use DCC | E | 2017-10-10 | E | 2017-10-11 | - | N/A | 1 |  |  | ON TRACK | - | -
Milestone | Small Supplier User Mandate | Small Supplier User Mandate | [5 empty] | All Suppliers use DCC | E | 2017-11-25 | E | 2017-11-26 | - | N/A | 1 |  |  | ON TRACK | - | -
Milestone | SMETS1 end | Installation end date for SMETS1 Meters | [5 empty] | SMETS1 end | E | 2018-04-06 | E | 2018-04-07 | - | N/A | 1 |  |  | ON TRACK | - | -
Milestone | Rollout complete | Smart Meter rollout complete | [5 empty] | Rollout complete | E | 2020-12-31 | E | 2021-01-01 | - | N/A | 1 |  |  | ON TRACK | - | -
Note on O19: All estimated implementation dates are the earliest possible implementation dates. These are subject to change.

## A2. Half Hourly Settlement
Area 2. Half Hourly Settlement
Half Hourly Settlement aims to settle all consumers using Half Hourly consumption data.
For more information, please visit the Ofgem website.
Headlines
* The overall status of Half Hourly Settlement is 'on track'. This is because 15 of the 16 live changes are on track. * DCUSA CP (DCP) 268 'DUoS Charging Using HH Settlement Data' was issued for consultation on 17 February 2017. This is the second consultion by the DCUSA Workgroup. There is a potential cross code impact on the BSC.
Code | Change Ref | Title | A1 | A2 | A3 | A4 | A5 | Timeline Ref | S | Raised | S | Imp Decision | S | Imp Date | Assessment Duration | Implementation Duration | Progression State | RAG Status | Commentary | Drivers
Status | Elective HH Settlement status | Elective Half Hourly Settlement timeline and status | [5 empty] | Elective HH Settlement status | C | 2014-04-04 | C | 2017-06-29 |  |  | 1182 | -42915 |  | ON TRACK | The overall status of Elective Half Hourly Settlement is 'on track'. This is because15 of the 16 live changes are on track. | Ofgem
Status | Mandatory Half Hourly Settlement status | Mandatory Half Hourly Settlement timeline | [5 empty] | Mandatory HH Settlement status | C | 2016-11-11 | E | 2018-06-30 |  |  | 596 | -43281 |  | ON TRACK | The overall status of Mandatory HH Settlement is 'on track'. Based on Ofgem's consultation, it is anticpated that Ofgem will make a how to implement mandatory HHS should be taken by the first half of 2018 following their policy and design work. The proposed approach sets out a ‘potential‘ SCR. | Ofgem
Today | Today | Today's date | [5 empty] | Today | C | 2017-03-23 | C | 2017-03-24 | N | N/A | 1 |  |  | On Track | - | -
BSC | P272 | Mandatory Hlaf Hourly Settlement for Profle Classes 5-8 | Yes | Yes | No | No | No | BSC-P272 | C | 2011-05-20 | C | 2014-10-29 | C | 2017-04-01 | 1258 | 885 | Awaiting Implementation | On Track | - | -
DCUSA | DCP 160 | Non-Half Hourly (NHH) Notional Capacity | No | Yes | No | No | No | DCUSA-DCP 160 | C | 2013-01-08 | C | 2016-10-18 | N | n/a | 1379 |  | Authority Rejected the change | On Track | Authority Rejected the change | -
DCUSA | DCP 169 | Seasonal Time of Day (SToD) HH Metered Tariffs in the CDCM | No | Yes | No | No | No | DCUSA-DCP 169 | C | 2013-03-13 | E | TBD | E | TBD | 1 |  | Assessment | At Risk | CP on Hold - Working Group is awaiting Ofgem decision on DCP 228 before deciding on how to proceed with DCP 169. DCP 225 is due to be implemented 1 Apr 2018 | -
BSC | P320 | Reporting on Profile Classes 5 – 8 Metering Systems after the implementation of P272 | No | Yes | No | No | No | BSC-P320 | C | 2015-03-13 | C | 2015-09-09 | C | 2017-04-01 | 180 | 750 | Awaiting Implementation | On Track | - | -
Milestone | Elective HH consultation | Ofgem consultation 'Half-hourly Settlement: the way forward' | [5 empty] | Elective HH consultation | C | 2015-12-17 | C | 2016-01-29 | - | N/A | 43 |  |  | On Track | This consultation is now closed. | -
DCUSA | DCP 262 | Schedule 19 Credit/Re-invoice for HH Specific Data | No | Yes | No | No | No | DCUSA-DCP 262 | C | 2016-01-13 | C | 2016-07-29 | C | 2016-09-01 | 198 | 232 | Implemented | On Track | - | -
DCUSA | DCP 268 | DUoS Charging Using HH settlement data | No | Yes | No | No | No | DCUSA-DCP 268 | C | 2016-03-14 | E | TBD | E | 2018-04-01 |  | 748 | Assessment | On Track | Under Development - Working Group developing the CP solution | -
BSC | P338 | Consequential changes to P272 legal text | No | Yes | No | No | No | BSC-P338 | C | 2016-04-14 | C | 2016-04-14 | C | 2017-04-01 | 0 | 352 | Awaiting Implementation | On Track | - | -
BSC | P339 | Introduction of new Consumption Component Classes for Measurement Classes E-G | No | Yes | No | No | No | BSC-P339 | C | 2016-05-04 | C | 2016-12-08 | C | 2017-04-01 | 218 | 332 | Awaiting Implementation | On Track | - | -
Milestone | Elective HH consultation conclusions | Ofgem consultation decision 'Elective half-hourly settlement: conclusions paper' | [5 empty] | Elective HH consultation conclusions | C | 2016-05-26 | C | 2016-05-27 | - | N/A | 1 |  |  | On Track | The conclusions paper to Ofgem's consultation on elective HH Settlement, published on 26/05/2016. | -
BSC | CP1466 | Removing SMETS compliant Meters from the scope of BSCP601 ‘Metering Protocol Approval and Compliance Testing’ | No | Yes | No | No | No | BSC-CP1466 | C | 2016-06-14 | C | 2016-12-08 | C | 2017-02-23 | 177 | 254 | Implemented | On Track | - | Settlement Reform Advisory Group recommendations
BSC | P346 | Changes to Specific Charges for Elective HH Settlement | No | Yes | No | No | No | BSC-P346 | C | 2016-06-23 | C | 2016-11-10 | C | 2017-04-01 | 140 | 282 | Awaiting Implementation | On Track | Approved. Awaiting implementation in April Standalone release | -
BSC | P347 | Reduction in R1 Read Threshold | Yes | Yes | No | No | No | BSC-P347 | C | 2016-07-01 | E | 2017-02-10 | C | 2017-04-01 | 224 | 274 | Awaiting Implementation | On Track | On 19 January the Panel considered the Sendback Direction from the Authority and approved the revised Final Modification Report for P347. The Panel maintained its recomendation to the Authority that P347 should be rejected. The revised Final Modification Report was submitted to the Authority for decision on 19 January 2017. On 30 January 2017 the Authority determined that P347 should be Approved and implemented on 1 April 2017. | -
BSC | CP1469 | Changes to support the implementation of the SRAG’s recommendations | No | Yes | No | No | No | BSC-CP1469 | C | 2016-07-19 | C | 2016-10-04 | C | 2017-06-29 | 77 | 345 | Awaiting Implementation | On Track | - | Settlement Reform Advisory Group recommendations
DCUSA | DCP 281 | Changes to Schedule 19 – Portfolio Billing | No | Yes | No | No | No | DCUSA-DCP 281 | C | 2016-09-14 | E | TBD | E | 2019-04-01 |  | 929 | Assessment | On Track | Under Development - Working Group developing the CP solution | -
BSC | CP1474 | Updating the CoMC processes to facilitate the elective HH Settlement of SMETS Meters | No | Yes | No | No | No | BSC-CP1474 | C | 2016-10-14 | C | 2017-01-04 | C | 2017-06-29 | 82 | 258 | Awaiting Implementation | On Track | -
BSC | CP1475 | Remove obligation to re-date final NHH Meter readings on CoMC | No | Yes | No | No | No | BSC-CP1475 | C | 2016-10-14 | C | 2017-01-03 | C | 2017-06-29 | 81 | 258 | Awaiting Implementation | On Track | -
Milestone | Mandatory HH consultation | Ofgem 'Consultation on mandatory half-hourly Settlement: aims and timetable for reform' | [5 empty] | Mandatory HH consultation | C | 2016-11-11 | C | 2017-01-06 | - | N/A | 56 |  |  | On Track | Ofgem consultation on mandatory HH Settlement. The proposed timetable is all changes to enable mandatory HH Settlement should be in place by the first half of 2018. An SCR is likely to follow the conclusions from the consultation. | -
Milestone | SCR mandatory HH | SCR for mandatory HH Settlement | [5 empty] | SCR mandatory HH | E | 2017-06-01 | E | 2018-06-30 | - | N/A | 394 |  |  | On Track | These are estimated dates for the SCR, based on when the consultation closes and Ofgem's aspirations for changes in place to enable mandatory HH Settlement by the first half of 2018. | -
BSC | BSC Potential Change 14 | Ofgem SCR on HH Settlement | No | Yes | No | No | No | BSC-BSC Potential Change 14 | E | 2017-06-01 | E | 2018-03-01 | E | 2018-06-28 | 273 | 392 | Upcoming | - | - | -
Milestone | Changes for elective HH | Deadline for changes to facilitate elective HH Settlement | [5 empty] | Changes for elective HH | C | 2017-06-30 | C | 2017-07-01 | - | N/A | 1 |  |  | On Track | The deadlines for changes to facilitate election HH Settlement have been approved. | -
Milestone | Decision on mandatory HH | Ofgem target for decision on if, when, and how to implement mandatory Half Hourly Settlement | [5 empty] | Decsion on mandatory HH | E | 2018-06-30 | E | 2018-07-01 | - | N/A | 1 |  |  | On Track | Ofgem have indicated that the decision will be taken by the first half of 2018, following their policy and design work | -

## A3. European Harmonisation
Area 3. European Harmonisation
European harmonisation aims to ensure that the GB energy market is compliant with European obligations.
For more information, please visit the Ofgem website.
Please be aware SQSS changes have also been provided, as the relevant to European Harmonisation. Please also note that there are differing assumptions on the implementation dates for Electricity Balancing Guidelines (EBGL) changes between Code bodies.
Headline
* The overall status of European Harmonisation is 'on track'. This is because of the 13 live changes under European Harmonsiation, 12 are 'on track' and one has been identified as 'at risk'. * Discussions continue on how required changes will be coordinated and implemented within the codes. To facilitate coordination, upcoming European Network Code (ENC) changes have been identified within the BSC, CUSC, DCode, Grid Code and STC * Code Administrators presented their plans for ENC implementation to Ofgem on 14 March 2017. In the meeting, Code Administrators agreed for this project plan to be the sinlge view of ENC implementation. * The European Member States’ formally voted to approve the text of the Electricity Balancing Guideline on 16 March 2017.
Code | Change Ref | Title | A1 | A2 | A3 | A4 | A5 | Timeline Ref | S | Raised | S | Imp Decision | S | Imp Date | Assessment Duration | Implementation Duration | Progression State | RAG Status | Commentary | Drivers
Status | European harmonisation status | European harmonisation timeline and status | [5 empty] | European harmonisation status |  | 2015-08-01 | E | 2022-01-01 |  |  | 2345 |  |  | ON TRACK | 11 out of 12 live changes are 'on track'. This gives European Harmonisation an overall 'on track' status. | EU Legislation
Today | Today | Today's date | [5 empty] | Today | C | 2017-03-23 | C | 2017-03-24 | - | N/A | 1 |  |  | ON TRACK | - | -
SQSS | GSR012 | Treatment of Interconnectors | No | No | Yes | No | Yes | SQSS-GSR012 | C | 2010-10-05 | E | TBD | E | TBD | 1 |  | Assessment | At Risk | Workgroup meetings need to re-convene following 1 year hiatus. | -
GC | GC0048 | Requirements for Generators - Implementation of European Network Code | No | No | Yes | No | Yes | GC-GC0048 | C | 2013-07-01 | C | TBD | C | 2018-05-17 |  | 1781 | Raised | On Track | This is a workgroup, and it is expected that this workgroup will manage the raising of all additional modifications required to deliver The deadline for EIF is fixed. National Implementation Compliance date is 17/05/2018 | ENC
GC | GC0090 | HVDC - Implementation of European Network Code | No | No | Yes | No | Yes | GC-GC0090 | C | 2015-07-01 | C | TBD | C | 2018-09-29 |  | 1186 | Raised | On Track | This is a workgroup, and it is expected that this workgroup will manage the raising of all additional modifications required to deliver Deadline for EIF is fixed. National Implementation Compliance date is 29/09/2018 | ENC
Milestone | CACM came into force | CACM came into force | [5 empty] | CACM came into force | C | 2015-08-01 |  | 2015-08-02 | - | N/A | 1 |  |  |  |  | ENC
BSC | P329 | Changes to REMIT inside information reporting | No | No | Yes | No | No | BSC-P329 | C | 2015-11-25 | C | 2016-04-19 | C | 2017-06-19 | 146 | 426 | Awaiting Implementation | On Track | This Modification aligns the BMRS with the the Regulation on Wholesale Energy Markets Integrity and Transparency (REMIT) common schemas for inside information web feeds, required by the Agency for the Cooperation of Energy Regulators (ACER) P329 will be implemented as part of the June 2017 BSC Release | REMIT
GC | GC0091 | Application of the the Demand Connection Code - Implementation of European Network Code | No | No | Yes | No | Yes | GC-GC0091 | C | 2016-03-01 | C | TBD | C | 2018-09-07 |  | 920 | Raised | On Track | This is a workgroup, and it is expected that this workgroup will manage the raising of all additional modifications required to deliver. Deadline for EIF is fixed. National Implementation Compliance date is 07/09/2018 | ENC
BSC | P342 | Change to Gate Closure for Energy Contract Volume Notifications | No | No | Yes | No | Yes | BSC-P342 | C | 2016-05-25 | E | 2016-12-08 | C | 2017-11-02 | 197 | 329 | Awaiting Implementation | On Track | This Modification introduce a new deadline for the purpose of submitting Energy Contract Volume Notification (ECVNs) and Metered Volume Reallocation Notifications (MVRNs) for each Settlement Period. This new contract notification deadline would be decoupled from Gate Closure, and would be set 60 minutes after the start of the relevant Settlement Period. P342 will be implemented as part of the November 2017 BSC Release. This Mod may inform the scope of what is proposed under GC and the BSC to meet the CACM requirement on time of submission of interconnector data. | -
GC | GC0095 | GB implementation workgroup for Transmission System Operation Guideline (TSOG) European Network Code | No | No | Yes | No | Yes | GC-GC0095 | C | 2016-05-27 | E | TBD | C | 2018-10-01 |  | 857 | Assessment | On Track | All areas of TSOG are curently held within one workgroup, this may change as modification are raised to deliver respective areas are completed There is a range of Entry into Force dates ranging to October 2018 | ENC
BSC | P344 | Project TERRE implementation into GB market arrangements | No | No | Yes | No | No | BSC-P344 | C | 2016-06-01 | C | 2017-09-21 | E | 2018-09-01 | 477 | 345 | Assessment | On track | Project TERRE is currently set to go-live in Q3 2018. | ENC
UNC | 0597 | Rules for the release of incremental capacity at Interconnection Points | No | No | Yes | No | Yes | UNC-0597 | C | 2016-10-10 | E | 2017-03-31 | E | 2017-04-01 | 172 | 1 | Assessment | On Track | - | EU CAM
UNC | 0598 | Amendments to Capacity Allocations Mechanisms to comply with EU Capacity Regulations | No | No | Yes | No | Yes | UNC-0598 | C | 2016-10-10 | E | 2017-03-31 | E | 2017-04-01 | 172 | 1 | Assessment | On Track | - | EU CAM
UNC | 0599 | Amendments to Capacity Allocations Mechanisms (Interruptible) to comply with EU Capacity Regulations | No | No | Yes | No | Yes | UNC-0599 (withdrawn) | C | 2016-10-10 | C | n/a | C | n/a | 1 |  | Withdrawn | On Track | Withdrawn | EU CAM
GC | GC0097 | European Energy Balancing Guidelines - Replacement Reserves - TERRE | No | No | Yes | No | Yes | GC-GC0097 | E | 2016-11-16 | C | TBD | E | 2019-07-01 |  | 957 | Assessment | On Track | This modification maybe required to address changes associated with project TERRE Deadline for EIF is fixed. This mod is set to be implemented Q3 2019. | ENC
GC | Grid Code Potential Change 1 | Implementation of CACM European Network Code | No | No | Yes | No | Yes | GC-Grid Code Potential Change 1 | E | 2017-01-01 | C | TBD | E | 2018-01-01 |  | 365 | Upcoming | On Track | This modification may be required to address the requirements of the Common Grid Model This mod is currently set to be raised in Q1 2017 Deadline for EIF is fixed. Compliance for CGM is Jan 2018 - and TBC based on methodologies | ENC
GC | Grid Code Potential Change 2 | European Energy Balancing Guidelines - General Compliance | No | No | Yes | No | Yes | GC-Grid Code Potential Change 2 | E | 2017-01-01 | E | TBD | E | 2018-07-01 |  | 546 | Upcoming | On Track | This modification maybe required to address general compliance requirements of the EB GL The mod if currently set to be raised in Q1 2020. Deadline for EIF is fixed. The mod if set to be implemented in Q3 2021. | ENC
GC | Grid Code Potential Change 5 | European RfG Banding and RfG/HVDC requirements | No | No | Yes | No | Yes | GC-Grid Code Potential Change 5 | E | 2017-04-19 | E | TBD | E | 2018-04-01 |  | 347 | Upcoming | On Track | This mod is set to be raised in Q2 2017. This mod is set to be implementedin Q2 2018. | ENC
Milestone | NC ER comes into force | NC ER comes into force | [5 empty] | NC ER comes into force | E | 2017-05-01 | E | 2017-05-02 | - | N/A | 1 |  |  |  |  | ENC
BSC | BSC Potential Change 1 | Time of Interconnector Data Submission | No | No | Yes | No | No | BSC-BSC Potential Change 1 | E | 2017-06-01 | E | 2018-03-01 | E | 2018-06-01 | 273 | 92 | Upcoming | - | A Modification is expected to be raised in April 2017 under Grid Code, to address the CACM requirement. If the Grid Code Modification removes the impact on the BSC, this Modification will be redundant. | ENC
Dcode | Dcode Potential Change 3 | To Implement within the Dcode the Fast Fault Current Injection requirements contained within the EU Network Code - Requirements for Generators | No | No | Yes | No | Yes | Dcode-Dcode Potential Change 3 | E | 2017-06-30 | E | TBD | E | TBD | 1 |  | Upcoming | TBC | Depends on National Grid GC 0048 modification | ENC
GC | Grid Code Potential Change 4 | European Emergency & Restoration Code - System Defence & Restoration Plan | No | No | Yes | No | Yes | GC-Grid Code Potential Change 4 | E | 2017-07-01 | E | TBD | E | 2018-07-01 |  | 365 | Upcoming | On Track | This mod is set to be raised in Q2 2017. This mod is set to be implemente din Q3 2018. | ENC
Milestone | EB GL entry into force | EB GL entry into force | [5 empty] | EB GL entry into force | E | 2017-10-01 | E | 2017-10-02 | - | N/A | 1 |  |  |  |  | ENC
Milestone | Assignment of EB GL where needed | Assignment of EB GL where needed | [5 empty] | Assignment of EB GL where needed | E | 2017-10-01 | E | 2017-10-02 | - | N/A | 1 |  |  |  |  | ENC
Milestone | Application for Exemption from 15 min Settlement | Application for Exemption from 15 min Settlement | [5 empty] | Application for Exemption from 15 min Settlement | E | 2017-10-01 | E | 2017-10-02 | - | N/A | 1 |  |  |  |  | ENC
Milestone | Backstop date for Derogation from Article 55 (imbalance price) | Backstop date for Derogation from Article 55 (Imbalance Price) | [5 empty] | Backstop date for Derogation from Article 55 (Imbalance Price) | E | 2017-10-01 | E | 2017-10-02 | - | N/A | 1 |  |  |  |  | ENC
BSC | BSC Potential Change 2 | Imbalance Price (without derogation) | No | No | Yes | No | No | BSC-BSC Potential Change 2 (without derogation) | E | 2017-10-01 | E | 2018-04-01 | E | 2018-10-01 | 182 | 183 | Upcoming | - | It is assumed that NGET will apply for a derogation for this requirement. If a derogation is approved, this Modification will be included within the scope of Potential Modification 11 "Harmonised Imbalance Settlement". | ENC
BSC | BSC Potential Change 3 | Inclusion of Imbalance Adjustments (without derogation) | No | No | Yes | No | No | BSC-BSC Potential Change 3 (without derogation) | E | 2017-10-01 | E | 2018-04-01 | E | 2018-10-01 | 182 | 183 | Upcoming | - | It is assumed that NGET will apply for a derogation for this requirement. If a derogation be approved, this Modification will be raised on 01/10/19 | ENC
BSC | BSC Potential Change 4 | Align BSC with the Authority's oversight obligation | No | No | Yes | No | No | BSC-BSC Potential Change 4 | E | 2017-10-01 | E | 2018-04-01 | E | 2018-10-01 | 182 | 183 | Upcoming | - | Assignment by BEIS/Ofgem and decisions by Ofgem on how it wishes to approach this requirement | ENC
CUSC | CUSC Potential Change 1 | European Energy Balancing Guidelines - Replacement Reserves | No | No | Yes | No | Yes | CUSC -CUSC Potential Change 1 | E | 2017-10-01 | E | TBD | E | 2018-10-01 |  | 365 | Upcoming | On Track | This mod is set to be raised in Q4 2017. This mod is set to be implemented in Q4 2018. | ENC
STC | STC Potential Change 1 | European TSOG - Multi TSO Training Cooperation | No | No | Yes | No | Yes | STC-STC Potential Change 1 | E | 2017-10-01 | E | TBD | C | 2018-10-01 |  | 365 | Upcoming | On Track | - | ENC
STC | STC Potential Change 2 | European TSOG Implementation - Data Exchange | No | No | Yes | No | Yes | STC-STC Potential Change 2 | E | 2017-10-01 | E | TBD | C | 2018-10-01 |  | 365 | Upcoming | On Track | - | ENC
Dcode | DCRP1702 | Implementation of the Ofgem CGR3 recommendation on Significant Code Review | No | No | Yes | No | Yes | Dcode-DCRP1702 | E | 2017-12-08 | E | TBD | E | TBD | 1 |  | Awaiting Implementation | On Track | RTA submitted on 09/03/17 | CGR3
Dcode | Dcode Potential Change 2 | Changes to DOC 5 of the Distribution Code | No | No | Yes | No | Yes | Dcode-Dcode Potential Change 2 | E | 2017-12-08 | E | TBD | E | TBD | 1 |  | Upcoming | On Track | RTA submitted on 09/03/17 | ENC
STC | STC Potential Change 3 | European TSOG Implementation -Regional Outage Coordination | No | No | Yes | No | Yes | STC-STC Potential Change 3 | E | 2018-01-01 | E | TBD | C | 2018-12-01 |  | 334 | Upcoming | On Track | This mod is set to be raised in Q1 2018 | ENC
Milestone | NGET suspension/restoration proposals | NGET proposals for suspension and restoration | [5 empty] | NGET proposals for suspension and restoration | E | 2018-05-01 | E | 2018-05-02 | - | N/A | 1 |  |  |  |  | ENC
Milestone | ELEXON assigned / delegated | Backstop date for ELEXON assigned / delegated | [5 empty] | Backstop date for ELEXON assigned / delegated | E | 2018-10-01 | E | 2018-10-02 | - | N/A | 1 |  |  |  | GB Legislation for Assignment (would need to changed first, to allow us to be assigned. BEIS will need to write consultation) Derogation requires a contract with NGET, Ofem would need to issue a consultation before this is agreed. | ENC
Milestone | EB GL provisions apply | EB GL provisions apply (assumed) | [5 empty] | EB GL provisions apply (assumed) | E | 2018-10-01 | E | 2018-10-02 | - | N/A | 1 |  |  |  |  | ENC
BSC | BSC Potential Change 5 | Amendments to Imbalance Price | No | No | Yes | No | No | BSC-BSC Potential Change 5 | E | 2018-10-01 | E | 2019-04-01 | E | 2020-04-01 | 182 | 366 | Upcoming | - | If TSO Proposal for activiation purpose do not align with the BSC, this Modification will be raised to amend the imbalance price calculation | ENC
BSC | BSC Potential Change 6 | Align BSC with the TSO's Terms and Conditions | No | No | Yes | No | No | BSC-BSC Potential Change 6 | E | 2018-10-01 | E | 2019-04-01 | E | 2019-10-01 | 182 | 183 | Upcoming | - | If NGET write Ts & Cs in a way that differs from the Ts & Cs of the BSC, this Modification will be raised to align the BSC with the Ts & Cs of the TSO. | ENC
BSC | BSC Potential Change 7 | Project TERRE 2 | No | No | Yes | No | No | BSC-BSC Potential Change 7 | E | 2018-10-01 | E | 2019-07-01 | E | 2020-03-01 | 273 | 244 | Upcoming | - | This Modification will be raised to implement outstanding activities from Project TERRE | ENC
BSC | BSC Potential Change 8 | Unintended exchanges of energy | No | No | Yes | No | No | BSC-BSC Potential Change 8 | E | 2018-10-01 | E | 2019-04-01 | E | 2019-10-01 | 182 | 183 | Upcoming | - | Assumption of assignment. Certainty on whether this Mod if required is based on the provision of information from NGET, on what will be proposed. | ENC
BSC | BSC Potential Change 9 | NGET proposal on specific products | No | No | Yes | No | No | BSC-BSC Potential Change 9 | E | 2018-10-01 | E | 2019-04-01 | E | 2019-10-01 | 182 | 183 | Upcoming | - | If NGET make a proposal on specific products, an assessment will be required to ensure that the understanding of specific products aligns with the BSC. If understanding of specific products in the TSO proposal, differs from the BSC, this Modification will be raised to align the BSC with the proposal. | ENC
BSC | BSC Potential Change 10 | Market Suspension and Restoration Arrangement | No | No | Yes | No | No | BSC-BSC Potential Change 10 | E | 2018-11-01 | E | 2019-08-01 | E | 2020-05-01 | 273 | 274 | Upcoming | - | If NGET makes proposals for rules concerning the suspension and restoration of market activities; and the rules for balancing energy and imbalance settlement during market suspension, that differ from the BSC, this Modification will be raised to align the BSC with the proposals. | ENC
Milestone | UK leaves EU | UK leaves EU (assumed) | [5 empty] | UK leaves EU (assumed) | E | 2019-03-30 | E | 2019-03-31 | - | N/A | 1 |  |  |  |  | ENC
BSC | BSC Potential Change 3 | Inclusion of Imbalance Adjustments (with derogation) | No | No | Yes | No | No | BSC-BSC Potential Change 3 (with derogation) | E | 2019-04-01 | E | 2020-01-01 | E | 2020-10-01 | 275 | 274 | Upcoming | - | It is assumed that NGET will apply for a derogation for this requirement. If a derogation be approved, this Modification will be raised on 01/10/19 | ENC
BSC | BSC Potential Change 11 | Harmonised Imbalance Settlement (Includes Mod 2 with derogation) | No | No | Yes | No | No | BSC-BSC Potential Change 11 | E | 2019-04-01 | E | 2020-01-01 | E | 2020-10-01 | 275 | 274 | Upcoming | - | This Modification will be raised to align the BSC with NGETs proposals to harmonise the main features of imbalance settlement If Potential Modification 2 'Imbalance Price' receives a derogation, it will be included within the scope of this Modification. | ENC
BSC | BSC Potential Change 12 | Project mFRR | No | No | Yes | No | No | BSC-BSC Potential Change 12 | E | 2019-04-01 | E | 2021-01-01 | E | 2021-10-01 | 641 | 273 | Upcoming | - | This Modification will be raised, as an extension of the principles introduced under P344 ' Project TERRE' | ENC
Milestone | Backstop date for RR standard products | Backstop date for RR standard products | [5 empty] | Backstop date for RR standard products | E | 2019-10-01 | E | 2019-10-02 | - | N/A | 1 |  |  |  |  | ENC
BSC | BSC Potential Change 13 | Project TERRE 3 | No | No | Yes | No | No | BSC-BSC Potential Change 13 | E | 2019-10-01 | E | 2020-07-01 | E | 2020-02-27 | 274 | -125 | Upcoming | - | This Modification will be raised to implementation outstanding activities from P344 'Project TERRE' | ENC
GC | Grid Code Potential Change 3 | European Energy Balancing Guidelines - Manual Frequency Restoration Reserves (mFRR) | No | No | Yes | No | Yes | GC-Grid Code Potential Change 3 | E | 2020-01-01 | E | TBD | E | 2021-07-01 |  | 547 | Upcoming | On Track | This modification maybe required to address mFRR requirements of the EB GL This mod is set to be raised in Q1 2020. Deadline for EIF is fixed. This mod is set to be implemented in Q3 2021. | ENC
CUSC | CUSC Potential Change 2 | European Energy Balancing Guidelines - Manual Frequency Restoration Reserves (mFRR) | No | No | Yes | No | Yes | CUSC -CUSC Potential Change 2 | E | 2020-07-01 | E | TBD | E | 2021-07-01 |  | 365 | Upcoming | On Track | This mod is set ot be raised Q3 2020. This mod is set to be implemented in Q3 2021 | ENC
Milestone | The earliest decision on bidding zone change | Earliest decision on bidding zone change | [5 empty] | Earliest decision on bidding zone change | E | 2020-07-01 | E | 2020-07-02 | - | N/A | 1 |  |  |  |  | ENC
Milestone | Backstop date for hamonised Imbalance Settlement | Backstop date for harmonised Imbalance Settlement | [5 empty] | Backstop date for harmonised Imbalance Settlement | E | 2020-10-01 | E | 2020-10-02 | - | N/A | 1 |  |  |  |  | ENC
Milestone | Implementation date for any bidding zone change | Implementation date for any bidding zone change | [5 empty] | Implementation date for any bidding zone change | E | 2021-07-01 | E | 2021-07-02 | - | N/A | 1 |  |  |  |  | ENC
Milestone | Backstop date for FRR standard products | Backstop date for FRR standard products | [5 empty] | Backstop date for FRR standard products | E | 2021-10-01 | E | 2021-10-02 | - | N/A | 1 |  |  |  |  | ENC
Dcode | Dcode Potential Change 1 | Implementation of the requirements of the European Network Code - Demand Connection | No | No | Yes | No | Yes | Dcode-Dcode Potential Change 1 | E | TBD | E | TBD | E | TBD |  |  | Upcoming | On Track | Will be raised at the the time of the GC0048 housekeeping mods | ENC
Dcode | Dcode Potential Change 4 | To Implement within the Dcode the Fault Ride Through requirements contained within the EU Network Code - Requirements for Generators | No | No | Yes | No | Yes | Dcode-Dcode Potential Change 4 | E | TBD | E | TBD | E | TBD |  |  | Upcoming | TBD | Depends on National Grid GC 0048 modification | ENC
Dcode | Dcode Potential Change 5 | To Implement within the Dcode the Frequency Response requirements contained within the EU Network Code - Requirements for Generators | No | No | Yes | No | Yes | Dcode-Dcode Potential Change 5 | E | TBD | E | TBD | E | TBD |  |  | Upcoming | TBD | Depends on National Grid GC 0048 modification | ENC
Dcode | Dcode Potential Change 6 | To Implement within the Dcode the Reactive Power and Voltage Control requirements contained within the EU Network Code - Requirements for Generators | No | No | Yes | No | Yes | Dcode-Dcode Potential Change 6 | E | TBD | E | TBD | E | TBD |  |  | Upcoming | TBD | Depends on National Grid GC 0048 modification | ENC
Dcode | Dcode Potential Change 7 | Implementation of the new Engineering Recommendation G98 | No | No | Yes | No | Yes | Dcode-Dcode Potential Change 7 | E | TBD | E | TBD | E | TBD |  |  | Upcoming | TBD | Target for public consultation Sept 2017 | ENC
Dcode | Dcode Potential Change 8 | Implementation of the new Engineering Recommendation G99 | No | No | Yes | No | Yes | Dcode-Dcode Potential Change 8 | E | TBD | E | TBD | E | TBD |  |  | Upcoming | TBD | TBC | ENC
Dcode | Dcode Potential Change 9 | Implementation of the Transmission System Operators Guidelines | No | No | Yes | No | Yes | Dcode-Dcode Potential Change 9 | E | TBD | E | TBD | E | TBD |  |  | Upcoming | TBD | TBC | ENC

## A4. Faster Switching
Area 4. Faster Switching
Faster and more reliable switching aims to improve customers' experience of switching, leading to greater engagement in the retail energy market by designing and implementing a new switching process that is reliable, fast and cost-effective.
For more information, please visit the Ofgem website.
Headlines
* The overall status of Faster Switching is 'on track'. This is because all 7 milestones are 'on track'. * The Switching Programme is in the planning phase, as such there are currently no live changes being progressed under Faster Switching. * Ofgem provided notice of the upcoming consultation 'Switching Programme - Blueprint Phase consultation'.
Code | Change Ref | Title | A1 | A2 | A3 | A4 | A5 | Timeline Ref | S | Raised | S | Imp Decision | S | Imp Date | Assessment Duration | Implementation Duration | Progression State | RAG Status | Commentary | Drivers
Status | Faster and more reliable switching status | Faster and more reliable switching timeline and status | [5 empty] | Faster and more reliable switching status | C | 2014-06-16 | E | 2019-01-01 |  |  | 1660 | -43466 |  | ON TRACK | There are currently no live changes being progressed. Howeve, 6 of the 7 milestones are 'on track', this gives faster and more reliable switching an overall 'on track' status. Ofgem view is for new arrangements to go live in 2019. | Ofgem
Today | Today | Today's date | [5 empty] | Today | C | 2017-03-23 | C | 2017-03-24 | N | N/A | 1 |  |  | ON TRACK | - | -
Milestone | Next-day switching consultation | Ofgem consultation 'Moving to reliable next-day switching' | [5 empty] | Next-day switching consultation | C | 2014-06-16 | C | 2014-08-11 | - | N/A | 56 |  |  | ON TRACK | Ofgem consultation on reliable next-day switching. Ofgem proposes to lead a programme of work to deliver these policy proposals for 2019. | -
Milestone | Next-day switching consultation conclusions | Ofgem consultation decision on moving to reliable next-day switching | [5 empty] | Next-day switching consultation conclusions | C | 2015-02-10 | C | 2015-02-11 | - | N/A | 1 |  |  | ON TRACK | The conclusions paper to Ofgem's consultation on reliable next-day switching, published on 10/02/2015. | -
Milestone | SCR switching | Switching Significant Code Review launch statement and request for expressions of interest to participate in Programme workgroups | [5 empty] | SCR switching | C | 2015-11-17 | E | 2019-01-01 | - | N/A | 1141 |  |  | ON TRACK | - | -
Milestone | SCR Blueprint | SCR Blueprint Phase | [5 empty] | SCR Blueprint | E | 2016-01-01 | E | 2017-04-01 | - | N/A | 456 |  |  | ON TRACK | - | -
Milestone | SCR DLS | SCR Detailed-Level Specification Phase | [5 empty] | SCR DLS | E | 2016-01-01 | E | 401769 | - | N/A | 359399 |  |  | ON TRACK |  | -
Milestone | SCR Enactment | SCR Enactment Phase | [5 empty] | SCR Enactment | E | 2016-01-01 | E | 401769 | - | N/A | 359399 |  |  | ON TRACK | - | -
Milestone | Deadline for changes for faster and more reliable switching | Deadline for changes to enable faster and more reliable switching | [5 empty] | Deadline for changes to enable faster and more reliable switching | E | 2019-01-01 | E | 2019-01-02 | - | N/A | 1 |  |  | ON TRACK | - | -

## Code Changes
Code Changes
Code Change highlights any live and upcoming changes to assist in the release management. It also provide headline updates for code specific changes that may also be of importance to the industry.
Headlines
* The CMA published its updated guidance on the CMA’s approach to market investigations. * Ofgem published "The Futures of Domestic Energy Consumption". The paper outlines some of the key changes to the energy landscape for domestic consumers over the coming decade. These include the growth of smart technology within homes, new business models and the role of third party intermediaries in the retail market.
Code | Change Ref | Title | A1 | A2 | A3 | A4 | A5 | Timeline Ref | S | Raised | S | Imp Decision | S | Imp Date | Assessment Duration | Implementation Duration | Progression State | RAG Status | Commentary | Drivers
BSC | P329 | Changes to REMIT inside information reporting | No | No | Yes | No | No | BSC-P329 | C | 2015-11-25 | C | 2016-04-19 | C | 2017-06-29 | 146 | 436 | Awaiting Implementation | On Track | - | -
BSC | P342 | Change to Gate Closure for Energy Contract Volume Notifications | No | No | Yes | No | Yes | BSC-P342 | C | 2016-05-25 | E | 2016-12-08 | C | 2017-11-02 | 197 | 329 | Awaiting Implementation | On Track | - | -
BSC | P344 | Project TERRE implementation into GB market arrangements | No | No | Yes | No | No | BSC-P344 | C | 2016-06-01 | C | 2017-09-21 | E | 2018-09-01 | 477 | 345 | Assessment | On track | Project TERRE is currently set to go-live in Q3 2018. | -
BSC | BSC Potential Change 14 | Ofgem SCR on HH Settlement | No | Yes | No | No | No | BSC-BSC Potential Change 14 | E | 2017-06-01 | E | 2018-03-01 | E | 2018-06-28 | 273 | 119 | Upcoming | - | - | -
BSC | CP1465 | Sending revised Meter Technical Details following a change of Meter Operator Agent | No | No | No | No | Yes | BSC-CP1465 | C | 2016-06-13 | C | 2016-09-06 | C | 2017-02-23 | 85 | 170 | Implemented | On track | - | -
BSC | CP1466 | Removing SMETS compliant Meters from the scope of BSCP601 ‘Metering Protocol Approval and Compliance Testing’ | No | Yes | No | No | No | BSC-CP1466 | C | 2016-06-14 | C | 2016-12-08 | C | 2017-02-23 | 177 | 77 | Implemented | On track | - | Settlement Reform Advisory Group recommendations
BSC | CP1469 | Changes to support the implementation of the SRAG’s recommendations | No | Yes | No | No | No | BSC-CP1469 | C | 2016-07-19 | C | 2016-10-04 | C | 2017-06-29 | 77 | 268 | Awaiting Implementation | On track | - | Settlement Reform Advisory Group recommendations
BSC | CP1470 | Housekeeping Change to CoPs 1, 2, 3 and 5 following P266 | No | No | No | No | No | BSC-CP1470 | C | 2016-08-12 | C | 2016-10-04 | C | 2017-02-23 | 53 | 142 | Implemented | On track | - | -
BSC | CP1471 | Housekeeping - discrepancies in the requirements of the CRA URS | No | No | No | No | Yes | BSC-CP1471 | C | 2016-10-04 | C | 2016-10-04 | C | 2017-02-23 | 0 | 142 | Implemented | On track | - | -
BSC | CP1472 | Removal of SVA proving tests for Meters with a pulse multiplier of one | No | No | No | No | Yes | BSC-CP1472 | C | 2016-09-14 | C | 2017-01-24 | C | 2017-02-23 |  |  | Implemented | On track | - | BSC Audit Issue Review Group
BSC | CP1473 | Alteration to the LTV Entry Criteria | No | No | No | No | Yes | BSC-CP1473 | C | 2016-10-05 | E | 2017-01-03 | C | 2017-02-23 |  |  | Implemented | On Track | -
BSC | CP1474 | Updating the CoMC processes to facilitate the elective HH Settlement of SMETS Meters | No | Yes | No | No | No | BSC-CP1474 | C | 2016-10-14 | C | 2017-01-04 | C | 2017-06-29 |  |  | Awaiting Implementation | On Track | -
BSC | CP1475 | Remove obligation to re-date final NHH Meter readings on CoMC | No | Yes | No | No | No | BSC-CP1475 | C | 2016-10-14 | C | 2017-01-03 | C | 2017-06-29 |  |  | Awaiting Implementation | On Track | -
BSC | CP1476 | Facilitation of Incremental LLFs | No | No | No | No | Yes | BSC-CP1476 | C | 2016-10-27 | E | 2017-01-31 | E | 2017-06-29 |  |  | Awaiting Implementation | On Track | - | -
BSC | CP1477 | Updates to BSCP537 Appendix 1 as a result of P283 | No | No | No | No | Yes | BSC-CP1477 | C | 2016-11-07 | E | 2017-04-04 | E | 2017-06-29 | 148 | 86 | Assessment | On Track | - | -
BSC | CP1478 | Automate the loading of the DF Matrix | No | No | No | No | No | BSC-CP1478 | C | 2016-11-22 | E | 2017-02-28 | E | 2017-11-02 | 98 | 247 | Awaiting Implemenation | On Track | - | -
BSC | CP1479 | Updates to the Defined Metering Points in Codes of Practice 1, 2, 3, 5 and 10 | No | No | No | No | Yes | BSC-CP1479 | C | 2016-11-23 | E | 2017-02-20 | E | 2017-11-02 | 89 | 255 | Assessment | On Track | - | -
BSC | CP1480 | Creation of a new authorisation category for corrections to BOA related data | No | No | No | No | No | BSC-CP1480 | C | 2016-11-28 | E | 2017-02-28 | E | 2017-06-29 | 92 | 121 | Assessment | On Track | - | -
BSC | CP1481 | Housekeeping Change to BSCP536 following approval of P339 | No | No | No | No | Yes | BSC-CP1481 | C | 2016-12-14 | E | 2017-01-26 | E | 2017-04-01 | 43 | 65 | Awaiting Implementation | On Track | - | -
BSC | CP1482 | Upgrade of NHHDA and EAC/AA systems from Oracle 11g to version 12c | No | No | No | No | Yes | BSC-CP1482 | C | 2017-01-05 | E | TBD | E | 2017-11-02 |  | 301 | Assessment | On Track | - | -
BSC | CP1483 | Changes to BSCP550 – Shared Metering Arrangements | No | No | No | No | Yes | BSC-CP1483 | C | 2017-01-18 | E | TBD | E | 2017-11-03 |  | 289 | Assessment | On Track | - | -
BSC | P272 | Mandatory Hlaf Hourly Settlement for Profle Classes 5-8 | Yes | Yes | No | No | No | BSC-P272 | C | 2011-05-20 | C | 2014-10-29 | C | 2017-04-01 | 1258 | 885 | Awaiting Implementation | On Track | - | -
BSC | P297 | Receipt and Publication of New and Revised Dynamic Data items | No | No | No | No | Yes | BSC-P297 | C | 2013-07-24 | C | 2014-04-28 | C | TBD | 278 |  | Awaiting Implementation | On Track | Due to further EBS delays, the Panel requested a revised Implementation Date for P297. The revised implementation date is TBD | -
BSC | CP1484 | Introduction of Additional SVAA Validation at SVA Run time | No | No | No | No | Yes | BSC-CP1484 | C | 2017-02-08 | E | TBD | E | 2017-11-03 |  | 268 | Assessment | On Track | - | -
BSC | P308 | Alternative security product for securing credit under the BSC | No | No | No | No | Yes | BSC-P308 | C | 2014-06-04 | E | 2017-02-01 | E | TBD | 973 |  | Withdrawn | At risk | The Proposer’s Representative withdrew Modification P308 on 2 February 2017. | -
BSC | P320 | Reporting on Profile Classes 5 – 8 Metering Systems after the implementation of P272 | No | Yes | No | No | No | BSC-P320 | C | 2015-03-13 | C | 2015-09-09 | C | 2017-04-01 | 180 | 570 | Awaiting Implementation | On Track | - | -
BSC | P321 | Publication of Trading Unit Delivery Mode | No | No | No | No | Yes | BSC-P321 | C | 2015-04-01 | C | 2015-10-08 | C | 2017-06-29 | 190 | 630 | Awaiting Implementation | On Track | P321 was originally approved under Self-Governance on 8 October 2015 for implementation on 30 June 2016. On 5 January 2016, the Panel wrote to the Authority to request the approved Implementation Date be deferred to 3 November 2016. The Authority approved this request on 26 January 2016. On 9 June 2016, the Panel wrote to the Authority to request the approved Implementation Date be deferred to 29 June 2017. The Authority approved this request on 8 August 2016. P321 will therefore be implemented on 29 June 2017 as part of the June 2017 BSC Systems Release. | -
BSC | P325 | Improving the accountability of BSCCo to stakeholders and better aligning BSCCo governance with best practice | No | No | No | No | Yes | BSC-P325 | C | 2015-07-30 | E | TBD | E | TBD |  |  | Assessment | On Track | - | -
BSC | P326 | Introduction of a non-Working Day adjustment to the Credit Cover Percentage calculation | No | No | No | No | Yes | BSC-P326 | C | 2015-08-25 | C | 2016-04-14 | C | 2017-02-23 | 233 | 315 | Implemented | On Track | - | -
BSC | P332 | Revisions to the Supplier Hub Principle | No | No | No | No | Yes | BSC-P332 | C | 2016-01-28 | E | TBD | E | TBD |  |  | Assessment | On Track | - | -
BSC | P335 | Inclusion of Non-BM STOR costs and volumes in the indicative cashout price | No | No | No | No | Yes | BSC-P335 | C | 2016-02-19 | C | 2016-09-19 | C | 2017-11-02 | 213 | 409 | Awaiting Implementation | On Track | - | -
BSC | P336 | Fuel types on the BMRS | No | No | No | No | Yes | BSC-P336 | C | 2016-02-29 | C | 2016-04-14 | C | 2017-11-02 | 45 | 567 | Awaiting Implementation | On Track | - | -
BSC | P338 | Consequential changes to P272 legal text | No | Yes | No | No | No | BSC-P338 | C | 2016-04-14 | C | 2016-04-14 | C | 2017-04-01 | 0 | 352 | Awaiting Implementation | On Track | - | -
BSC | P339 | Introduction of new Consumption Component Classes for Measurement Classes E-G | No | Yes | No | No | No | BSC-P339 | C | 2016-05-04 | C | 2016-12-08 | C | 2017-04-01 | 218 | 114 | Awaiting Implementation | On Track | - | -
BSC | P341 | MEL and other data earlier than Gate Closure | No | No | No | No | Yes | BSC-P341 | C | 2016-05-20 | E | 2017-04-01 | E | TBD | 316 |  | Assessment | At risk | Awaiting confirmation from Ofgem and a decision on progression from the Workgroup. | -
BSC | BSC Potential Change 1 | Time of Interconnector Data Submission | No | No | Yes | No | No | BSC-BSC Potential Change 1 | E | 2017-06-01 | E | 2018-03-01 | E | 2018-06-01 | 273 | 92 | Upcoming | - | A Modification is expected to be raised in April 2017 under Grid Code, to address the CACM requirement. If the Grid Code Modification removes the impact on the BSC, this Modification will be redundant. | ENC
BSC | P343 | Increase to the number of Supplier IDs that can be held by a Supplier | No | No | No | No | Yes | BSC-P343 | C | 2016-05-26 | C | 2016-11-10 | C | 2017-02-23 | 168 | 105 | Implemented | On Track | - | -
BSC | P346 | Changes to Specific Charges for Elective HH Settlement | No | Yes | No | No | No | BSC-P346 | C | 2016-06-23 | C | 2016-11-10 | C | 2017-04-01 | 140 | 142 | Awaiting Implementation | On Track | Approved. Awaiting implementation in April Standalone release | -
BSC | P347 | Reduction in R1 Read Threshold | Yes | Yes | No | No | No | BSC-P347 | C | 2016-07-01 | E | 2017-02-10 | C | 2017-04-01 | 224 | 50 | Awaiting Implementation | On Track | On 19 January the Panel considered the Sendback Direction from the Authority and approved the revised Final Modification Report for P347. The Panel maintained its recomendation to the Authority that P347 should be rejected. The revised Final Modification Report was submitted to the Authority for decision on 19 January 2017. On 30 January 2017 the Authority determined that P347 should be Approved and implemented on 1 April 2017. | -
BSC | P348 | Provision of gross BM Unit data for TNUoS charging | No | No | No | No | Yes | BSC-P348 | C | 2016-07-01 | E | 2017-04-13 | E | 2019-11-07 | 286 | 938 | Assessment | On Track | This Modification will be progressed in line with P349. | Transmission Network Use of System (TNUoS) Charging changes
BSC | P349 | Facilitating Embedded Generation Triad Avoidance Standstill | No | No | No | No | Yes | BSC-P349 | C | 2016-07-04 | E | 2017-04-13 | E | 2017-06-29 | 283 | 77 | Assessment | On Track | New Embedded Generators will be defined for the purpose of this Modification by Connection Use of System Code (CUSC) Modification Proposal (CMP) 264 ‘Embedded Generation Triad Avoidance Standstill’. The implementation of CMP264 requires both SVA and CVA meter data flows for new embedded generation. It is believed that the Transmission Company already receives the necessary CVA metered data to allow for the benefits of CMP264 to be realised. If this assumption is proved invalid, this Modification will require including CVA as well as SVA registered generators. | -
BSC | P350 | Introduction of a seasonal Zonal Transmission Losses scheme | No | No | No | No | Yes | BSC-P350 | C | 2016-07-05 | E | 2017-03-31 | E | 2018-04-01 | 269 | 366 | Assessment | On Track | The CMA has placed obligations on National Grid to raise a Modification, for implementation by 1 April 2018. If the Modification is not implemented in time, then National Grid will be required to implement the same technical solution on the same date but outside of the BSC. The BSC Panel will make its final reccomendation to Ofgem on 9 Febraury 2017. Ofgem is expected to make its final decision by the end of March 2017. | CMA
BSC | P351 | Align the BSC with changes to the SCR requirements | No | No | No | No | Yes | BSC-P351 | C | 2016-07-29 | C | 2017-01-19 | E | 2017-04-01 | 174 | 72 | Awaiting Implementation | On Track | Initially rejected by Panel. Report consultation now closed and Final report decision on 19/1/17 | -
BSC | P353 | Fast Track Self-Governance Mod following P324 | No | No | No | No | Yes | BSC-P353 | C | 2016-11-10 | C | 2016-12-08 | C | 2017-01-06 | 28 | 29 | Implemented | On track | - | -
BSC | P354 | Use of ABSVD for non-BM Balancing Services at the metered (MPAN) level | No | No | No | No | Yes | BSC-P354 | C | 11-Jan-17 | E | TBD | E | TBD |  |  | Assessment | - | - | -
BSC | BSC Potential Change 2 | Imbalance Price (without derogation) | No | No | Yes | No | No | BSC-BSC Potential Change 2 | E | 2017-10-01 | E | 2018-04-01 | E | 2018-10-01 | 182 | 183 | Upcoming | - | It is assumed that NGET will apply for a derogation for this requirement. If a derogation is approved, this Modification will be included within the scope of Potential Modification 11 "Harmonised Imbalance Settlement". | ENC
BSC | BSC Potential Change 3 | Inclusion of Imbalance Adjustments (without derogation) | No | No | Yes | No | No | BSC-BSC Potential Change 3 | E | 2017-10-01 | E | 2018-04-01 | E | 2018-10-01 | 182 | 183 | Upcoming | - | It is assumed that NGET will apply for a derogation for this requirement. If a derogation be approved, this Modification will be raised on 01/10/19 | ENC
BSC | BSC Potential Change 4 | Align BSC with the Authority's oversight obligation | No | No | Yes | No | No | BSC-BSC Potential Change 4 | E | 2017-10-01 | E | 2018-04-01 | E | 2018-10-01 | 182 | 183 | Upcoming | - | Assignment by BEIS/Ofgem and decisions by Ofgem on how it wishes to approach this requirement | ENC
BSC | BSC Potential Change 3 | Inclusion of Imbalance Adjustments (with derogation) | No | No | Yes | No | No | BSC-BSC Potential Change 3 | E | 2017-10-01 | E | 2018-04-01 | E | 2018-10-01 | 182 | 183 | Upcoming | - | It is assumed that NGET will apply for a derogation for this requirement. If a derogation be approved, this Modification will be raised on 01/10/19 | ENC
BSC | BSC Potential Change 5 | Amendments to Imbalance Price | No | No | Yes | No | No | BSC-BSC Potential Change 5 | E | 2018-10-01 | E | 2019-04-01 | E | 2020-04-01 | 182 | 366 | Upcoming | - | If TSO Proposal for activiation purpose do not align with the BSC, this Modification will be raised to amend the imbalance price calculation | ENC
BSC | BSC Potential Change 6 | Align BSC with the TSO's Terms and Conditions | No | No | Yes | No | No | BSC-BSC Potential Change 6 | E | 2018-10-01 | E | 2019-04-01 | E | 2019-10-01 | 182 | 183 | Upcoming | - | If NGET write Ts & Cs in a way that differs from the Ts & Cs of the BSC, this Modification will be raised to align the BSC with the Ts & Cs of the TSO. | ENC
BSC | BSC Potential Change 7 | Project TERRE 2 | No | No | Yes | No | No | BSC-BSC Potential Change 7 | E | 2018-10-01 | E | 2019-07-01 | E | 2020-03-01 | 273 | 244 | Upcoming | - | This Modification will be raised to implement outstanding activities from Project TERRE | ENC
BSC | BSC Potential Change 8 | Unintended exchanges of energy | No | No | Yes | No | No | BSC-BSC Potential Change 8 | E | 2018-10-01 | E | 2019-04-01 | E | 2019-10-01 | 182 | 183 | Upcoming | - |  | ENC
BSC | BSC Potential Change 9 | NGET proposal on specific products | No | No | Yes | No | No | BSC-BSC Potential Change 9 | E | 2018-10-01 | E | 2019-04-01 | E | 2019-10-01 | 182 | 183 | Upcoming | - | If NGET make a proposal on specific products, an assessment will be required to ensure that the understanding of specific products aligns with the BSC. If understanding of specific products in the TSO proposal, differs from the BSC, this Modification will be raised to align the BSC with the proposal. | ENC
BSC | BSC Potential Change 10 | Market Suspension and Restoration Arrangement | No | No | Yes | No | No | BSC-BSC Potential Change 10 | E | 2018-11-01 | E | 2019-08-01 | E | 2020-05-01 | 273 | 274 | Upcoming | - | If NGET makes proposals for rules concerning the suspension and restoration of market activities; and the rules for balancing energy and imbalance settlement during market suspension, that differ from the BSC, this Modification will be raised to align the BSC with the proposals. | ENC
BSC | BSC Potential Change 13 | Project TERRE 3 | No | No | Yes | No | No | BSC-BSC Potential Change 13 | E | 2019-01-01 | E | 2019-11-01 | E | 2020-02-27 | 304 | 118 | Upcoming | - | This Modification will be raised to implementation outstanding activities from P344 'Project TERRE' | -
BSC | BSC Potential Change 11 | Harmonised Imbalance Settlement (Includes Mod 2 with derogation) | No | No | Yes | No | No | BSC-BSC Potential Change 11 | E | 2019-04-01 | E | 2020-01-01 | E | 2020-10-01 | 275 | 274 | Upcoming | - | This Modification will be raised to align the BSC with NGETs proposals to harmonise the main features of imbalance settlement If Potential Modification 2 'Imbalance Price' receives a derogation, it will be included within the scope of this Modification. | ENC
BSC | BSC Potential Change 12 | Project mFRR | No | No | Yes | No | No | BSC-BSC Potential Change 12 | E | 2019-04-01 | E | 2021-01-01 | E | 2021-10-01 | 641 | 273 | Upcoming | - | This Modification will be raised, as an extension of the principles introduced under P344 ' Project TERRE' | ENC
CUSC | CMP250 | Stabilising BSUoS with at least a twelve month notice period | No | No | No | No | Yes | CUSC -CMP250 | C | 2015-08-19 | E | 2017-07-10 | E | 2017-07-17 | 691 | 7 | Assessment | At Risk | - | CMP250
CUSC | CMP251 | Removing the error margin in the cap on total TNUoS recovered by generation and introducing a new charging element to TNUoS to ensure compliance with European Commission Regulation 838/2010 | No | No | No | No | Yes | CUSC -CMP251 | C | 2015-08-28 | C | 2016-10-14 | E | TBD | 413 |  | Authority Decision | - | - | -
CUSC | CMP259 | Clarification of decrease in TEC as a Modification | No | No | No | No | Yes | CUSC -CMP259 | C | 2016-05-22 | C | 2016-10-14 | E | TBD | 145 |  | Authority Decision | - | - | -
CUSC | CMP261 | Ensuring the TNUoS paid by Generators in GB in Charging Year 2015/16 is in compliance with the €2.5/MWh annual average limit set in EU Regulation 838/2010 Part B (3) | No | No | No | No | Yes | CUSC -CMP261 | C | 2016-03-11 | C | 2016-11-30 | E | TBD | 264 |  | Authority Decision | - | - | -
CUSC | CMP264 | Embedded Generation Triad Avoidance Standstill | No | No | No | No | Yes | CUSC -CMP264 | C | 2016-05-27 | C | 2016-11-28 | E | TBD | 185 |  | Authority Decision | - | - | -
CUSC | CMP265 | Gross charging of TNUoS for HH demand where embedded generation is in Capacity Market | No | No | No | No | Yes | CUSC -CMP265 | C | 2016-05-27 | C | 2016-11-28 | E | TBD | 185 |  | Authority Decision | - | - | -
CUSC | CMP266 | Removal of Demand TNUoS charging as a barrier to future elective Half Hourly settlement | No | No | No | No | Yes | CUSC -CMP266 | C | 2016-07-05 | C | 2016-11-30 | E | 2016-12-22 | 148 | 22 | Implemented | - | - | -
CUSC | CMP268 | Recognition of sharing by Conventional Carbon plant of Not-Shared Year-Round circuits | No | No | No | No | Yes | CUSC -CMP268 | C | 2016-08-02 | E | TBD | E | TBD |  |  | Workgroup | - | - | -
CUSC | CMP269 | Potential consequential changes to the CUSC as a result of CMP264 | No | No | No | No | Yes | CUSC -CMP269 | C | 2016-08-26 | C | 2016-11-28 | E | TBD | 94 |  | Authority Decision | - | - | Consequential of CMP264
CUSC | CMP270 | Potential consequential changes to the CUSC as a result of CMP265 | No | No | No | No | Yes | CUSC -CMP270 | C | 2016-08-19 | C | 2016-11-28 | E | TBD | 101 |  | Authority Decision | - | - | Consequential of CMP265
CUSC | CMP271 | Improving the cost reflectivity of demand transmission charges | No | No | No | No | Yes | CUSC -CMP271 | C | 2016-09-20 | E | 2018-03-16 | E | 2021-04-01 | 542 | 1112 | Assessment | On Track | - | CMP271
CUSC | CMP272 | Aligning Condition C5 of the CUSC to changes introduced by the Code Governance Review Phase 3 | No | No | No | No | Yes | CUSC -CMP272 | C | 2016-09-29 | E | 2017-03-07 | E | 2017-03-14 | 159 | 7 | Assessment | On Track | - | CMP272
CUSC | CMP274 | Winter TNUoS Time of Use Tariff (TToUT) for Demand TNUoS | No | No | No | No | Yes | CUSC -CMP274 | C | 2016-09-29 | E | 2018-03-16 | E | 2021-04-01 | 533 | 1112 | Assessment | On Track | - | CMP274
CUSC | CMP275 | Transmission Generator Benefits in the provision of ancillary and balancing services – levelling the playing field. | No | No | No | No | Yes | CUSC -CMP275 | C | 2017-01-18 | E | TBD | E | TBD |  |  | Assessment | On Track | - | -
CUSC | CUSC Potential Change 1 | European Energy Balancing Guidelines - Replacement Reserves | No | No | Yes | No | Yes | CUSC -CUSC Potential Change 1 | E | 2017-10-01 | E | TBD | E | 2018-10-01 |  | 365 | Upcoming | On Track | This mod is set to be raised in Q4 2017. This mod is set to be implemented in Q4 2018. | EU Regulation/Law
CUSC | CUSC Potential Change 2 | European Energy Balancing Guidelines - Manual Frequency Restoration Reserves (mFRR) | No | No | Yes | No | Yes | CUSC -CUSC Potential Change 2 | E | 2020-07-01 | E | TBD | E | 2021-07-01 |  | 365 | Upcoming | On Track | This mod is set ot be raised Q3 2020. This mod is set to be implemented in Q3 2021 | EU Regulation/Law
Dcode | Dcode Potential Change 3 | To Implement within the Dcode the Fast Fault Current Injection requirements contained within the EU Network Code - Requirements for Generators | No | No | Yes | No | Yes | Dcode-Dcode Potential Change 3 | E | 2017-06-30 | E | TBD | E | TBD |  |  | Upcoming | TBC | Depends on National Grid GC 0048 modification | EU Regulation/Law
Dcode | DCRP1702 | Implementation of the Ofgem CGR3 recommendation on Significant Code Review | No | No | Yes | No | Yes | Dcode-DCRP1702 | E | 2017-12-08 | E | TBD | E | TBD |  |  | Awaiting Implementation | On Track | RTA submitted on 09/03/17 | CGR3
Dcode | Dcode Potential Change 2 | Changes to DOC 5 of the Distribution Code | No | No | Yes | No | Yes | Dcode-Dcode Potential Change 2 | E | 2017-12-08 | E | TBD | E | TBD |  |  | Upcoming | On Track | RTA submitted on 09/03/17 | EU Regulation/Law
Dcode | Dcode Potential Change 1 | Implementation of the requirements of the European Network Code - Demand Connection | No | No | Yes | No | Yes | Dcode-Dcode Potential Change 1 | E | TBD | E | TBD | E | TBD |  |  | Upcoming | On Track | Will be raised at the the time of the GC0048 housekeeping mods | EU Regulation/Law
Dcode | Dcode Potential Change 4 | To Implement within the Dcode the Fault Ride Through requirements contained within the EU Network Code - Requirements for Generators | No | No | Yes | No | Yes | Dcode-Dcode Potential Change 4 | E | TBD | E | TBD | E | TBD |  |  | Upcoming | TBD | Depends on National Grid GC 0048 modification | EU Regulation/Law
Dcode | Dcode Potential Change 5 | To Implement within the Dcode the Frequency Response requirements contained within the EU Network Code - Requirements for Generators | No | No | Yes | No | Yes | Dcode-Dcode Potential Change 5 | E | TBD | E | TBD | E | TBD |  |  | Upcoming | TBD | Depends on National Grid GC 0048 modification | EU Regulation/Law
Dcode | Dcode Potential Change 6 | To Implement within the Dcode the Reactive Power and Voltage Control requirements contained within the EU Network Code - Requirements for Generators | No | No | Yes | No | Yes | Dcode-Dcode Potential Change 6 | E | TBD | E | TBD | E | TBD |  |  | Upcoming | TBD | Depends on National Grid GC 0048 modification | EU Regulation/Law
Dcode | Dcode Potential Change 7 | Implementation of the new Engineering Recommendation G98 | No | No | Yes | No | Yes | Dcode-Dcode Potential Change 7 | E | TBD | E | TBD | E | TBD |  |  | Upcoming | TBD | Target for public consultation Sept 2017 | EU Regulation/Law
Dcode | Dcode Potential Change 8 | Implementation of the new Engineering Recommendation G99 | No | No | Yes | No | Yes | Dcode-Dcode Potential Change 8 | E | TBD | E | TBD | E | TBD |  |  | Upcoming | TBD | TBC | EU Regulation/Law
Dcode | Dcode Potential Change 9 | Implementation of the Transmission System Operators Guidelines | No | No | Yes | No | Yes | Dcode-Dcode Potential Change 9 | E | TBD | E | TBD | E | TBD |  |  | Upcoming | TBD | TBC | EU Regulation/Law
DCUSA | DCP 138 | Implementation of alternative network use factor (NUF) calculation method in EDCM | No | No | No | No | No | DCUSA-DCP 138 | C | 2012-06-18 | C | 2015-10-09 | C | 2017-04-01 | 1208 | 540 | Awaiting Implementation | On Track | - | -
DCUSA | DCP 160 | Non-Half Hourly (NHH) Notional Capacity | No | Yes | No | No | No | DCUSA-DCP 160 | C | 2013-01-08 | C | 2016-10-18 | n/a | n/a | 1379 |  | Authority Rejected the change | On Track | Authority Rejected the change | -
DCUSA | DCP 161 | Excess Capacity Charges | No | No | No | No | No | DCUSA-DCP 161 | C | 2013-02-06 | C | 2015-10-21 | C | 2018-04-01 | 987 | 893 | Awaiting Implementation | On Track | - | -
DCUSA | DCP 169 | Seasonal Time of Day (SToD) HH Metered Tariffs in the CDCM | No | Yes | No | No | No | DCUSA-DCP 169 | C | 2013-03-13 | E | TBD | E | TBD |  |  | Assessment | At Risk | CP on Hold - Working Group is awaiting Ofgem decision on DCP 228 before deciding on how to proceed with DCP 169. DCP 225 is due to be implemented 1 Apr 2018 | -
DCUSA | DCP 181 | Previous Connection Terms Enduring | No | No | No | No | No | DCUSA-DCP 181 | C | 2013-06-17 | C | 2016-06-15 | C | 2016-10-01 | 1094 | 108 | Implemented | On Track | - | -
DCUSA | DCP 204 | Smart Metering Related Amendments to Schedule 8 | Yes | No | No | No | No | DCUSA-DCP 204 | C | 2014-02-27 | C | 2016-02-23 | C | 2016-09-01 | 726 | 191 | Implemented | On Track | - | -
DCUSA | DCP 209 | Resolving Unregistered Customers | No | No | No | No | No | DCUSA-DCP 209 | C | 2014-05-08 | C | 2016-08-30 | C | 2016-10-01 | 845 | 32 | Implemented | On Track | - | -
DCUSA | DCP 222 | Non Billing Of Excess Reactive Power Charges | No | No | No | No | No | DCUSA-DCP 222 | C | 2014-12-02 | C | 2016-08-15 | C | 2018-04-01 | 622 | 594 | Awaiting Implementation | On Track | - | -
DCUSA | DCP 226 | Housekeeping 66/72/73/77/80 | No | No | No | No | Yes | DCUSA-DCP 226 | C | 2015-01-05 | E | TBD | E | TBD |  |  | Assessment | At Risk | CP on Hold - housekeeping change to review refrences throuout the DCUSA Document. Work on this is to be carried out after the 1 October 2016 DCUSA Release. | -
DCUSA | DCP 227 | Removing the inconsistency in the application of Peaking Probabilities in the CDCM | No | No | No | No | No | DCUSA-DCP 227 | C | 2015-01-13 | C | 2015-10-21 | C | 2017-04-01 | 281 | 528 | Awaiting Implementation | On Track | - | -
DCUSA | DCP 228 | Revenue Matching in the CDCM | No | No | No | No | No | DCUSA-DCP 228 | C | 2015-01-13 | C | 2016-09-08 | C | 2018-04-01 | 604 | 570 | Awaiting Implementation | On Track | - | -
DCUSA | DCP 234 | Merging the PCDM and extended PCDM | No | No | No | No | No | DCUSA-DCP 234 | C | 2015-02-27 | C | 2016-08-03 | C | 2018-04-01 | 523 | 606 | Awaiting Implementation | On Track | - | -
DCUSA | DCP 243 | Treatment of Customer Contributions in the CDCM | No | No | No | No | No | DCUSA-DCP 243 | C | 2015-06-05 | E | TBD | E | TBD |  |  | Assessment | On Track | Under Development - Working Group developing the CP solution | -
DCUSA | DCP 244 | MOP Leaving Site for Cat A Situations | No | No | No | No | No | DCUSA-DCP 244 | C | 2015-06-19 | E | TBD | E | TBD |  |  | Assessment | At Risk | CP on Hold - Working Group is waiting for Operational Delivery Group (ODG) to develop MOP guidance on leaving site where there is a category A situation. | -
DCUSA | DCP 251 | Clarification And Extension Of The Application Of LDNO Tariffs Under The CDCM | No | No | No | No | No | DCUSA-DCP 251 | C | 2015-10-15 | E | TBD | E | TBD |  |  | Assessment | On Track | Under Development - Working Group developing the CP solution DCP251/2 WG meeting indicated that the change declaration may be issued in June 2017, with an Ofgem decision anticipated in August 2017 | -
DCUSA | DCP 252 | Clarification And Extension Of The Application Of Portfolio Tariffs Under The EDCM | No | No | No | No | No | DCUSA-DCP 252 | C | 2015-10-15 | E | TBD | E | TBD |  |  | Assessment | On Track | Under Development - Working Group developing the CP solution DCP251/2 WG meeting indicated that the change declaration may be issued in June 2017, with an Ofgem decision anticipated in August 2017 | -
DCUSA | DCP 253 | Retightening and remaking of whole current metering system terminal connections. | No | No | No | No | No | DCUSA-DCP 253 | C | 2015-11-03 | C | 2016-09-21 | C | 2016-09-01 | 323 | -20 | Implemented | On Track | - | -
DCUSA | DCP 255 | Changes to Electricity (Connection Charges) Regulations 2002 | No | No | No | No | No | DCUSA-DCP 255 | C | 2015-11-06 | E | TBD | E | TBD |  |  | Assessment | On Track | The Working Group are awaiting the receipt of the final ECCR 2016 legal text from BEIS (formaly DECC) before progressing this change. | -
DCUSA | DCP 256 | Change to DCUSA to mitigate risks of non-payment of non-payment of DCUSA invoices | No | No | No | No | No | DCUSA-DCP 256 | C | 2015-11-10 | C | 2016-09-21 | C | 2016-10-01 | 316 | 10 | Implemented | On Track | - | -
DCUSA | DCP 262 | Schedule 19 Credit/Re-invoice for HH Specific Data | No | Yes | No | No | No | DCUSA-DCP 262 | C | 2016-01-13 | C | 2016-07-29 | C | 2016-09-01 | 198 | 34 | Implemented | On Track | - | -
DCUSA | DCP 263 | NTC DEH Gap | No | No | No | No | No | DCUSA-DCP 263 | C | 2016-01-22 | E | 17/01/201 | E | 2017-02-23 |  |  | Change Report issued for Voting | On Track | Change Report issued for Voting | -
DCUSA | DCP 264 | Introduction of Energy Theft Tip Off Line Service | No | No | No | No | No | DCUSA-DCP 264 | C | 2016-02-15 | C | 2016-08-15 | C | 2016-08-22 | 182 | 7 | Implemented | On Track | - | -
DCUSA | DCP 266 | The calculation and application of IDNO discounts | No | No | No | No | No | DCUSA-DCP 266 | C | 2016-03-09 | E | n/a | E | n/a |  |  | Assessment | On Track | Under Development - Working Group developing the CP solution | -
DCUSA | DCP 267 | Introduction of a new definition for 'Confirmed Theft' | No | No | No | No | No | DCUSA-DCP 267 | C | 2016-03-09 | C | 2016-09-14 | C | 2016-11-03 | 189 | 50 | Implemented | On Track | - | -
DCUSA | DCP 268 | DUoS Charging Using HH settlement data | No | Yes | No | No | No | DCUSA-DCP 268 | C | 2016-03-14 | E | TBD | E | 2018-04-01 |  | 748 | Assessment | On Track | Under Development - Working Group developing the CP solution | -
DCUSA | DCP 269 | Revenue Protection Service Withdrawal Period | No | No | No | No | No | DCUSA-DCP 269 | C | 2016-04-25 | C | 2016-07-12 | C | 2016-09-01 | 78 | 51 | Implemented | On Track | - | -
DCUSA | DCP 270 | Removal of HV Medium tariff from CDCM | No | No | No | No | No | DCUSA-DCP 270 | C | 2016-04-28 | C | 2017-11-16 | n/a | n/a | 567 |  | Rejected | On Track | Authority Rejected the change | -
DCUSA | DCP 271 | TRAS - Process and Costs of Providing Additional Hunter Facilities | No | No | No | No | No | DCUSA-DCP 271 | C | 2016-05-11 | C | 2016-09-15 | C | 2016-11-03 | 127 | 49 | Implemented | On Track | - | -
DCUSA | DCP 272 | TRAS – Amendment of Schedule 25 Appendix 2 | No | No | No | No | No | DCUSA-DCP 272 | C | 2016-05-11 | C | 2016-09-15 | C | 2016-11-03 | 127 | 49 | Implemented | On Track | - | -
DCUSA | DCP 273 | Align CDCM table 1001 (target revenue) to latest Schedule 15 template | No | No | No | No | No | DCUSA-DCP 273 | C | 2016-05-18 | C | 2016-10-14 | C | 2018-04-01 | 149 | 534 | Awaiting Implementation | On Track | - | -
DCUSA | DCP 274 | The application of export capacity charges in the EDCM | No | No | No | No | No | DCUSA-DCP 274 | C | 2016-06-10 | E | TBD | E | 2018-04-01 |  | 660 | Assessment | On Track | Under Development - Working Group developing the CP solution | -
DCUSA | DCP 275 | Code Governance Review 3 & SLC 22 | No | No | No | No | No | DCUSA-DCP 275 | C | 2016-06-10 | C | 2016-11-15 | C | 2017-02-23 | 158 | 100 | Awaiting Implementation | On Track | - | -
DCUSA | DCP 276 | Amendments to CDCM LV Substation Tariff ‘Note 5’ | No | No | No | No | No | DCUSA-DCP 276 | C | 2016-07-04 | C | 2016-09-14 | C | 2016-11-03 | 72 | 50 | Implemented | On Track | - | -
DCUSA | DCP 277 | Schedule 25 – Amendment to Appendix 2 - Conditionality | No | No | No | No | No | DCUSA-DCP 277 | C | 2016-07-13 | C | 2016-11-17 | C | 2017-02-23 | 127 | 98 | Awaiting Implementation | On Track | - | -
DCUSA | DCP 278 | Allocation of Users to the ETTOS Secure Email Service | No | No | No | No | No | DCUSA-DCP 278 | C | 2016-07-13 | C | 2016-12-15 | C | 2017-02-23 | 155 | 70 | Awaiting Implementation | On Track | - | -
DCUSA | DCP 279 | Linking Credit Cover to the Annual Iteration Process | No | No | No | No | No | DCUSA-DCP 279 | C | 2016-07-29 | C | 2016-12-23 | C | 2017-02-23 | 147 | 62 | Awaiting Implementation | On Track | - | -
DCUSA | DCP 280 | Clarification of TRAS Accession Process | No | No | No | No | No | DCUSA-DCP 280 | C | 2016-08-18 | C | 2016-12-15 | C | 2017-02-23 | 119 | 70 | Awaiting Implementation | On Track | The voting period was extended to align with the equivilent SPAA CP (CP16/346) | -
DCUSA | DCP 281 | Changes to Schedule 19 – Portfolio Billing | No | Yes | No | No | No | DCUSA-DCP 281 | C | 2016-09-14 | E | TBD | E | 2019-04-01 |  | 929 | Assessment | On Track | Under Development - Working Group developing the CP solution | -
DCUSA | DCP 282 | Embedded Distribution Network Operator (EDNO) UMSO | No | No | No | No | No | DCUSA-DCP 282 | C | 2016-09-14 | E | 2017-03-14 | E | TBD | 181 |  | Assessment | On Track | Under Development - Working Group developing the CP solution | -
DCUSA | DCP 283 | The calculation of generation credits in the CDCM | No | No | No | No | No | DCUSA-DCP 283 | C | 2016-10-12 | E | TBD | E | 2019-04-01 |  | 901 | Assessment | On Track | Under Development - Working Group developing the CP solution | -
DCUSA | DCP 284 | The application of scaling to generation credits in the CDCM | No | No | No | No | No | DCUSA-DCP 284 | C | 2016-10-12 | E | TBD | E | 2019-04-01 |  | 901 | Assessment | On Track | Under Development - Working Group developing the CP solution | -
DCUSA | DCP 285 | Schedule 23, Appendix 1 SLC References | No | No | No | No | No | DCUSA-DCP 285 | C | 2016-10-12 | E | 2017-01-24 | E | 2017-02-23 | 104 | 30 | Assessment | On Track | Under Development - legal text being updated | -
DCUSA | DCP 286 | Formalising the Theft Steering Group | No | No | No | No | No | DCUSA-DCP 286 | C | 2016-11-09 | E | TBD | E | TBD |  |  | Assessment | On Track | Under Development - Definition Stage | -
DCUSA | DCP 287 | Generation Credits in the EDCM | No | No | No | No | No | DCUSA-DCP 287 | C | 2016-11-11 | E | TBD | E | 2019-04-01 |  | 871 | Assessment | On Track | - | -
DCUSA | DCP 288 | Introduction of the Electricity Theft Detection Incentive Scheme | No | No | No | No | No | DCUSA-DCP 288 | C | 2016-12-12 | E | TBD | E | TBD |  |  | Assessment | On Track | - | -
DCUSA | DCP 289 | Creation of Distribution Charging Methodology Development Group | No | No | No | No | No | DCUSA-DCP 289 | C | 2016-12-16 | E | TBD | E | TBD |  |  | Assessment | On Track | - | -
DCUSA | DCP 290 | Housekeeping Change to Update PCDM Model References | No | No | No | No | No | DCUSA-DCP 290 | C | 2017-01-17 | E | TBD | C | 2018-04-01 |  | 439 | Awaiting Implementation | On Track | - | -
DCUSA | DCP 291 | Application of Generation Credits to EDCM Customers | No | No | No | No | No | DCUSA-DCP 291 | E | 2017-02-17 | E | TBD | E | 2019-04-01 |  | 773 | Definition | On Track | - | -
DCUSA | DCP 292 | Align DCUSA Schedule 15 table 3 to the CDCM tariff structure following the approval DCP 222 ‘Non billing of Excess Reactive Power Charges’ | No | No | No | No | No | DCUSA-DCP 292 | E | 2017-02-10 | E | TBD | E | 2017-06-29 |  | 139 | Change Report | On Track | - | -
DCUSA | DCP 293 | Charging Methodology Cut-off Date | No | No | No | No | No | DCUSA-DCP 293 | E | 2001-02-14 | E | TBD | E | 2017-10-01 |  | 6073 | Definition | On Track | - | -
GC | GC0048 | Requirements for Generators - Implementation of European Network Code | No | No | Yes | No | Yes | GC-GC0048 | C | 2013-07-01 | C | TBD | C | 2018-05-17 |  | 1781 | Raised | On Track | This is a workgroup, and it is expected that this workgroup will manage the raising of all additional modifications required to deliver The deadline for EIF is fixed. National Implementation Compliance date is 17/05/2018 | European Regulation/Law
GC | GC0090 | HVDC - Implementation of European Network Code | No | No | Yes | No | Yes | GC-GC0090 | C | 2015-07-01 | C | TBD | C | 2018-09-29 |  | 1186 | Raised | On Track | This is a workgroup, and it is expected that this workgroup will manage the raising of all additional modifications required to deliver Deadline for EIF is fixed. National Implementation Compliance date is 29/09/2018 | European Regulation/Law
GC | GC0091 | Application of the the Demand Connection Code - Implementation of European Network Code | No | No | Yes | No | Yes | GC-GC0091 | C | 2016-03-01 | C | TBD | C | 2018-09-07 |  | 920 | Raised | On Track | This is a workgroup, and it is expected that this workgroup will manage the raising of all additional modifications required to deliver. Deadline for EIF is fixed. National Implementation Compliance date is 07/09/2018 | European Regulation/Law
GC | GC0095 | GB implementation workgroup for Transmission System Operation Guideline (TSOG) European Network Code | No | No | Yes | No | Yes | GC-GC0095 | C | 2016-05-27 | E | TBD | C | 2018-10-01 |  | 857 | Assessment | On Track | All areas of TSOG are curently held within one workgroup, this may change as modification are raised to deliver respective areas are completed There is a range of Entry into Force dates ranging to October 2018 | EU Regulation/Law
GC | GC0097 | European Energy Balancing Guidelines - Replacement Reserves - TERRE | No | No | Yes | No | Yes | GC-GC0097 | E | 2016-11-16 | C | TBD | E | 2019-07-01 |  | 957 | Assessment | On Track | This modification maybe required to address changes associated with project TERRE Deadline for EIF is fixed. This mod is set to be implemented Q3 2019. | EU Regulation/Law
GC | Grid Code Potential Change 1 | Implementation of CACM European Network Code | No | No | Yes | No | Yes | GC-Grid Code Potential Change 1 | E | 2017-01-01 | C | TBD | E | 2018-01-01 |  | 365 | Upcoming | On Track | This modification may be required to address the requirements of the Common Grid Model This mod is currently set to be raised in Q1 2017 Deadline for EIF is fixed. Compliance for CGM is Jan 2018 - and TBC based on methodologies | European Regulation/Law
GC | Grid Code Potential Change 2 | European Energy Balancing Guidelines - General Compliance | No | No | Yes | No | Yes | GC-Grid Code Potential Change 2 | E | 2017-01-01 | E | TBD | E | 2018-07-01 |  | 546 | Upcoming | On Track | This modification maybe required to address general compliance requirements of the EB GL The mod if currently set to be raised in Q1 2020. Deadline for EIF is fixed. The mod if set to be implemented in Q3 2021. | EU Regulation/Law
GC | Grid Code Potential Change 5 | European RfG Banding and RfG/HVDC requirements | No | No | Yes | No | Yes | GC-Grid Code Potential Change 5 | E | 2017-04-19 | E | TBD | E | 2018-04-01 |  | 347 | Upcoming | On Track | This mod is set to be raised in Q2 2017. This mod is set to be implementedin Q2 2018. | EU Regulation/Law
GC | Grid Code Potential Change 4 | European Emergency & Restoration Code - System Defence & Restoration Plan | No | No | Yes | No | Yes | GC-Grid Code Potential Change 4 | E | 2017-07-01 | E | TBD | E | 2018-07-01 |  | 365 | Upcoming | On Track | This mod is set to be raised in Q2 2017. This mod is set to be implemente din Q3 2018. | EU Regulation/Law
GC | GC0077 | Suppression of Sub-Synchronous Resonance from Series Capacitive Compensation | No | No | No | No | Yes | GC-GC0077 | C | 2013-08-14 | E | 2017-03-01 | E | 2017-04-01 | 1295 | 31 | Assessment | On Track | - | -
GC | GC0079 | GC0035 / GC0079 Frequency Changes during Large Disturbances and their effect on the total system - Phase 1 & 2 | No | No | No | No | Yes | GC-GC0079 | C | 2008-05-21 | E | TBD | E | TBD |  |  | Assessment | At Risk | Ongoing for 8 years with with deliberations over funding arrangements to be decided. | -
GC | GC0086 | Open Governance | No | No | No | No | Yes | GC-GC0086 | C | 2014-07-02 | E | 2017-02-01 | E | 2017-03-01 | 945 | 28 | Assessment | On Track | - | -
GC | GC0087 | Requirements for Generators Frequency Provisions | No | No | No | No | Yes | GC-GC0087 | C | 2014-11-04 | E | 2017-07-01 | E | 2017-08-01 | 970 | 31 | Assessment | On Track | - | GC0022
GC | GC0096 | Energy Storage | No | No | No | No | Yes | GC-GC0096 | C | 2016-05-18 | E | 2017-05-01 | E | 2017-06-01 | 348 | 31 | Assessment | On Track | - | -
GC | Grid Code Potential Change 3 | European Energy Balancing Guidelines - Manual Frequency Restoration Reserves (mFRR) | No | No | Yes | No | Yes | GC-Grid Code Potential Change 3 | E | 2020-01-01 | E | TBD | E | 2021-07-01 |  | 547 | Upcoming | On Track | This modification maybe required to address mFRR requirements of the EB GL This mod is set to be raised in Q1 2020. Deadline for EIF is fixed. This mod is set to be implemented in Q3 2021. | EU Regulation/Law
GC | Grid Code Potential Change 6 | RfG and HVDC Voltage and Frequency Response requirements | No | No | No | No | Yes | GC-Grid Code Potential Change 6 | E | 2017-04-19 | E | TBD | E | 2018-01-01 |  | 257 | Upcoming | On Track | This mod is set to be raised in Q2 2017 Deadline for EIF is fixed. This mod is set to be implemented in Q1 2018. | EU Regulation/Law
GC | Grid Code Potential Change 7 | RfG and HVDC Compliance and System Management | No | No | No | No | Yes | GC-Grid Code Potential Change 7 | E | 2017-06-21 | E | TBD | E | 2018-01-01 |  | 194 | Upcoming | On Track | This mod is set to be raised in Q2 2017 Deadline for EIF is fixed. This mod is set to be implemented in Q1 2018. | EU Regulation/Law
GC | Grid Code Potential Change 8 | DCC Technical & Demand Side Response | No | No | No | No | Yes | GC-Grid Code Potential Change 8 | E | 2017-06-21 | E | TBD | E | 2018-09-01 |  | 437 | Upcoming | On Track | This mod is set to be raised in Q2 2017 Deadline for EIF is fixed. This mod is set to be implemented in Q3 2018. | EU Regulation/Law
GC | Grid Code Potential Change 9 | Interconnector Data Provision | No | No | No | No | Yes | GC-Grid Code Potential Change 9 | E | 2017-06-21 | E | TBD | E | 2019-01-01 |  | 559 | Upcoming | On Track | This mod is set to be raised in Q2 2017 Deadline for EIF is provisionally Q1 2019 | EU Regulation/Law
GC | Grid Code Potential Change 10 | Frequency Restoration Reserves | No | No | No | No | Yes | GC-Grid Code Potential Change 10 | E | 2020-01-01 | E | TBD | E | 2021-10-01 |  | 639 | Upcoming | On Track | This mod is set to be raised in Q1 2020 Deadline for EIF is provisionally Q3 2021 | EU Regulation/Law
GC | Grid Code Potential Change 11 | European TSOG Implementation -Regional Outage Coordination | No | No | No | No | Yes | GC-Grid Code Potential Change 11 | E | 2018-01-01 | E | TBD | E | 2018-10-01 |  | 273 | Upcoming | On Track | This mod is set to be raised in Q1 2018 Deadline for EIF is provisionally Q4 2018 | EU Regulation/Law
GC | Grid Code Potential Change 12 | European TSOG - Requirements | No | No | No | No | Yes | GC-Grid Code Potential Change 12 | E | 2018-01-01 | E | TBD | E | 2018-10-01 |  | 273 | Upcoming | On Track | This mod is set to be raised in Q1 2018 Deadline for EIF is provisionally Q4 2018 | EU Regulation/Law
GC | Grid Code Potential Change 13 | Market Suspension | No | No | No | No | Yes | GC-Grid Code Potential Change 13 | E | 2017-07-01 | E | TBD | E | 2018-10-01 |  | 457 | Upcoming | On Track | This mod is set to be raised in Q3 2017 Deadline for EIF is provisionally Q3 2018 | EU Regulation/Law
SEC | SECMP0002 | Add New Command to Reset Debt Registers | Yes | No | No | No | Yes | SEC-SECMP0002 | C | 2016-02-19 | E | TBD | E | 2018-06-01 |  | 833 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0004 | Inclusion of Device Serial Number data item in the Smart Metering Inventory | Yes | No | No | No | Yes | SEC-SECMP0004 | C | 2016-02-19 | E | TBD | E | 2018-06-01 |  | 833 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0005 | Include Tariff and Register Labels in SMETS2 Devices | Yes | No | No | No | Yes | SEC-SECMP0005 | C | 2016-03-01 | E | TBD | E | 2018-06-01 |  | 822 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0006 | Specifying the number of digits for device display | Yes | No | No | No | Yes | SEC-SECMP0006 | C | 2016-03-01 | E | TBD | E | 2018-06-01 |  | 822 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0007 | Firmware updates to mandated HAN devices | Yes | No | No | No | Yes | SEC-SECMP0007 | C | 2016-03-01 | E | TBD | E | 2018-06-01 |  | 822 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0008 | Provision of a Service Request error response for quarantined Service Requests | Yes | No | No | No | Yes | SEC-SECMP0008 | C | 2016-03-01 | E | TBD | E | 2018-06-01 |  | 822 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0009 | Centralised Firmware Library | Yes | No | No | No | Yes | SEC-SECMP0009 | C | 2016-03-01 | E | TBD | E | 2018-06-01 |  | 822 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0010 | Introduction of triage arrangements for Communication Hubs | Yes | No | No | No | Yes | SEC-SECMP0010 | C | 2016-03-02 | E | TBD | E | 2018-06-01 |  | 821 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0011 | Inclusion of Meter Asset Provider Participant Code (MAP ID) Participant Codes in the Smart Metering Inventory | Yes | No | No | No | Yes | SEC-SECMP0011 | C | 2016-03-22 | E | TBD | E | 2018-06-01 |  | 801 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0012 | Channel selection to support Shared HAN solutions | Yes | No | No | No | Yes | SEC-SECMP0012 | C | 2016-05-05 | E | TBD | E | 2018-06-01 |  | 757 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0013 | Smart meter device diagnostics and triage | Yes | No | No | No | Yes | SEC-SECMP0013 | C | 2016-05-04 | E | TBD | E | 2018-06-01 |  | 758 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0015 | GPF timestamp for reading instantaneous Gas values | Yes | No | No | No | Yes | SEC-SECMP0015 | C | 2016-05-31 | E | TBD | E | 2018-06-01 |  | 731 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0016 | Consideration of "Maximum Credit" value in credit cover calculation | Yes | No | No | No | Yes | SEC-SECMP0016 | C | 2016-06-03 | E | TBD | E | 2017-06-01 |  | 363 | Awaiting Authority Determination | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0018 | Standard Electricity Distributor Configuration Settings | Yes | No | No | No | Yes | SEC-SECMP0018 | C | 2016-06-23 | E | TBD | E | 2018-06-01 |  | 708 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0019 | ALCS Description Labels | Yes | No | No | No | Yes | SEC-SECMP0019 | C | 2016-07-14 | E | TBD | E | 2017-11-02 |  | 476 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0021 | Increase Other SEC Party representation for TABASC and SSC | Yes | No | No | No | Yes | SEC-SECMP0021 | C | 2016-10-04 | E | TBD | E | 2017-06-29 |  | 268 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0023 | Correct Units of Measure for Uncontrolled Gas Flow Rate | Yes | No | No | No | Yes | SEC-SECMP0023 | C | 2016-10-26 | E | TBD | E | 2018-06-01 |  | 583 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0024 | Enduring Approach to Communication Hub Firmware Management | Yes | No | No | No | Yes | SEC-SECMP0024 | C | 2016-10-27 | E | TBD | E | 2018-06-01 |  | 582 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0025 | Electricity Network Party Access to Load Switching Information | Yes | No | No | No | Yes | SEC-SECMP0025 | C | 2016-11-18 | E | TBD | E | 2018-06-01 |  | 560 | Modification Proposal Submitted | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0026 | Changes to the Security Sub-Committee Nomination Process | Yes | No | No | No | Yes | SEC-SECMP0026 | C | 2016-12-12 | E | TBD | E | 2017-03-16 |  | 94 | Modification Proposal Submitted | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0027 | Amending Service Request Forecasting | Yes | No | No | No | Yes | SEC-SECMP0027 | C | 2016-12-16 | E | TBD | E | TBD |  |  | Modification Proposal Submitted | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0028 | Prioritising Service Requests | Yes | No | No | No | Yes | SEC-SECMP0028 | C | 2016-12-07 | E | TBD | E | TBD |  |  | Modification Proposal Submitted | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0029 | Business Continuity and Disaster Recovery Testing Amendments | Yes | No | No | No | Yes | SEC-SECMP0029 | C | 2016-12-19 | E | TBD | E | TBD |  |  | Modification Proposal Submitted | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0030 | Demand Management of DCC Systems | Yes | No | No | No | Yes | SEC-SECMP0030 | C | 2017-01-04 | E | TBD | E | TBD |  |  | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0031 | Adding UTRN Functionality to SMETS | Yes | No | No | No | Yes | SEC-SECMP0031 | C | 2017-02-20 | E | TBD | E | TBD |  |  | Initial Modification Report | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0032 | Prioritising Prepayment Customers in No WAN Situations | Yes | No | No | No | Yes | SEC-SECMP0032 | C | 2017-02-20 | E | TBD | E | TBD |  |  | Initial Modification Report | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SEC | SECMP0033 | Update to CH Handover Support Materials | Yes | No | No | No | Yes | SEC-SECMP0033 | C | 2017-02-22 | E | TBD | E | TBD |  |  | Initial Modification Report | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | -
SPAA | CP 14/268 | Introduction of The Gas Theft Incentive Scheme | No | No | No | No | No | SPAA-CP 14/268 | C | 2014-03-01 | C | n/a | E | TBD |  |  | Awaiting implementation | On Track | Confirmation of go-live date required Mod will be implemented 5 WDs after Authority Decision, with the Scheme Year to start on the first day of the calendar month two months after Authority Decision. | Gas Theft
SPAA | CP 15/305 | Additional MDD Rejection Codes for UKLP | No | No | No | No | No | SPAA-CP 15/305 | C | 2015-05-01 | C | 2016-07-21 | E | TBD | 447 |  | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus
SPAA | CP 15/306 | Inclusion of new definition – Project Nexus Implementation Date | No | No | No | No | No | SPAA-CP 15/306 | C | 2016-06-01 | C | 2016-07-21 | E | TBD | 50 |  | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus
SPAA | CP 15/307 | Amendment to the Implementation date of CP14/284 | No | No | No | No | No | SPAA-CP 15/307 | C | 2015-06-01 | C | 2016-07-21 | E | TBD | 416 |  | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus
SPAA | CP 15/308 | Removal of Schedule 7 (Cooperative Objections) as a result of Nexus | No | No | No | No | No | SPAA-CP 15/308 | C | 2016-03-01 | C | 2016-04-01 | E | TBD | 31 |  | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus
SPAA | CP 15/317 | Amendment to Schedule 23 to reflect Changes at Project Nexus Implementation | No | No | No | No | No | SPAA-CP 15/317 | C | 2015-11-01 | C | 2015-12-01 | E | TBD | 30 |  | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus
SPAA | CP 16/327 | Revision and Implementation of the Gas Theft Detection Incentive Scheme | No | No | No | No | No | SPAA-CP 16/327 | C | 2016-06-01 | C | 2016-07-21 | C | 2017-06-05 | 50 | 319 | Awaiting implementation | On Track | - | Gas Theft
SPAA | CP 16/329 | Introduction of Schedule 38 and a new defined term in Schedule 29 | No | No | No | No | No | SPAA-CP 16/329 | C | 2016-05-01 | C | 2017-02-01 | C | 2017-02-24 | 276 | 23 | Awaiting implementation | On Track | - | n/a
SPAA | CP 16/334 | Introduction of Smart Prepayment Change of Supplier Exceptions Process | Yes | No | No | No | No | SPAA-CP 16/334 | C | 2016-05-01 | C | 2016-10-20 | E | TBD | 172 |  | Awaiting implementation | On Track | Confirmation of authority approval 1 WD after Authority Consent received | n/a
SPAA | CP 16/336 | Amendments to the SPAA change process v1.1 | No | No | No | No | No | SPAA-CP 16/336 | C | 2016-06-01 | C | 2016-10-20 | C | 2017-02-24 | 141 | 127 | Awaiting implementation | On Track | - | n/a
SPAA | CP 16/338 | Process and Costs of Providing Additional Hunter Facilities | No | No | No | No | No | SPAA-CP 16/338 | C | 2016-05-01 | C | 2016-09-15 | C | 2017-02-24 | 137 | 162 | Awaiting implementation | On Track | - | TRAS
SPAA | CP 16/339 | TRAS Amendment of Schedule 34 Appendix 2 | No | No | No | No | Yes | SPAA-CP 16/339 | C | 2016-05-01 | C | 2016-09-15 | E | TBD | 137 |  | Issued | On Track | Confirmation of authority approval 5WDs after decision to align with DCUSA | TRAS
SPAA | CP 16/343 | Housekeeping amendment to redundant Schedules | No | No | No | No | Yes | SPAA-CP 16/343 | C | 2016-06-01 | C | 2016-07-21 | C | TBD | 50 |  | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus
SPAA | CP 16/344 | Requirement on Gas Transporters to Provide Data to the ETTOS Service Provider | No | No | No | No | No | SPAA-CP 16/344 | C | 2016-06-01 | C | 2016-07-21 | E | TBD | 50 |  | Awaiting implementation | On Track | Confirmation of authority approval 5 Working Days following Authority approval (aligned with the DCUSA change) | TRAS
SPAA | CP 16/346 | Inclusion of User Allocation Rules for ETTOS Secure Email System (Draft) | No | No | No | No | No | SPAA-CP 16/346 | C | 2016-07-01 | C | 2016-12-15 | E | 2017-02-24 | 167 | 71 | Issued in Change Pack | On Track | - | TRAS
SPAA | CP 16/346 | Inclusion of User Allocation Rules for ETTOS Secure Email System | No | No | No | No | No | SPAA-CP 16/346 | C | 2016-07-01 | C | 2016-12-15 | E | 2017-02-24 | 167 | 71 | Issued in Change Pack | On Track | - | TRAS
SPAA | CP 16/347 | Amendments to Pre-Payment tariff pages (Draft) | No | No | No | No | No | SPAA-CP 16/347 | C | 2016-07-01 | C | n/a | E | TBD |  |  | Awaiting implementation | On Track | Confirmation of authority approval 5WD after Authority Consent received | -
SPAA | CP 16/349 | Introduction of OAMI into SPAA EC Vires | No | No | No | No | No | SPAA-CP 16/349 | C | n/a | C | n/a | E | TBD |  |  | Awaiting implementation | On Track | Confirmation of authority approval 5WD after Authority Consent received | -
SPAA | CP 16/349 | Introduction of OAMI into SPAA EC Vires | No | No | No | No | No | SPAA-CP 16/349 | C | n/a | C | n/a | E | TBD |  |  | Awaiting implementation | On Track | Confirmation of authority approval 5WD after Authority Consent received | -
SPAA | CP 16/350 | Clarification of TRAS Accession Process | No | No | No | No | No | SPAA-CP 16/350 | C | 2016-11-01 | C | 2016-12-15 | C | 2017-02-24 | 44 | 71 | Awaiting implementation | On Track | 0 | TRAS
SPAA | CP 16/352 | Changes to SLC 30 of SPAA | No | No | No | No | No | SPAA-CP 16/352 | C | 2016-08-01 | C | 2016-10-20 | C | 2017-02-24 | 80 | 127 | Awaiting implementation | On Track | - | -
SPAA | CP 16/353 | Housekeeping Amendments to the SPAA Main Body | No | No | No | No | Yes | SPAA-CP 16/353 | C | 2016-08-01 | C | 2016-10-20 | C | 2017-02-24 | 80 | 127 | Awaiting implementation | On Track | - | -
SPAA | CP 16/354 | Mandate that all Suppliers shall use the DTN for the exchange of RET Flows | No | No | No | No | No | SPAA-CP 16/354 | C | 2016-09-01 | C | 2016-10-20 | C | 2017-06-05 | 49 | 228 | Awaiting implementation | On Track | - | -
SPAA | CP 16/355 | Mandate that all Suppliers shall use the DTN for the exchange of SAR Flows | No | No | No | No | No | SPAA-CP 16/355 | C | 2016-09-01 | C | 2016-10-20 | C | 2017-06-05 | 49 | 228 | Awaiting implementation | On Track | - | -
SPAA | CP 16/360 | Schedule 33, Appendix 1 SLC References | No | No | No | No | Yes | SPAA-CP 16/360 | C | 2016-11-01 | C | 2016-12-15 | C | 2017-02-24 | 44 | 71 | Deferred | On Track | - | -
SPAA | CP 16/363 | Adding Meter Serial Number (MSN) to the Supplier Agreed Read (SAR) flow. | No | No | No | No | No | SPAA-CP 16/363 | C | 2016-11-01 | C | 2016-12-15 | C | 2017-06-05 | 44 | 172 | Awaiting implementation | On Track | - | -
SPAA | CP 16/364 | Amendment to Actual Reading Definition | No | No | No | No | Yes | SPAA-CP 16/364 | C | 2016-11-01 | C | 2016-12-15 | C | 2017-02-24 | 44 | 71 | Awaiting implementation | On Track | - | -
SPAA | CP 16/365 | Update to MDD A0163- Payment Method Code for smart meter models | No | No | No | No | No | SPAA-CP 16/365 | C | 2016-11-01 | C | 2016-12-15 | C | 2017-01-02 | 44 | 18 | Awaiting implementation | On Track | - | -
SPAA | CP 16/370A | Alternate: Refining the Needs Codes information | No | No | No | No | No | SPAA-CP 16/370A | C | 2017-01-01 | C | 2017-02-01 | 0 | 2017-06-30 | 31 | 149 | Issued in Change Pack | On Track | 0 | 0
SPAA | CP 17/371 | To reference ‘MAP 24’ within Schedule 38 | No | No | No | No | No | SPAA-CP 17/371 | C | 2017-01-01 | C | 2017-02-01 | C | 2017-06-30 | 31 | 149 | Issued in Change Pack | On Track | - | -
SPAA | CP 17/372 | Implementation of the Approved Meter Installer Governance | No | No | No | No | No | SPAA-CP 17/372 | C | 2017-01-01 | C | 2017-02-01 | C | 2017-04-01 | 31 | 59 | Issued in Change Pack | On Track | - | -
SPAA | CP 17/373 | Reordering Schedule 32 | No | No | No | No | No | SPAA-CP 17/373 | C | 2017-01-01 | C | 2017-02-01 | C | 2017-06-30 | 31 | 149 | Issued in Change Pack | On Track | - | -
SPAA | CP 17/374 | Introducing a funding mechanism into Schedule 32 | No | No | No | No | No | SPAA-CP 17/374 | C | 2017-01-01 | C | 2017-02-01 | C | 2017-09-01 | 31 | 212 | Issued in Change Pack | On Track | - | -
SPAA | CP 17/375 | Removal of reference to commercial disputes from Schedule 32 | No | No | No | No | No | SPAA-CP 17/375 | C | 2017-01-01 | C | 2017-02-01 | C | 2017-06-30 | 31 | 149 | Issued in Change Pack | On Track | - | -
SPAA | CP 17/376 | Xoserve funding and Governance Impacts | No | No | No | No | No | SPAA-CP 17/376 | C | 2017-01-01 | C | 2017-02-01 | C | 2017-04-01 | 31 | 59 | Withdrawn | On Track | - | -
SPAA | CP 17/377 | Amendments to Prepayment Tariff Pages | No | No | No | No | No | SPAA-CP 17/377 | C | 2017-01-01 | C | 2017-02-01 | C | 2017-04-01 | 31 | 59 | Issued in Change Pack | On Track | - | -
SPAA | CP 17/378 | Amendments to Prepayment Tariff Pages | No | No | No | No | No | SPAA-CP 17/378 | C | 2017-01-01 | C | 2017-02-01 | E | TBD | 31 |  | Issued in Change Pack | On Track | Modication due to be implemented 5 Working Days after Authority Decision | -
SPAA | CP 17/379 | Introduction of an Unidentified Funds Process in Schedule 25 | No | No | No | No | No | SPAA-CP 17/379 | C | 2017-02-16 | C | 2017-03-14 | E | 2017-06-30 | 26 | 108 | Issued in Change Pack | On Track | - | -
SPAA | CP 17/380 | Amendments to Schedule 32 in relation to the Provision of Services Regulations | No | No | No | No | No | SPAA-CP 17/380 | C | 2017-02-17 | C | 2017-03-14 | E | 2017-07-01 | 25 | 109 | Issued in Change Pack | On Track | - | -
SPAA | CP 17/381 | Introducing Failed Status in the Asset Status Code (A0037) for In Home Display. | No | No | No | No | No | SPAA-CP 17/381 | C | 2017-02-18 | C | 2017-03-14 | E | 2017-11-03 | 24 | 234 | Issued in Change Pack | On Track | - | -
SPAA | CP 17/382 | Amendments to Prepayment Tariff Pages – Updated following legal review | No | No | No | No | No | SPAA-CP 17/382 | C | 2017-03-03 | C | 2017-03-15 | E | TBD | 12 |  | Issued in Change Pack | On Track | Urgent The proposed implementation date is 5 working days after Authority approval | CMA
SQSS | GSR012 | Treatment of Interconnectors | No | No | Yes | No | Yes | SQSS-GSR012 | C | 2010-10-05 | E | TBD | E | TBD |  |  | Assessment | At Risk | Workgroup meetings need to re-convene following 1 year hiatus. | -
SQSS | GSR014 | Offshore Transformer Requirements | No | No | No | No | No | SQSS-GSR014 | C | 2012-11-19 | E | TBD | E | TBD |  |  | Assessment | At Risk | Finalising report | -
SQSS | GSR016 | Embedded Generation Scaling | No | No | No | No | Yes | SQSS-GSR016 | C | 2013-07-22 | E | TBD | E | TBD |  |  | Assessment | On Track | - | -
SQSS | GSR017 | Treatment of Switch Faults in Operational Timescales | No | No | No | No | No | SQSS-GSR017 | C | 2014-02-05 | E | TBD | E | TBD |  |  | Raised | On Track | - | -
SQSS | GSR018 | Treatment of Sub-Synchronous Oscillations in the NETS SQSS | No | No | No | No | Yes | SQSS-GSR018 | C | 2014-12-04 | E | TBD | E | TBD |  |  | Raised | On Track | - | GC0077
SQSS | GSR022 | Review of Security and Economy Planned Transfer Conditions | No | No | No | No | Yes | SQSS-GSR022 | C | 2016-06-01 | E | TBD | E | TBD |  |  | Raised | On Track | - | -
SQSS | SQSS Potential Change 1 | European TSOG -Minimum Required Inertia | No | No | No | No | No | SQSS-SQSS Potential Change 1 | E | 2017-10-01 | E | TBD | E | 2018-10-01 |  | 365 | Upcoming | On Track | - | -
SQSS | SQSS Potential Change 2 | European TSOG Implementation -Regional Outage Coordination | No | No | No | No | No | SQSS-SQSS Potential Change 2 | E | 2018-01-01 | E | TBD | E | 2018-10-01 |  | 273 | Upcoming | On Track | - | -
SQSS | SQSS Potential Change 3 | European TSOG - Requirements | No | No | No | No | No | SQSS-SQSS Potential Change 3 | E | 2018-01-01 | E | TBD | E | 2018-10-01 |  | 273 | Upcoming | On Track | - | -
STC | STC Potential Change 1 | European TSOG - Multi TSO Training Cooperation | No | No | Yes | No | Yes | STC-STC Potential Change 1 | E | 2017-10-01 | E | TBD | C | 2018-10-01 |  | 365 | Upcoming | On Track | - | EU Regulation/Law
STC | STC Potential Change 2 | European TSOG Implementation - Data Exchange | No | No | Yes | No | Yes | STC-STC Potential Change 2 | E | 2017-10-01 | E | TBD | C | 2018-10-01 |  | 365 | Upcoming | On Track | - | EU Regulation/Law
STC | STC Potential Change 3 | European TSOG Implementation -Regional Outage Coordination | No | No | Yes | No | Yes | STC-STC Potential Change 3 | E | 2018-01-01 | E | TBD | C | 2018-12-01 |  | 334 | Upcoming | On Track | This mod is set to be raised in Q1 2018 | EU Regulation/Law
STC | CM059 | Changes to Section C and H following OFGEM Response to Adjudication Request | No | No | No | No | No | STC-CM059 | C | 2016-09-21 | E | TBD | E | TBD |  |  | Assessment | On Track | - | -
UNC | 0597 | Rules for the release of incremental capacity at Interconnection Points | No | No | Yes | No | Yes | UNC-0597 | C | 2016-10-10 | E | 2017-03-31 | E | 2017-04-01 | 172 | 1 | Assessment | On Track | - | EU CAM
UNC | 0598 | Amendments to Capacity Allocations Mechanisms to comply with EU Capacity Regulations | No | No | Yes | No | Yes | UNC-0598 | C | 2016-10-10 | E | 2017-03-31 | E | 2017-04-01 | 172 | 1 | Assessment | On Track | - | EU CAM
UNC | 0599 | Amendments to Capacity Allocations Mechanisms (Interruptible) to comply with EU Capacity Regulations | No | No | Yes | No | Yes | UNC-0599 | C | 2016-10-10 | C | n/a | C | n/a |  |  | Withdrawn | On Track | Withdrawn | EU CAM
UNC | 0565 | Central Data Service Provider: General framework and obligations | No | No | No | No | Yes | UNC-0565 | C | 2015-11-05 | E | 2017-01-31 | E | 2017-04-01 | 453 | 60 | Ofgem Decision | On Track | No clear recommendation from the UNC Panel - awaiting Ofgem decision on which Alternate should be implemented | Licence - FGO
UNC | 0565A | Central Data Service Provider: General framework and obligations | No | No | No | No | Yes | UNC-0565A | C | 2016-10-10 | E | 2017-01-31 | E | 2017-04-01 | 113 | 60 | Ofgem Decision | On Track | No clear recommendation from the UNC Panel - awaiting Ofgem decision on which Alternate should be implemented | Licence - FGO
UNC | 0565B | Central Data Service Provider: General framework and obligations | No | No | No | No | Yes | UNC-0565B | C | 2016-10-26 | E | 2017-01-31 | E | 2017-04-01 | 97 | 60 | Ofgem Decision | On Track | No clear recommendation from the UNC Panel - awaiting Ofgem decision on which Alternate should be implemented | Licence - FGO
UNC | 0570 | Obligation on Shippers to provide at least one valid meter reading per meter point into settlement once per annum | No | No | No | No | Yes | UNC-0570 | C | 2015-12-03 | E | 2017-05-30 | E | 2017-08-01 | 544 | 63 | Assessment | On Track | Workgroup assessment timetable has been extended | CMA Order
UNC | 0571 | Application of Ratchets Charges to Class 1 Supply Points Only | No | No | No | No | Yes | UNC-0571 | C | 2015-12-24 | E | 2017-05-30 | E | 2017-08-01 | 523 | 63 | Assessment | On Track | Workgroup assessment timetable has been extended | -
UNC | 0571A | Application of Ratchet Charges to Class 1 Supply Points and Class 2 with an AQ above 73,200kWhs | No | No | No | No | Yes | UNC-0571A | C | 2016-05-05 | E | 2017-05-30 | E | 2017-08-01 | 390 | 63 | Assessment | On Track | Workgroup assessment timetable has been extended | -
UNC | 0587 | Seasonal Energy Balancing Credit Cover | No | No | No | No | Yes | UNC-0587 | C | 2016-06-06 | C | 2016-11-24 | C | 2017-05-01 | 171 | 158 | Awaiting Implementation | On Track | Minor changes required - and elective as required | -
UNC | 0593 | Provision of access to data for Price Comparison Websites and Third Party Intermediaries | No | No | No | No | Yes | UNC-0593 | C | 2016-08-08 | E | 2017-03-31 | E | 2017-04-01 | 235 | 1 | Assessment | On Track | - | -
UNC | 0594R | Meter Reading Submission for Advanced & Smart Metering | Yes | No | No | No | No | UNC-0594R | C | 2016-09-02 | 0 | n/a | 0 | n/a |  |  | Request | On Track | This is a UNC Request - to review the arrangements for meter reading submission. A modification is one possible output. | None- Review
UNC | 0595S | Amendment to the Arrangements between National Grid NTS and GNI at the Moffat IP to Provide for Interruption of Virtual Reverse Flow | No | No | No | No | Yes | UNC-0595S | C | 2016-09-02 | C | 2016-11-17 | C | 2016-12-09 | 76 | 22 | Implemented | On Track | No action to implement since the service was already available in Ireland | -
UNC | 0596 | Implementing CGR3 decisions on Significant Code Reviews and self-governance | No | No | No | No | Yes | UNC-0596 | C | 2016-10-07 | E | 2017-01-31 | E | 2017-02-01 | 116 | 1 | Ofgem Decision | On Track | UNC Panel recommended implementation - awaiting Ofgem decision | CGR3
UNC | 0600S | Amend obligation for the acceptance of EPDQD revisions made after D+5 | No | No | No | No | Yes | UNC-0600S | C | 2016-10-10 | E | 2017-03-16 | E | 2017-04-01 | 157 | 16 | Assessment | On Track | - | -
UNC | 0601FT | Revision of National Grid Gas plc’s Individual Network Code to reflect the correct company name | No | No | No | No | No | UNC-0601FT | C | 2016-11-01 | C | 2016-11-17 | C | 2016-12-09 | 16 | 22 | Implemented | On Track | - | -
UNC | 0602 | Implementation of Non Effective Days and Variant Non-Business Days for Project Nexus Implementation (Project Nexus transitional modification) | No | No | No | No | Yes | UNC-0602 | C | 2016-11-07 | E | 2017-03-31 | E | 2017-04-01 | 144 | 1 | Assessment | On Track | Project Nexus Steering Group has settled on '9+3' - these mods catch up the UNC (with 0602A adding an alternative view on objections) | Nexus
UNC | 0602A | Implementation of Non Effective Days and Variant Non-Business Days for Project Nexus Implementation, maintaining two Supply Point Business Days (Project Nexus transitional modification) | No | No | No | No | Yes | UNC-0602A | C | 2016-12-23 | E | 2017-03-31 | E | 2017-04-01 | 98 | 1 | Assessment | On Track | Project Nexus Steering Group has settled on '9+3' - these mods catch up the UNC (with 0602A adding an alternative view on objections) | Nexus
UNC | 0603S | Removal of liability for members of Performance Assurance Committee | No | No | No | No | Yes | UNC-0603S | C | 2016-11-08 | C | 2016-12-15 | C | 2017-01-11 | 37 | 27 | Awaiting Implementation | On Track | Minor change - no action required | -
UNC | 0604S | Central Data Services Provider – Arrangements following implementation of Project Nexus | No | No | No | No | Yes | UNC-0604S | C | 2016-11-30 | E | 2017-04-30 | E | 2017-06-01 | 151 | 32 | Assessment | On Track | - | Licence - FGO
UNC | 0605S | Amendments to TPD Section K - Additional Methods to Procure and Dispose of Operating Margins Gas | No | No | No | No | Yes | UNC-0605S | C | 2016-12-02 | E | 2017-03-31 | E | 2017-04-01 | 119 | 1 | Assessment | On Track | - | -
UNC | 0606S | National Grid Gas plc and National Grid Gas Distribution Limited transitional invoicing arrangement post Project Nexus implementation | No | No | No | No | Yes | UNC-0606S | C | 2016-12-05 | E | 2017-03-30 | E | 2017-06-01 | 115 | 63 | Assessment | On Track | - | -
UNC | 0607S | Amendment to Gas Quality NTS Entry Specification at the St Fergus NSMP System Entry Point | No | No | No | No | No | UNC-0607S | C | 2016-12-07 | E | 2017-08-30 | E | 2017-09-01 | 266 | 2 | Assessment | On Track | - | -
UNC | 0609 | Transitional arrangements for gas settlement and replacement of Meter Readings (Project Nexus transitional modification) | No | No | No | No | No | UNC-0609 | C | 2017-01-09 | C | 2017-03-16 | E | TBD | 66 |  | Issued to Workgroup | On Track | - | -
UNC | 0608S | Implementation of ‘single service provision’ arrangements for iGT connected system exit points (Project Nexus transitional modification) | No | No | No | No | No | UNC-0608S | C | 2017-01-09 | C | 2017-03-16 | E | TBD | 66 |  | Issued to Workgroup | On Track | - | -
UNC | 0610S | Project Nexus - Miscellaneous Requirements | No | No | No | No | No | UNC-0610S | C | 2017-01-11 | C | 2017-03-16 | E | TBD | 64 |  | Issued to Workgroup | On Track | - | -
UNC | 0611 | Amendments to the firm capacity payable price at Interconnection Points | No | No | No | No | No | UNC-0611 | C | 2017-02-03 | C | 2017-05-18 | E | TBD | 104 |  | Issued to Workgroup | On Track | - | -
UNC | 0612R | Project Management and Assurance provisions for gas industry changes | No | No | No | No | No | UNC-0612R | C | 2017-02-06 | C | 2017-09-12 | E | TBD | 218 |  | Issued to Workgroup | On Track | - | -
UNC | 0609A | Transitional arrangements for gas settlement and replacement of Meter Readings, retaining AQ2017 (Project Nexus transitional modification) | No | No | No | No | No | UNC-0609A | C | 2017-02-08 | C | 2017-03-16 | E | TBD | 36 |  | Issued to Workgroup | On Track | - | -
Formulas:
Raised = VLOOKUP([Change Ref],'Change Register'!B:P,11,FALSE)
Imp Decision = VLOOKUP([Change Ref],'Change Register'!B:P,13,FALSE)
Imp Date = VLOOKUP([Change Ref],'Change Register'!B:P,15,FALSE)
S = VLOOKUP([Change Ref],'Change Register'!B:P,14,FALSE)

## Change Register
Change Register
The Change Regiser is a list of live, closed and upcoming changes provided by Code Administrators to determine potential cross-code coordination opportunities to assist in forward work planning.
Updates that have been provided since the previous publication, are shown in red.
Please be aware the National Grid also provided SQSS changes, as the relevant to European Harmonisation.
FURTHER GUIDANCE |  |  |  |  | Does the change involve Smart Metering? (Yes, No) | Does the change involve HH Settlement? (Yes, No) | Does the change involve EU Harmonisation? (Yes, No) | Does the change involve switching ? (Yes, No) | Does the change involve a specific code change? Yes, No) | What is the status of the raised date? (E for Estimated or C for Confirmed) |  | What is the status of the decision date? (E for Estimated or C for Confirmed) |  | What is the Status of the implementation date? (E for Estimated or C for Confirmed) |  | At what state of progression is the change? (Upcoming, Raised, Assessment, Awaiting Implementation, Implemented) |  | Any other information or updates |  |  | What type of change? (Mod , CP) |  |  |  | Does this change need to be displayed in the FWP? (Yes,No)
Code | Change Ref | Title | Summary | Proposer | A1 | A2 | A3 | A4 | A5 | Status (raised date) | Raised | Status (imp decision date) | Imp Decision | Status (imp date) | Imp Date | Progression State | RAG Status | Commentary | Drivers | Other Codes impacted | Category of Modification | Workgroup website | Code Administrator | Live/closed | Display
BSC | BSC Potential Change 1 | Time of Interconnector Data Submission |  | National Grid | No | No | Yes | No | No | E | 2017-06-01 | E | 2018-03-01 | E | 2018-06-01 | Upcoming | - | A Modification is expected to be raised in April 2017 under Grid Code, to address the CACM requirement. If the Grid Code Modification removes the impact on the BSC, this Modification will be redundant. | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 2 | Imbalance Price (without derogation) |  | National Grid | No | No | Yes | No | No | E | 2017-10-01 | E | 2018-04-01 | E | 2018-10-01 | Upcoming | - | It is assumed that NGET will apply for a derogation for this requirement. If a derogation is approved, this Modification will be included within the scope of Potential Modification 11 "Harmonised Imbalance Settlement". | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 3 | Inclusion of Imbalance Adjustments (without derogation) |  | National Grid | No | No | Yes | No | No | E | 2017-10-01 | E | 2018-04-01 | E | 2018-10-01 | Upcoming | - | It is assumed that NGET will apply for a derogation for this requirement. If a derogation be approved, this Modification will be raised on 01/10/19 | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 4 | Align BSC with the Authority's oversight obligation |  | National Grid | No | No | Yes | No | No | E | 2017-10-01 | E | 2018-04-01 | E | 2018-10-01 | Upcoming | - | Assignment by BEIS/Ofgem and decisions by Ofgem on how it wishes to approach this requirement | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 5 | Amendments to Imbalance Price |  | National Grid | No | No | Yes | No | No | E | 2018-10-01 | E | 2019-04-01 | E | 2020-04-01 | Upcoming | - | If TSO Proposal for activiation purpose do not align with the BSC, this Modification will be raised to amend the imbalance price calculation | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 6 | Align BSC with the TSO's Terms and Conditions |  | National Grid | No | No | Yes | No | No | E | 2018-10-01 | E | 2019-04-01 | E | 2019-10-01 | Upcoming | - | If NGET write Ts & Cs in a way that differs from the Ts & Cs of the BSC, this Modification will be raised to align the BSC with the Ts & Cs of the TSO. | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 7 | Project TERRE 2 |  | National Grid | No | No | Yes | No | No | E | 2018-10-01 | E | 2019-07-01 | E | 2020-03-01 | Upcoming | - | This Modification will be raised to implement outstanding activities from Project TERRE | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 8 | Unintended exchanges of energy |  | National Grid | No | No | Yes | No | No | E | 2018-10-01 | E | 2019-04-01 | E | 2019-10-01 | Upcoming | - | Assignment Certainty on whether this Mod is reaquired, is based on the provision of infomration from NGET, on what will be proposed. | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 9 | NGET proposal on specific products |  | National Grid | No | No | Yes | No | No | E | 2018-10-01 | E | 2019-04-01 | E | 2019-10-01 | Upcoming | - | If NGET make a proposal on specific products, an assessment will be required to ensure that the understanding of specific products aligns with the BSC. If understanding of specific products in the TSO proposal, differs from the BSC, this Modification will be raised to align the BSC with the proposal. | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 10 | Market Suspension and Restoration Arrangement |  | National Grid | No | No | Yes | No | No | E | 2018-11-01 | E | 2019-08-01 | E | 2020-05-01 | Upcoming | - | If NGET makes proposals for rules concerning the suspension and restoration of market activities; and the rules for balancing energy and imbalance settlement during market suspension, that differ from the BSC, this Modification will be raised to align the BSC with the proposals. | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 3 | Inclusion of Imbalance Adjustments (with derogation) |  | National Grid | No | No | Yes | No | No | E | 2019-04-01 | E | 2020-01-01 | E | 2020-10-01 | Upcoming | - | It is assumed that NGET will apply for a derogation for this requirement. If a derogation be approved, this Modification will be raised on 01/10/19 | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 11 | Harmonised Imbalance Settlement (Includes Mod 2 with derogation) |  | National Grid | No | No | Yes | No | No | E | 2019-04-01 | E | 2020-01-01 | E | 2020-10-01 | Upcoming | - | This Modification will be raised to align the BSC with NGETs proposals to harmonise the main features of imbalance settlement If Potential Modification 2 'Imbalance Price' receives a derogation, it will be included within the scope of this Modification. | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 12 | Project mFRR |  | National Grid | No | No | Yes | No | No | E | 2019-04-01 | E | 2021-01-01 | E | 2021-10-01 | Upcoming | - | This Modification will be raised, as an extension of the principles introduced under P344 ' Project TERRE' | ENC |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 13 | Project TERRE 3 |  | National Grid | No | No | Yes | No | No | E | 2019-01-01 | E | 2019-11-01 | E | 2020-02-27 | Upcoming | - | This Modification will be raised to implementation outstanding activities from P344 'Project TERRE' | - |  | Mod |  | ELEXON | Upcoming | Yes
BSC | BSC Potential Change 14 | Ofgem SCR on HH Settlement |  |  | No | Yes | No | No | No | E | 2017-06-01 | E | 2018-03-01 | E | 2018-06-28 | Upcoming | - | - | - |  | Mod |  | ELEXON | Upcoming | Yes
BSC | CP1465 | Sending revised Meter Technical Details following a change of Meter Operator Agent | CP1465 proposes to add a new footnote only to those sections of BSCP514 that specifically relate to a change of Non Half Hourly Meter Operator Agent (NHHMOA), these being sections 6.2.1 and 6.2.4. The new footnote will be additional to footnote 30 (which will remain unchanged) and will ensure that the enhanced requirement for sending MTD applies only to the scenarios identified by the Electricity Data Quality Working Group (DQWG). | ELEXON | No | No | No | No | Yes | C | 2016-06-13 | C | 2016-09-06 | C | 2017-02-23 | Implemented | On track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1465-2/ | ELEXON | Live | Yes
BSC | CP1466 | Removing SMETS compliant Meters from the scope of BSCP601 ‘Metering Protocol Approval and Compliance Testing’ | CP1466 proposes to remove the requirement of protocol approval and compliance testing for Smart Metering Equipment Technical Specifications (SMETS) compliant Meters. This will be achieved by removing SMETS compliant Meters from the scope of BSCP601. | ELEXON | No | Yes | No | No | No | C | 2016-06-14 | C | 2016-12-08 | C | 2017-02-23 | Implemented | On track | - | Settlement Reform Advisory Group recommendations | No | CP | https://www.elexon.co.uk/change-proposal/cp1466/ | ELEXON | Closed | Yes
BSC | CP1469 | Changes to support the implementation of the SRAG’s recommendations | CP1469 seeks to introduce new processes for getting smart Meter data from the Supplier to the HHDC. The validation and estimation requirements are also defined under this CP for smart Meters. | ELEXON | No | Yes | No | No | No | C | 2016-07-19 | C | 2016-10-04 | C | 2017-06-29 | Awaiting Implementation | On track | - | Settlement Reform Advisory Group recommendations | No | CP | https://www.elexon.co.uk/change-proposal/cp1469/ | ELEXON | Closed | Yes
BSC | CP1470 | Housekeeping Change to CoPs 1, 2, 3 and 5 following P266 | CP1470 proposes to make a Housekeeping Change to correct the manifest error in CoPs 1, 2, 3 and 5. This will amend the sections which incorrectly reference section 4.3.1 ‘Overall Accuracy’ section as 4.2.1 | ELEXON | No | No | No | No | No | C | 2016-08-12 | C | 2016-10-04 | C | 2017-02-23 | Implemented | On track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1470/ | ELEXON | Closed | No
BSC | CP1471 | Housekeeping - discrepancies in the requirements of the CRA URS | CP1471 seeks to make a Housekeeping Change to amend discrepancies between the Central Registration Agent (CRA) User Requirements Specification (URS) and the content of the New Electricity Trading Arrangements (NETA) Interface Definition and Design (IDD). | ELEXON | No | No | No | No | Yes | C | 2016-10-04 | C | 2016-10-04 | C | 2017-02-23 | Implemented | On track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1471/ | ELEXON | Closed | No
BSC | CP1472 | Removal of SVA proving tests for Meters with a pulse multiplier of one | CP1472 proposes to amend BSCPs 502, 514 and 601 to remove the requirement for proving test for Meters that only have a pulse multiplier of one. It also proposes a new process for the validation of complex sites. | NPower | No | No | No | No | Yes | C | 2016-09-14 | C | 2017-01-24 | C | 2017-02-23 | Implemented | On track | - | BSC Audit Issue Review Group | No | CP | https://www.elexon.co.uk/change-proposal/cp1472/ | ELEXON | Closed | Yes
BSC | CP1473 | Alteration to the LTV Entry Criteria | CP1473 seeks to alter the qualification criteria to be more reflective of the ‘Remain’ criteria. A Site will be able to be enter into the LTV process even if D0004s with SVCC’s of 18, 19, 20 and 28 are received in between the two qualifying D0004s with a SVCC 02. Proactive attempts to indentify the owner to obtain meter reads via mail or phone will still be required. | British Gas | No | No | No | No | Yes | C | 2016-10-05 | E | 2017-01-03 | C | 2017-02-23 | Implemented | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1473-2/ | ELEXON | Closed | Yes
BSC | CP1474 | Updating the CoMC processes to facilitate the elective HH Settlement of SMETS Meters | CP1474 proposes to create new Change of Measurement Class processes for smart Meters. | ELEXON | No | Yes | No | No | No | C | 2016-10-14 | C | 2017-01-04 | C | 2017-06-29 | Awaiting Implementation | On Track | - | Ofgem’s Elective half-hourly settlement: conclusions paper | No | CP | https://www.elexon.co.uk/change-proposal/cp1474/ | ELEXON | Live | Yes
BSC | CP1475 | Remove obligation to re-date final NHH Meter readings on CoMC | CP1475 proposes to stop the re-dating of final Non Half Hourly (NHH) reading(s) on a Change of Measurement Class (CoMC) from NHH to Half Hourly (HH). This will be achieved by removing the process step where the NHH Meter Operator Agent (MOA) re-dates the meter register reading(s) in BSCP514. | E.ON | No | Yes | No | No | No | C | 2016-10-14 | C | 2017-01-03 | C | 2017-06-29 | Awaiting Implementation | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1475/ | ELEXON | Live | Yes
BSC | CP1476 | Facilitation of Incremental LLFs | CP1476 proposes to amend BSCP128 Appendix 7 to allow LDSOs to submit incremental changes their Line Loss Factor data set. | ELEXON | No | No | No | No | Yes | C | 2016-10-27 | E | 2017-01-31 | E | 2017-06-29 | Awaiting Implementation | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1476/ | ELEXON | Live | Yes
BSC | CP1477 | Updates to BSCP537 Appendix 1 as a result of P283 | CP1477 proposes to update BSCP537 Appendix 1 to account for the new Commissioning obligations introduced by P283. Specifically, this CP will update the guidance to answering questions around the Commissioning process. | ELEXON | No | No | No | No | Yes | C | 2016-11-07 | E | 2017-04-04 | E | 2017-06-29 | Assessment | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1477/ | ELEXON | Live | Yes
BSC | CP1478 | Automate the loading of the DF Matrix | CP1478 seeks to automate the loading of Trading Disputes information into the DF matrix in the Supplier Volume Allocation Agent system. It is proposed that this will reduce the risk of error associated with the current manual data entry process. | ELEXON | No | No | No | No | No | C | 2016-11-22 | E | 2017-02-28 | E | 2017-11-02 | Awaiting Implemenation | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1478/ | ELEXON | Live | Yes
BSC | CP1479 | Updates to the Defined Metering Points in Codes of Practice 1, 2, 3, 5 and 10 | CP1479 proposes to amend CoPs 1, 2, 3, 5 and 10 in order to resolve the three issues highlighted and implement the recommendations in the Issue 54 Report. | ELEXON | No | No | No | No | Yes | C | 2016-11-23 | E | 2017-02-20 | E | 2017-11-02 | Assessment | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1479/ | ELEXON | Live | Yes
BSC | CP1480 | Creation of a new authorisation category for corrections to BOA related data | CP1480 proposes the creation of a new authorisation category specifically for this activity. Details of individuals in this new category would be made available to the TC for the purpose of seeking consent for corrections to BOA related data to be made. | National Grid | No | No | No | No | No | C | 2016-11-28 | E | 2017-02-28 | E | 2017-06-29 | Assessment | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1480/ | ELEXON | Live | Yes
BSC | CP1481 | Housekeeping Change to BSCP536 following approval of P339 | CP1481 proposes to make a housekeeping change following approval of P339. | ELEXON | No | No | No | No | Yes | C | 2016-12-14 | E | 2017-01-26 | E | 2017-04-01 | Awaiting Implementation | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1481/ | ELEXON | Live | Yes
BSC | CP1482 | Upgrade of NHHDA and EAC/AA systems from Oracle 11g to version 12c | The current versions of NHHDA and EAC/AA applications that ELEXON provides to Party Agents run on Oracle 11g, for which Oracle Corporation will withdraw application support in 2018. The Oracle 11g platform was installed as part of CP1383 in June 2013. It will be necessary to complete an Upgrade to Oracle 12c as soon as possible in order to ensure continuity of service. | ELEXON | No | No | No | No | Yes | C | 2017-01-05 | E | TBD | E | 2017-11-02 | Assessment | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1482/ | ELEXON | Live | Yes
BSC | CP1483 | Changes to BSCP550 – Shared Metering Arrangements | This CP will make it a requirement for Suppliers to inform their agents, at the time of agent appointments, of the allocation schedule and any technical information necessary for the agent to deploy that solution. | ELEXON | No | No | No | No | Yes | C | 2017-01-18 | E | TBD | E | 2017-11-03 | Assessment | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1483/ | ELEXON | Live | Yes
BSC | P272 | Mandatory Hlaf Hourly Settlement for Profle Classes 5-8 | P272 proposes to make HH Settlement mandatory for all Metering Systems within PCs 5-8 (where capable metering has been installed), as the Proposer believes that the use of Non Half Hourly (NHH) data is not as accurate and masks individual customer behaviour. | Smartest Energy | Yes | Yes | No | No | No | C | 2011-05-20 | C | 2014-10-29 | C | 2017-04-01 | Awaiting Implementation | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p272-mandatory-half-hourly-settlement-for-profile-classes-5-8/ | ELEXON | Live | Yes
BSC | P297 | Receipt and Publication of New and Revised Dynamic Data items | P297 proposes to amend the BSC to reflect the changes in the Dynamic Data Set under the Grid Code. Sections Q and V of the BSC will need to be updated whilst the BMRS will need to be modified to receive and publish the new and revised Dynamic Data from the Transmission Company. | National Grid | No | No | No | No | Yes | C | 2013-07-24 | C | 2014-04-28 | C | TBD | Awaiting Implementation | On Track | Due to further EBS delays, the Panel requested a revised Implementation Date for P297. The revised implementation date is TBD | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p297/ | ELEXON | Live | Yes
BSC | CP1484 | Introduction of Additional SVAA Validation at SVA Run time | This CP proposes to introduce validation measures to reduce errors. Firstly, individual DA data will be validated and checked for the plausibility of the consumption values. Secondly, it will ensure there is a complete set of DA data ready for the VAR. Lastly, it will include checks on the results of VARs. | ELEXON | No | No | No | No | Yes | C | 2017-02-08 | E | TBD | E | 2017-11-03 | Assessment | On Track | - | - | No | CP | https://www.elexon.co.uk/change-proposal/cp1483/ | ELEXON | Live | Yes
BSC | P308 | Alternative security product for securing credit under the BSC | P308 proposes to introduce a centrally provided alternative security product as an alternative method for securing credit under the BSC, which Parties could use in place of the existing requirements to provide Credit Cover individually. | Eggborough Power | No | No | No | No | Yes | C | 2014-06-04 | E | 2017-02-01 | E | TBD | Withdrawn | At risk | The Proposer’s Representative withdrew Modification P308 on 2 February 2017. | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p308/ | ELEXON | Live | Yes
BSC | P320 | Reporting on Profile Classes 5 – 8 Metering Systems after the implementation of P272 | P320 proposes to remove the relevant paragraphs that require PARMS changes introduced by P272 | British Gas | No | Yes | No | No | No | C | 2015-03-13 | C | 2015-09-09 | C | 2017-04-01 | Awaiting Implementation | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p320/ | ELEXON | Live | Yes
BSC | P321 | Publication of Trading Unit Delivery Mode | P321 proposes to publish information on the direction of delivery (delivering or offtaking) of Trading Units, particularly for each Grid Supply Point (GSP) Group, in each Settlement Period. | Smartest Energy | No | No | No | No | Yes | C | 2015-04-01 | C | 2015-10-08 | C | 2017-06-29 | Awaiting Implementation | On Track | P321 was originally approved under Self-Governance on 8 October 2015 for implementation on 30 June 2016. On 5 January 2016, the Panel wrote to the Authority to request the approved Implementation Date be deferred to 3 November 2016. The Authority approved this request on 26 January 2016. On 9 June 2016, the Panel wrote to the Authority to request the approved Implementation Date be deferred to 29 June 2017. The Authority approved this request on 8 August 2016. P321 will therefore be implemented on 29 June 2017 as part of the June 2017 BSC Systems Release. | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p321/ | ELEXON | Live | Yes
BSC | P325 | Improving the accountability of BSCCo to stakeholders and better aligning BSCCo governance with best practice | The P325 proposes to amend proposes to amend the current provisions in BSC Section C to permit ELEXON to undertake roles and activities outside the BSC, subject to the approval of BSC Parties. | SSE Energy Supply Ltd | No | No | No | No | Yes | C | 2015-07-30 | E | TBD | E | TBD | Assessment | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p325/ | ELEXON | Live | Yes
BSC | P326 | Introduction of a non-Working Day adjustment to the Credit Cover Percentage calculation | P326 proposes to introduce a method to account for reductions in Supplier demand on non-Working Days within the Credit Cover calculations. | Haven Power | No | No | No | No | Yes | C | 2015-08-25 | C | 2016-04-14 | C | 2017-02-23 | Implemented | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p326/ | ELEXON | Live | Yes
BSC | P329 | Changes to REMIT inside information reporting | P329 proposes to align the BSC and Balancing Mechanism Reporting Service (BMRS) with the Regulation on Wholesale Energy Markets Integrity and Transparency (REMIT) common schemas for inside information web feeds, required by the Agency for the Cooperation of Energy Regulators (ACER). | National Grid | No | No | Yes | No | No | C | 2015-11-25 | C | 2016-04-19 | C | 2017-06-29 | Awaiting Implementation | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p329/ | ELEXON | Live | Yes
BSC | P332 | Revisions to the Supplier Hub Principle | P332 seeks to address issues associated with customers choosing Party Agents, instead of Party Agents being appointed by Suppliers. The Modificaiton propsoes to make Party Agents signatories to the BSC and make all of their activities directly accountable to the Performance Assurance Board (PAB) and ELEXON. | Smartest Energy | No | No | No | No | Yes | C | 2016-01-28 | E | TBD | E | TBD | Assessment | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p332/ | ELEXON | Live | Yes
BSC | P335 | Inclusion of Non-BM STOR costs and volumes in the indicative cashout price | P335 seeks to facilitate the submission of non-BM STOR costs and volumes such that they can be included in the indicative cashout price | ENGIE | No | No | No | No | Yes | C | 2016-02-19 | C | 2016-09-19 | C | 2017-11-02 | Awaiting Implementation | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p335/ | ELEXON | Live | Yes
BSC | P336 | Fuel types on the BMRS | P336 proposes to add ‘biomass’ as a specific fuel type category reported on the Balancing Mechanism Reporting Service (BMRS). It also seeks to allow the Panel to approve further fuel types without needing to raise a Modification. | Drax Power Limited | No | No | No | No | Yes | C | 2016-02-29 | C | 2016-04-14 | C | 2017-11-02 | Awaiting Implementation | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p336/ | ELEXON | Live | Yes
BSC | P338 | Consequential changes to P272 legal text | P338 proposes to make consequential changes to the approved legal text for P272 ‘Mandatory Half Hourly Settlement for Profile Classes 5-8’, to resolve conflicts that exist between it and certain approved Modifications. | BSC Panel | No | Yes | No | No | No | C | 2016-04-14 | C | 2016-04-14 | C | 2017-04-01 | Awaiting Implementation | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/consequential-changes-to-p272-legal-text/ | ELEXON | Live | Yes
BSC | P339 | Introduction of new Consumption Component Classes for Measurement Classes E-G | P339 seeks to introduce new Consumption Component Classes (CCCs) for Measurement Classes “E”, “F” and “G” to enable aggregated consumption volumes for both Active Import (AI) and Active Export (AE) to be identified separately. | Ovo | No | Yes | No | No | No | C | 2016-05-04 | C | 2016-12-08 | C | 2017-04-01 | Awaiting Implementation | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p339/ | ELEXON | Live | Yes
BSC | P341 | MEL and other data earlier than Gate Closure | P341 seeks to mandate the Transmission Company to send MEL and MIL data to the BMRA for a period up to two days ahead to the BMRA for publication. | EDF | No | No | No | No | Yes | C | 2016-05-20 | E | 2017-04-01 | E | TBD | Assessment | At risk | Awaiting confirmation from Ofgem and a decision on progression from the Workgroup. | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p341/ | ELEXON | Live | Yes
BSC | P342 | Change to Gate Closure for Energy Contract Volume Notifications | P342 proposes to introduce a new deadline for the purpose of submitting Energy Contract Volume Notifications (ECVNs) and Metered Volume Reallocation Notifications (MVRNs) for each Settlement Period. | EDF | No | No | Yes | No | Yes | C | 2016-05-25 | E | 2016-12-08 | C | 2017-11-02 | Awaiting Implementation | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p342/ | ELEXON | Live | Yes
BSC | P343 | Increase to the number of Supplier IDs that can be held by a Supplier | P343 proposes to allow a Supplier to apply for a fourth or more Supplier IDs through an application form submitted to the Panel. | RWE npower | No | No | No | No | Yes | C | 2016-05-26 | C | 2016-11-10 | C | 2017-02-23 | Implemented | On Track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p343/ | ELEXON | Live | Yes
BSC | P344 | Project TERRE implementation into GB market arrangements | P344 seeks to align the Balancing and Settlement Code (BSC) with the European Balancing Project TERRE (Trans European Replacement Reserves Exchange) requirements. This is in order to allow the implementation of the project at national level and be compliant with the first tranche of obligations in the European Network Codes (ENCs). | National Grid | No | No | Yes | No | No | C | 2016-06-01 | C | 2017-09-21 | E | 2018-09-01 | Assessment | On track | Project TERRE is currently set to go-live in Q3 2018. | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p344/ | ELEXON | Live | Yes
BSC | P346 | Changes to Specific Charges for Elective HH Settlement | P346 proposes to reduce BSC costs to Suppliers for entering domestic and small non-domestic customers into elective Half Hourly (HH) Settlement and could encourage Suppliers to promote such Settlement on a larger scale | British Gas | No | Yes | No | No | No | C | 2016-06-23 | C | 2016-11-10 | C | 2017-04-01 | Awaiting Implementation | On Track | Approved. Awaiting implementation in April Standalone release | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p346/ | ELEXON | Live | Yes
BSC | P347 | Reduction in R1 Read Threshold | 347 seeks to reduce the R1 Read requirement to 90% for Measurement Classes “F” and “G”. | Npower | Yes | Yes | No | No | No | C | 2016-07-01 | E | 2017-02-10 | C | 2017-04-01 | Awaiting Implementation | On Track | On 19 January the Panel considered the Sendback Direction from the Authority and approved the revised Final Modification Report for P347. The Panel maintained its recomendation to the Authority that P347 should be rejected. The revised Final Modification Report was submitted to the Authority for decision on 19 January 2017. On 30 January 2017 the Authority determined that P347 should be Approved and implemented on 1 April 2017. | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p347/ | ELEXON | Live | Yes
BSC | P348 | Provision of gross BM Unit data for TNUoS charging | P348 seeks to enable the Supplier Volume Allocation Agent (SVAA) to provide gross export and gross import data to the Transmission Company (TC) to support proposed revisions to the Transmission Network Use of System (TNUoS) Charging methods under Connection Use of System Code (CUSC) Modification Proposal (CMP) 265 ‘Gross charging of TNUoS for HH demand where embedded generation is in Capacity Market’. | EDF | No | No | No | No | Yes | C | 2016-07-01 | E | 2017-04-13 | E | 2019-11-07 | Assessment | On Track | This Modification will be progressed in line with P349. | Transmission Network Use of System (TNUoS) Charging changes | No | Mod | https://www.elexon.co.uk/mod-proposal/p348/ | ELEXON | Live | Yes
BSC | P349 | Facilitating Embedded Generation Triad Avoidance Standstill | P349 introduce a requirement under the BSC for Suppliers that are the registrants of New Embedded Generators to tell their Half Hourly Data Aggregators (HHDAs) which Metering System IDs (MSIDs) relate to New Embedded Generation. They will also be requited to tell their HHDAs to provide Period Metered Data from these MSIDs to the Transmission Company (TC) in the most efficient and cost-effective manner. | ScottishPower | No | No | No | No | Yes | C | 2016-07-04 | E | 2017-04-13 | E | 2017-06-29 | Assessment | On Track | New Embedded Generators will be defined for the purpose of this Modification by Connection Use of System Code (CUSC) Modification Proposal (CMP) 264 ‘Embedded Generation Triad Avoidance Standstill’. The implementation of CMP264 requires both SVA and CVA meter data flows for new embedded generation. It is believed that the Transmission Company already receives the necessary CVA metered data to allow for the benefits of CMP264 to be realised. If this assumption is proved invalid, this Modification will require including CVA as well as SVA registered generators. | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p349/ | ELEXON | Live | Yes
BSC | P350 | Introduction of a seasonal Zonal Transmission Losses scheme | P350 proposes to introduce a Transmission Loss Factor for each TLF Zone (which will align with the existing Grid Supply Point (GSP) Groups) for each BSC Season in order to allocate transmission losses on a geographical basis. | National Grid | No | No | No | No | Yes | C | 2016-07-05 | E | 2017-03-31 | E | 2018-04-01 | Assessment | On Track | The CMA has placed obligations on National Grid to raise a Modification, for implementation by 1 April 2018. If the Modification is not implemented in time, then National Grid will be required to implement the same technical solution on the same date but outside of the BSC. The BSC Panel will make its final reccomendation to Ofgem on 9 Febraury 2017. Ofgem is expected to make its final decision by the end of March 2017. | CMA | No | Mod | https://www.elexon.co.uk/mod-proposal/p350/ | ELEXON | Live | Yes
BSC | P351 | Align the BSC with changes to the SCR requirements | P351 seeks to introduce three routes for taking forward the conclusions of an SCR. It is hoped that this will accelerate the change process and enable more efficient delivery of priority Modifications. | National Grid | No | No | No | No | Yes | C | 2016-07-29 | C | 2017-01-19 | E | 2017-04-01 | Awaiting Implementation | On Track | Initially rejected by Panel. Report consultation now closed and Final report decision on 19/1/17 | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p351/ | ELEXON | Live | Yes
BSC | P353 | Fast Track Self-Governance Mod following P324 | P353 proposes to make consequential changes to the approved legal text for P324 ‘Review of BSCCo’s governance: introducing improved accountability to BSC Parties’ to remove text no longer required in Section B 3.1.2 (h). | Panel | No | No | No | No | Yes | C | 2016-11-10 | C | 2016-12-08 | C | 2017-01-06 | Implemented | On track | - | - | No | Mod | https://www.elexon.co.uk/mod-proposal/p353/ | ELEXON | Live | Yes
BSC | P354 | Use of ABSVD for non-BM Balancing Services at the metered (MPAN) level | P354 proposes to allow the System Operator to provide Applicable Balancing Services Volume Data (ABSVD) volume at the MPAN level and the Settlement Administration Agent (SAA) to allocate this to the appropriate Supplier BM Unit. | ENGIE | No | No | No | No | Yes | C | 11-Jan-17 | E | TBD | E | TBD | Assessment | - | - | - | MRA | Mod | https://www.elexon.co.uk/mod-proposal/p354/ | ELEXON | Live | Yes
CUSC | CMP250 | Stabilising BSUoS with at least a twelve month notice period | The defect this modification seeks to address is that industry parties have no real certainty of their BSUoS costs when forward contracting their power. This is directly caused by the current BSUoS charging methodology that produces a highly volatile and unpredictable cost. This modification allows parties to know ahead of time what their BSUoS charge will be, and to reallocate this risk from those parties that are poorly placed to manage the risk, in particular smaller market participants, to a party that is better suited to deal with it . | Drax Power | No | No | No | No | Yes | C | 2015-08-19 | E | 2017-07-10 | E | 2017-07-17 | Assessment | At Risk | - | CMP250 | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP250/ | National Grid | Live | Yes
CUSC | CMP251 | Removing the error margin in the cap on total TNUoS recovered by generation and introducing a new charging element to TNUoS to ensure compliance with European Commission Regulation 838/2010 | CMP251 aims to ensure that there is no risk of non-compliance with European Regulation 838/2010 by removing the error margin introduced by CMP224 and by introducing a new charging element to the calculation of TNUoS. CMP251 has been raised as Urgent by the Proposer. | British Gas | No | No | No | No | Yes | C | 2015-08-28 | C | 2016-10-14 | E | TBD | Authority Decision | - | - | - | None | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP251/ | National Grid | Live | Yes
CUSC | CMP259 | Clarification of decrease in TEC as a Modification | CMP259 aims to amend the CUSC to enable a User to request both a TEC reduction and a subsequent TEC increase in the form of a single modification application to National Grid | RWE | No | No | No | No | Yes | C | 2016-05-22 | C | 2016-10-14 | E | TBD | Authority Decision | - | - | - | None | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP259/ | National Grid | Closed | Yes
CUSC | CMP261 | Ensuring the TNUoS paid by Generators in GB in Charging Year 2015/16 is in compliance with the €2.5/MWh annual average limit set in EU Regulation 838/2010 Part B (3) | Having due regard for Regulation (EC) No 714/2009, the Commission Regulation (EU) No 838/2010 entitled “Guidelines for a Common Regulatory Approach to Transmission Charging” was introduced to provide a common regulatory approach to transmission charging across all the Member States. This Regulation, in Part B (paragraph 3), restricts the annual average transmission charges paid by electricity generators in Great Britain to the range of €0/MWh to €2.50/MWh. | SSE | No | No | No | No | Yes | C | 2016-03-11 | C | 2016-11-30 | E | TBD | Authority Decision | - | - | - | None | Urgent | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP261/ | National Grid | Live | Yes
CUSC | CMP264 | Embedded Generation Triad Avoidance Standstill | CMP264 seeks to make changes to the Transport and Tariff Model and billing arrangements to remove the netting of output from New Embedded Generators until Ofgem has completed its consideration of the current electricity transmission Charging Arrangements (and any review which ensues) and any resulting changes have been fully implemented. | Scottish Power | No | No | No | No | Yes | C | 2016-05-27 | C | 2016-11-28 | E | TBD | Authority Decision | - | - | - | BSC & CMP265 | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP264/ | National Grid | Live | Yes
CUSC | CMP265 | Gross charging of TNUoS for HH demand where embedded generation is in Capacity Market | CMP265 specifically seeks to address the issue that half hourly metered (HH) demand for TNUoS purposes is currently charged net of embedded generation. CMP265 has been proposed as urgent, we are awaiting a decision from Ofgem on this. | EDF Energy | No | No | No | No | Yes | C | 2016-05-27 | C | 2016-11-28 | E | TBD | Authority Decision | - | - | - | BSC & CMP264 | Urgent | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP265/ | National Grid | Live | Yes
CUSC | CMP266 | Removal of Demand TNUoS charging as a barrier to future elective Half Hourly settlement | CMP266 seeks to prevent double charging of TNUoS for a meter electing to be HH settled, all demand within Measurement Class F & G will be charged under the TNUoS NHH methodology from April 2017 up until HH settlement is mandatory for all consumers. | National Grid | No | No | No | No | Yes | C | 2016-07-05 | C | 2016-11-30 | E | 2016-12-22 | Implemented | - | - | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP266/ | National Grid | Closed | Yes
CUSC | CMP268 | Recognition of sharing by Conventional Carbon plant of Not-Shared Year-Round circuits | Recognition of sharing by Conventional Carbon plant of Not-Shared Year-Round circuits | SSE | No | No | No | No | Yes | C | 2016-08-02 | E | TBD | E | TBD | Workgroup | - | - | - | No | Urgent | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP268/ | National Grid | Live | Yes
CUSC | CMP269 | Potential consequential changes to the CUSC as a result of CMP264 | This modification aims for the CMP264 Workgroup to address a number of consequential changes required to non-charging sections of the CUSC to reflect the CMP264 Proposal or any alternative proposals agreed by the CMP264 Workgroup. | SP | No | No | No | No | Yes | C | 2016-08-26 | C | 2016-11-28 | E | TBD | Authority Decision | - | - | Consequential of CMP264 |  | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP269/ | National Grid | Live | Yes
CUSC | CMP270 | Potential consequential changes to the CUSC as a result of CMP265 | This modification aims for the CMP265 Workgroup to address a number of consequential changes required to non-charging sections of the CUSC to reflect the CMP265 Proposal or any alternative proposals agreed by the CMP265 Workgroup. | EDF Energy | No | No | No | No | Yes | C | 2016-08-19 | C | 2016-11-28 | E | TBD | Authority Decision | - | - | Consequential of CMP265 |  | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP270/ | National Grid | Live | Yes
CUSC | CMP271 | Improving the cost reflectivity of demand transmission charges | This CUSC modification proposal aims to improve the cost reflectivity of demand transmission charges. It is proposed that the transmission charging methodology should include a Peak Security demand tariff levied at Triad, a Year Round demand tariff and revenue recovery levied on year round supplier demand. | RWE | No | No | No | No | Yes | C | 2016-09-20 | E | 2018-03-16 | E | 2021-04-01 | Assessment | On Track | - | CMP271 | SQSS | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP271/ | National Grid | Live | Yes
CUSC | CMP272 | Aligning Condition C5 of the CUSC to changes introduced by the Code Governance Review Phase 3 | CMP272 seeks to implement the license changes to the CUSC arising from Ofgem’s Code Governance Review (Phase 3). | National Grid | No | No | No | No | Yes | C | 2016-09-29 | E | 2017-03-07 | E | 2017-03-14 | Assessment | On Track | - | CMP272 | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP272/ | National Grid | Live | Yes
CUSC | CMP274 | Winter TNUoS Time of Use Tariff (TToUT) for Demand TNUoS | This CUSC modification proposal aims to improve the cost reflectivity of demand transmission charges. It is proposed that the transmission charging methodology should include a Winter Weekday Time of use demand tariff which reflects the existing Demand Residual element of the existing methodology so that revenue recovery is levied over a longer period of assessment. | UK Power Reserve | No | No | No | No | Yes | C | 2016-09-29 | E | 2018-03-16 | E | 2021-04-01 | Assessment | On Track | - | CMP274 | SQSS | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP274/ | National Grid | Live | Yes
CUSC | CMP275 | Transmission Generator Benefits in the provision of ancillary and balancing services – levelling the playing field. | CMP275 seeks that a principle of financial mutual exclusivity is introduced to prevent BM units from accessing multiple sources of duplicate and overlapping revenue from ancillary services on the same asset | UK Power Reserve | No | No | No | No | Yes | C | 2017-01-18 | E | TBD | E | TBD | Assessment | On Track | - | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/CUSC/Modifications/CMP275/ | National Grid | Live | Yes
CUSC | CUSC Potential Change 1 | European Energy Balancing Guidelines - Replacement Reserves | European Energy Balancing Guidelines - Replacement Reserves | National Grid | No | No | Yes | No | Yes | E | 2017-10-01 | E | TBD | E | 2018-10-01 | Upcoming | On Track | This mod is set to be raised in Q4 2017. This mod is set to be implemented in Q4 2018. | EU Regulation/Law | Yes | Mod | N/A | National Grid | Upcoming | Yes
CUSC | CUSC Potential Change 2 | European Energy Balancing Guidelines - Manual Frequency Restoration Reserves (mFRR) | European Energy Balancing Guidelines - Manual Frequency Restoration Reserves (mFRR) | National Grid | No | No | Yes | No | Yes | E | 2020-07-01 | E | TBD | E | 2021-07-01 | Upcoming | On Track | This mod is set ot be raised Q3 2020. This mod is set to be implemented in Q3 2021 | EU Regulation/Law | Yes | Mod | N/A | National Grid | Upcoming | Yes
Dcode | DCRP1702 | Implementation of the Ofgem CGR3 recommendation on Significant Code Review | This Modification, therefore, seeks to align the Distribution Code and the Distribution Code Constitution and Rules with the amended provisions for Significant Code Review. The creation of this Modification was directed by Ofgem as part of the CGR3. Although it will impact the governance of the Distribution Code and the Distribution Code Constitution and Rules Distribution Code with specific changes applied to DIN 2.1 of the Code and Section 21 of the Constitution and Rules these changes will be focussed on the SCR process | ENA | No | No | Yes | No | Yes | E | 2017-12-08 | E | TBD | E | TBD | Awaiting Implementation | On Track | RTA submitted on 09/03/17 | CGR3 |  | Mod | http://www.dcode.org.uk/dcrp/17/02.html | ENA | Upcoming | Yes
Dcode | Dcode Potential Change 1 | Implementation of the requirements of the European Network Code - Demand Connection | This modification will cater for the introduction of the new ER G99 which will replace ER G59 for all new geneartaion connections from May 2019 | ENA | No | No | Yes | No | Yes | E | TBD | E | TBD | E | TBD | Upcoming | On Track | Will be raised at the the time of the GC0048 housekeeping mods | EU Regulation/Law | Grid Code | Mod |  | ENA | Upcoming | Yes
Dcode | Dcode Potential Change 2 | Changes to DOC 5 of the Distribution Code | This modification seek to take cognisance of the consequential Changes to the Distribution Code on Entry into Force of the Transmission System Operation Guidelines EU Network Code.For the Distribution Code and its scope, there are two places where specific articles in the TSOG require activities that are probably implicit in the GB arrangements, but are infrequently (if ever) exercised and are not explicitly recognized in the D Code drafting.Article 54.2 requires a User to notify the DNO if there is any “operational disturbance” which affects itability to retain compliance. It is suggested that a simple amendment to the definition of “event” as used predominantly in DOC7 (and DOC9) of the D Code would cover off this requirement. Article 54.3 requires the DNO to recognize a User initiated test plan so that the User can establish compliance (or for other reasons). The ability of a User to initiate such tests, separate from those jointly undertaken at commissioning etc, is only implicit in the D Code (and G59). A simple modification to DOC5 would make the testing provisions of DOC5 reciprocal in that they can be initiated formally by either DNO or the User. | ENA | No | No | Yes | No | Yes | E | 2017-12-08 | E | TBD | E | TBD | Upcoming | On Track | RTA submitted on 09/03/17 | EU Regulation/Law | Grid Code | Mod | http://www.dcode.org.uk/dcrp/17/01.html | ENA | Upcoming | Yes
Dcode | Dcode Potential Change 3 | To Implement within the Dcode the Fast Fault Current Injection requirements contained within the EU Network Code - Requirements for Generators | This modification will cater for the application of Fast Fault Current Injection requirements to Power Generating Modules. | GC 0048 | No | No | Yes | No | Yes | E | 2017-06-30 | E | TBD | E | TBD | Upcoming | TBC | Depends on National Grid GC 0048 modification | EU Regulation/Law | Grid Code | Mod | TBC | ENA | Upcoming | Yes
Dcode | Dcode Potential Change 4 | To Implement within the Dcode the Fault Ride Through requirements contained within the EU Network Code - Requirements for Generators | This modification will cater for the application of voltage / reactive power capability requirements to Power Generating Modules which are of Type B or above within the Dcode. | GC 0048 | No | No | Yes | No | Yes | E | TBD | E | TBD | E | TBD | Upcoming | TBD | Depends on National Grid GC 0048 modification | EU Regulation/Law | Grid Code | Mod | TBC | ENA | Upcoming | Yes
Dcode | Dcode Potential Change 5 | To Implement within the Dcode the Frequency Response requirements contained within the EU Network Code - Requirements for Generators | This modification will cater for the application of voltage / reactive power capability requirements to Power Generating Modules. | GC 0048 | No | No | Yes | No | Yes | E | TBD | E | TBD | E | TBD | Upcoming | TBD | Depends on National Grid GC 0048 modification | EU Regulation/Law | Grid Code | Mod | TBC | ENA | Upcoming | Yes
Dcode | Dcode Potential Change 6 | To Implement within the Dcode the Reactive Power and Voltage Control requirements contained within the EU Network Code - Requirements for Generators | This modification will cater for the application of voltage / reactive power capability requirements to Power Generating Modules which are of Type B or above within the Dcode. | GC 0048 | No | No | Yes | No | Yes | E | TBD | E | TBD | E | TBD | Upcoming | TBD | Depends on National Grid GC 0048 modification | EU Regulation/Law | Grid Code | Mod | TBC | ENA | Upcoming | Yes
Dcode | Dcode Potential Change 7 | Implementation of the new Engineering Recommendation G98 | This modification will cater for the introduction of the new ER G98 which will replace ERG83 for all new geneartaion connections from May 2019 | ENA | No | No | Yes | No | Yes | E | TBD | E | TBD | E | TBD | Upcoming | TBD | Target for public consultation Sept 2017 | EU Regulation/Law | Grid Code | Mod | TBC | ENA | Upcoming | Yes
Dcode | Dcode Potential Change 8 | Implementation of the new Engineering Recommendation G99 | This modification will cater for the introduction of the new ER G99 which will replace ER G59 for all new geneartaion connections from May 2019 | ENA | No | No | Yes | No | Yes | E | TBD | E | TBD | E | TBD | Upcoming | TBD | TBC | EU Regulation/Law | Grid Code | Mod | TBC | ENA | Upcoming | Yes
Dcode | Dcode Potential Change 9 | Implementation of the Transmission System Operators Guidelines | This modification will cater for the introduction of the new ER G99 which will replace ER G59 for all new geneartaion connections from May 2019 |  | No | No | Yes | No | Yes | E | TBD | E | TBD | E | TBD | Upcoming | TBD | TBC | EU Regulation/Law | Grid Code | Mod | TBC | ENA | Upcoming | Yes
DCUSA | DCP 138 | Implementation of alternative network use factor (NUF) calculation method in EDCM | This CP seeks to amend the method of calculating Network Use Factors for EDCM demand customers as defined within DCUSA to address the concerns raised by Ofgem in Condition 3 of the Ofgem decision document on EDCM import charges published in September 2011. | SSE Energy Supply Limited | No | No | No | No | No | C | 2012-06-18 | C | 2015-10-09 | C | 2017-04-01 | Awaiting Implementation | On Track | - | - | No | CP | DCP 138 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 160 | Non-Half Hourly (NHH) Notional Capacity | This CP seeks to revise Schedule 16 (along with appropriate CDCM and ARP Modelling changes) to introduce a notional spare capacity requirement to be applied to the average maximum demand when calculating NHH tariffs. The notional spare capacity should align with the same proportions which are calculated and allocated to Half Hourly (HH) tariffs. | UK Power Networks | No | Yes | No | No | No | C | 2013-01-08 | C | 2016-10-18 | n/a | n/a | Authority Rejected the change | On Track | Authority Rejected the change | - | No | CP | DCP 160 Working Group | ElectraLink | Closed | No
DCUSA | DCP 161 | Excess Capacity Charges | To improve the cost reflectivity of the excess capacity charge calculation within the CDCM and EDCM by removing the customer contributions and adding in any additional costs that should be attributed to this charge. Also, to consider applying the excess capacity charge on either a monthly, seasonal or time of day basis. | Electricity North West Limited | No | No | No | No | No | C | 2013-02-06 | C | 2015-10-21 | C | 2018-04-01 | Awaiting Implementation | On Track | - | - | No | CP | DCP 161 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 169 | Seasonal Time of Day (SToD) HH Metered Tariffs in the CDCM | This CP seeks remove the restriction in paragraph 135 of Schedule 16 of DCUSA in order to allow the use of Seasonal Time of Day (SToD) tariffs to be calculated and applied. | UK Power Networks | No | Yes | No | No | No | C | 2013-03-13 | E | TBD | E | TBD | Assessment | At Risk | CP on Hold - Working Group is awaiting Ofgem decision on DCP 228 before deciding on how to proceed with DCP 169. DCP 225 is due to be implemented 1 Apr 2018 | - | No | CP | DCP 169 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 181 | Previous Connection Terms Enduring | Where a distributor has agreed a bi-lateral connection agreement with an owner or occupier in respect of a connection point, those terms should bind on change of ownership or occupation. | UK Power Networks | No | No | No | No | No | C | 2013-06-17 | C | 2016-06-15 | C | 2016-10-01 | Implemented | On Track | - | - | No | CP | DCP 181 Working Group | ElectraLink | Closed | No
DCUSA | DCP 204 | Smart Metering Related Amendments to Schedule 8 | The intent of this Change Proposal (CP) is to amend DCUSA Schedule 8 to reflect the migration of load switching technologies deployed by Suppliers in customer premises from established devices, such as radio teleswitches (RTS) and timeswitches, to smart metering technologies. | Scottish and Southern Electric Power Distribution | Yes | No | No | No | No | C | 2014-02-27 | C | 2016-02-23 | C | 2016-09-01 | Implemented | On Track | - | - | No | CP | DCP 204 Working Group | ElectraLink | Closed | No
DCUSA | DCP 209 | Resolving Unregistered Customers | This CP seeks to improve communications with unregistered customers, set out processes for managing unregistered customers up to, but excluding, the registration process itself and where necessary new obligations on parties. | Nothern Powergrid | No | No | No | No | No | C | 2014-05-08 | C | 2016-08-30 | C | 2016-10-01 | Implemented | On Track | - | - | Proposed addition of a note to the MRA dataflows. | CP | DCP 209 Working Group | ElectraLink | Closed | No
DCUSA | DCP 222 | Non Billing Of Excess Reactive Power Charges | This CP proposes the removal of the excess reactive power charge when a DNO requests that a generator operates outside of the 0.95 power factor limit. | Western Power Distribution | No | No | No | No | No | C | 2014-12-02 | C | 2016-08-15 | C | 2018-04-01 | Awaiting Implementation | On Track | - | - | No | CP | DCP 222 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 226 | Housekeeping 66/72/73/77/80 | This CP seeks to review and revise the DCUSA document to incorporate housekeeping log items 66/72/73/77/80 | UK Power Networks | No | No | No | No | Yes | C | 2015-01-05 | E | TBD | E | TBD | Assessment | At Risk | CP on Hold - housekeeping change to review refrences throuout the DCUSA Document. Work on this is to be carried out after the 1 October 2016 DCUSA Release. | - | No | CP | DCP 226 | ElectraLink | Live | Yes
DCUSA | DCP 227 | Removing the inconsistency in the application of Peaking Probabilities in the CDCM | ​The proposal changes the way that peaking probabilities are applied in the CDCM and therefore affects CDCM tariffs. | British Gas | No | No | No | No | No | C | 2015-01-13 | C | 2015-10-21 | C | 2017-04-01 | Awaiting Implementation | On Track | - | - | No | CP | DCP 227 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 228 | Revenue Matching in the CDCM | ​The intent of this proposal is to change the way revenue matching (scaling) is achieved within the CDCM to accurately reflect the price differentials produced by the cost-reflective incremental 500MW model. Currently this is achieved in a manner which primarily affects only the day/red unit prices. This change proposal intends to replace the current method of revenue matching such that all unit rates face the same absolute p/kWh adjustment (except where any unit rates are subject to a floor price). | British Gas | No | No | No | No | No | C | 2015-01-13 | C | 2016-09-08 | C | 2018-04-01 | Awaiting Implementation | On Track | - | - | No | CP | DCP 228 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 234 | Merging the PCDM and extended PCDM | To replace the Price Control Disaggregation (PCDM) and extended PCDM models with one model.To create a new schedule in DCUSA which contains the legal text that relates to IDNO charging that is currently contained in Schedules 16, 17 and 18. | Electricity North West Limited | No | No | No | No | No | C | 2015-02-27 | C | 2016-08-03 | C | 2018-04-01 | Awaiting Implementation | On Track | - | - | No | CP | DCP 234 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 243 | Treatment of Customer Contributions in the CDCM | ​This CP seeks to revise DCUSA Schedule 16 to utilise current source data to determine a common industry set of modelling inputs in order to improve clarity in the approach to be used in calculating ‘Customer contribution under the current connection charging policy’ for use in CDCM table 1060. | UK Power Networks | No | No | No | No | No | C | 2015-06-05 | E | TBD | E | TBD | Assessment | On Track | Under Development - Working Group developing the CP solution | - | No | CP | DCP 243 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 244 | MOP Leaving Site for Cat A Situations | ​This CP seeks to remove the DNO Intervention SLA for attending Category A jobs where the MOP operative will not or has not remained on site. And to address housekeeping issues with the DCP 195A legal text | UK Power Networks | No | No | No | No | No | C | 2015-06-19 | E | TBD | E | TBD | Assessment | At Risk | CP on Hold - Working Group is waiting for Operational Delivery Group (ODG) to develop MOP guidance on leaving site where there is a category A situation. | - | No | CP | DCP 244 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 251 | Clarification And Extension Of The Application Of LDNO Tariffs Under The CDCM | The intent of this proposal is to Correct drafting errors in the specification of the distribution systems that are eligible for LDNO tariffs under the CDCM and under the EDCM.2. Ensure that there the charging methodologies do not impose undue discrimination between licensed and licence-exempt distribution systems.3. Restore the 50 per cent LDNO discount on indirect costs which was removed by the approved legal text for DCP 185 in cases where the fixed adder is negative.​ | The Electricity Network Company | No | No | No | No | No | C | 2015-10-15 | E | TBD | E | TBD | Assessment | On Track | Under Development - Working Group developing the CP solution DCP251/2 WG meeting indicated that the change declaration may be issued in June 2017, with an Ofgem decision anticipated in August 2017 | - | BSC & MRA -Change of arrangements to how Unlicensed Customers are charged could have an impact upon both the MRA and BSC in relation to data flows or arrangements for operation | CP | DCP 251 & DCP 252 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 252 | Clarification And Extension Of The Application Of Portfolio Tariffs Under The EDCM | The intent of this proposal is toCorrect drafting errors and inconsistencies in the specification of the distribution systems that are eligible for Portfolio tariffs under the EDCM (schedules 17 and 18).2. Establish arrangements that ensure that methodologies in schedules 17 and 18 do not impose undue discrimination between licensed and licence exempt distribution systems.​ | The Electricity Network Company | No | No | No | No | No | C | 2015-10-15 | E | TBD | E | TBD | Assessment | On Track | Under Development - Working Group developing the CP solution DCP251/2 WG meeting indicated that the change declaration may be issued in June 2017, with an Ofgem decision anticipated in August 2017 | - | BSC & MRA - Change of arrangements to how Unlicensed Customers are charged could have an impact upon both the MRA and BSC in relation to data flows or arrangements for operation | CP | DCP 251 & DCP 252 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 253 | Retightening and remaking of whole current metering system terminal connections. | ​This Change Proposal seeks to permit a DNO/IDNO, when it replaces its service cut-out, to retighten the meter tails and customer tails connecting into and out of a whole current meter and/or remake connections to meter terminals as necessary prior to re-energisation. | UK Power Networks | No | No | No | No | No | C | 2015-11-03 | C | 2016-09-21 | C | 2016-09-01 | Implemented | On Track | - | - | No | CP | DCP 253 Working Goup | ElectraLink | Closed | No
DCUSA | DCP 255 | Changes to Electricity (Connection Charges) Regulations 2002 | ​This Change Proposal (CP) seeks to incorporate changes in the CCCM as a result of changes to the Electricity (Connection Charges) Regulations 2002​. | Electricity North West Limited | No | No | No | No | No | C | 2015-11-06 | E | TBD | E | TBD | Assessment | On Track | The Working Group are awaiting the receipt of the final ECCR 2016 legal text from BEIS (formaly DECC) before progressing this change. | - | No | CP | DCP 255 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 256 | Change to DCUSA to mitigate risks of non-payment of non-payment of DCUSA invoices | ​This DCP seeks to improve the transparency of likely DCUSA costs to enables Parties to better plan and budget for DCUSA invoices as well as improving the effectiveness of the arrangements for following up of non-payment of DCUSA invoices. | British Gas | No | No | No | No | No | C | 2015-11-10 | C | 2016-09-21 | C | 2016-10-01 | Implemented | On Track | - | - | No | CP | DCP 256 Working Group | ElectraLink | Closed | No
DCUSA | DCP 262 | Schedule 19 Credit/Re-invoice for HH Specific Data | ​The intent of this CP is to include a timeline for credit/re-invoice from DNOs to LDNOs upon the receipt of updated HH DUoS data | ESP Electricity Limited | No | Yes | No | No | No | C | 2016-01-13 | C | 2016-07-29 | C | 2016-09-01 | Implemented | On Track | - | - | No | CP | DCP 262 Working Group | ElectraLink | Closed | No
DCUSA | DCP 263 | NTC DEH Gap | This CP seeks to amend the NTC so that they cater for DNOs’ connections to non-metered DEH networks.There should be no impact from this change on the applicability of the NTC to boundary metered DEHs or on the contractual terms suppliers put in place by virtue of Schedule 2A of DCUSA. | UK Power Networks | No | No | No | No | No | C | 2016-01-22 | E | 17/01/201 | E | 2017-02-23 | Change Report issued for Voting | On Track | Change Report issued for Voting | - | No | CP | DCP 263 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 264 | Introduction of Energy Theft Tip Off Line Service | This CP seeks to include provisions relating to the Energy Theft Tip Off Line Service in the DCUSA. | E.ON UK Plc | No | No | No | No | No | C | 2016-02-15 | C | 2016-08-15 | C | 2016-08-22 | Implemented | On Track | - | - | No | CP | ETTOS Working Group | ElectraLink | Closed | No
DCUSA | DCP 266 | The calculation and application of IDNO discounts | This change seeks to change the way in which DNO tariffs to IDNOs are calculated in the CDCM. Instead of calculating an IDNO percentage discount by comparing the avoided total cost (p/kWh) with the total cost (p/kWh) in the CDCM “Price Control Disaggregation Model” (PCDM), the intent of this change proposal is that the avoided total cost (p/kWh) calculated in the PCDM is compared with the average p/kWh figure for each All The Way (ATW) CDCM tariff in order to determine the IDNO % discount factor to be applied to each of the tariff components of the CDCM ATW tariff. | British Gas | No | No | No | No | No | C | 2016-03-09 | E | n/a | E | n/a | Assessment | On Track | Under Development - Working Group developing the CP solution | - | No | CP | DCP 266 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 267 | Introduction of a new definition for 'Confirmed Theft' | This CP introduces a definition for Confirmed Theft under DCUSA to ensure consistency across Suppliers in submitting confirmed theft detections under TRAS. | British Gas | No | No | No | No | No | C | 2016-03-09 | C | 2016-09-14 | C | 2016-11-03 | Implemented | On Track | - | - | No | CP | DCP 267 Working Group | ElectraLink | Closed | No
DCUSA | DCP 268 | DUoS Charging Using HH settlement data | This CP seeks to facilitate a transition to half-hourly (HH) settlement for non-half hourly (NHH) customers by moving to a time band charging basis, based on the HH (profiled) data used in settlement. | Nothern Powergrid | No | Yes | No | No | No | C | 2016-03-14 | E | TBD | E | 2018-04-01 | Assessment | On Track | Under Development - Working Group developing the CP solution | - | BSC - P339 | CP | DCP 268 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 269 | Revenue Protection Service Withdrawal Period | The intent of this CP is to require 3 months’ notice to be given by a DNO in the event that they wish to withdraw the Revenue Protection service they provide under DCUSA. | Npower Ltd | No | No | No | No | No | C | 2016-04-25 | C | 2016-07-12 | C | 2016-09-01 | Implemented | On Track | - | - | No | CP | DCP 269 Working Group | ElectraLink | Closed | No
DCUSA | DCP 270 | Removal of HV Medium tariff from CDCM | This CP seeks for the removal of the HV Medium Non-domestic tariff and consideration of the removal of both the LV and LV Sub Medium Non Domestic tariffs from the CDCM. | Nothern Powergrid | No | No | No | No | No | C | 2016-04-28 | C | 2017-11-16 | n/a | n/a | Rejected | On Track | Authority Rejected the change | - | No | CP | DCP 270 Working Group | ElectraLink | Closed | No
DCUSA | DCP 271 | TRAS - Process and Costs of Providing Additional Hunter Facilities | This change seeks to introduce a process for Suppliers who wish to procure additional Hunter facilities from the TRAS Service Provider and to make those costs transparent to the Supplier community | Npower Ltd | No | No | No | No | No | C | 2016-05-11 | C | 2016-09-15 | C | 2016-11-03 | Implemented | On Track | - | - | No | CP | TRAS Expert Group | ElectraLink | Closed | No
DCUSA | DCP 272 | TRAS – Amendment of Schedule 25 Appendix 2 | This CP seeks to introduce a clear data item list in DCUSA for delivery of the TRAS solution. | E.ON UK Plc | No | No | No | No | No | C | 2016-05-11 | C | 2016-09-15 | C | 2016-11-03 | Implemented | On Track | - | - | No | CP | TRAS Expert Group | ElectraLink | Closed | No
DCUSA | DCP 273 | Align CDCM table 1001 (target revenue) to latest Schedule 15 template | The intent of this proposal is to align table 1001 in the CDCM to the current format of table in Schedule 15. | Nothern Powergrid | No | No | No | No | No | C | 2016-05-18 | C | 2016-10-14 | C | 2018-04-01 | Awaiting Implementation | On Track | - | - | No | CP | DCP 273 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 274 | The application of export capacity charges in the EDCM | The intent of this change proposal is to amend the EDCM methodology to ensure that distributed generation and storage sites do not pay distribution use of system charges for the import and export from a site where the same assets are used. | Neas Energy Limited | No | No | No | No | No | C | 2016-06-10 | E | TBD | E | 2018-04-01 | Assessment | On Track | Under Development - Working Group developing the CP solution | - | No | CP | DCP 274 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 275 | Code Governance Review 3 & SLC 22 | The CP seeks to implement the distribution licence changes arising from Ofgem’s Code Governance Review Phase 3 Final Proposals impacting DCUSA governance. | UK Power Networks | No | No | No | No | No | C | 2016-06-10 | C | 2016-11-15 | C | 2017-02-23 | Awaiting Implementation | On Track | - | - | No | CP | DCP 275 | ElectraLink | Live | Yes
DCUSA | DCP 276 | Amendments to CDCM LV Substation Tariff ‘Note 5’ | This Change Proposal intends to amend the text of Note 5 to Paragraph 144 of Schedule 16 (the CDCM), to: 1)Remove the customer or supplier evidence terms in Note 5, to better reflect responsibilities for allocation of a customer’s DUoS tariff; and 2)Require LV Substation tariff charges to be applied from when a customer became eligible for this tariff, subject to limitations legislation. | Scottish and Southern Electric Power Distribution | No | No | No | No | No | C | 2016-07-04 | C | 2016-09-14 | C | 2016-11-03 | Implemented | On Track | - | - | No | CP | DCP 276 | ElectraLink | Closed | No
DCUSA | DCP 277 | Schedule 25 – Amendment to Appendix 2 - Conditionality | Following on from the changes in DCP272 the TRAS Expert Group has reviewed the conditionality for data items within the TRAS Service Providers Programming Manual and seeks to update some of the data items conditional/mandatory status because the current conditionality cannot be always met. Additionally, some JCode/RGMA Codes also require back population as they were missed on the original drafting. | E.ON UK Plc | No | No | No | No | No | C | 2016-07-13 | C | 2016-11-17 | C | 2017-02-23 | Awaiting Implementation | On Track | - | - | No | CP | TRAS Expert Group | ElectraLink | Live | Yes
DCUSA | DCP 278 | Allocation of Users to the ETTOS Secure Email Service | This CP seeks to include the rules for allocation of user accounts for the ETTOS secure email service in the DCUSA | Npower Ltd | No | No | No | No | No | C | 2016-07-13 | C | 2016-12-15 | C | 2017-02-23 | Awaiting Implementation | On Track | - | - | No | CP | ETTOS Working Group | ElectraLink | Live | Yes
DCUSA | DCP 279 | Linking Credit Cover to the Annual Iteration Process | This change proposal has been submitted in order to update those clauses in DCUSA Schedule 1 (Credit Cover) that refer to the ‘Regulatory Asset Value (RAV)’ as the new price control, RIIO-ED1, redefines the calculation of a DNO’s Regulatory Asset Value. | Electricity North West Limited | No | No | No | No | No | C | 2016-07-29 | C | 2016-12-23 | C | 2017-02-23 | Awaiting Implementation | On Track | - | - | No | CP | DCP 279 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 280 | Clarification of TRAS Accession Process | This CP proposes to amend the TRAS Schedules to clarify the TRAS accession process. It has been assessed that there is a three-month time lag between a new Supplier starting to register metering systems and actually submitting data into TRAS. This time lag has not been reflected within the current TRAS Schedule and a change is required to explicitly reference the time lag so new parties are clear when they need to provide their initial data submission. The three-month time lag will also ensure that the new Supplier has time to work with the Service Provider to start submitting data. | British Gas | No | No | No | No | No | C | 2016-08-18 | C | 2016-12-15 | C | 2017-02-23 | Awaiting Implementation | On Track | The voting period was extended to align with the equivilent SPAA CP (CP16/346) | - | No | CP | DCP 280 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 281 | Changes to Schedule 19 – Portfolio Billing | This CP seeks to ensure that HH Portfolio data is reported to DNOs in a consistent manner by all embedded LDSOs and to define how revised data must be reported. | UK Power Networks | No | Yes | No | No | No | C | 2016-09-14 | E | TBD | E | 2019-04-01 | Assessment | On Track | Under Development - Working Group developing the CP solution | - | No | CP | DCP 281 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 282 | Embedded Distribution Network Operator (EDNO) UMSO | This CP seeks to facilitate the management and trading of UMS apparatus connected to EDNO networks via the “host” DNO’s UMSO service on one combined inventory, without the need for additional MPANs, following a request from the customer to the EDNO to do so. The EDNO will be deemed to have passed such a request to the DNO, through DCUSA wording, such that the DNO does not need to perform further checking or validation on any inventory it receives (i.e. to the extent of checking whether the inventory contains data for the correct EDNO or not). | UK Power Networks | No | No | No | No | No | C | 2016-09-14 | E | 2017-03-14 | E | TBD | Assessment | On Track | Under Development - Working Group developing the CP solution | - | No | CP | DCP 282 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 283 | The calculation of generation credits in the CDCM | The intent of this CP is to amend the calculation of credits for embedded generation to more closely reflect the benefits they bring to Distribution Network Operators. | MVV Environment Services Limited | No | No | No | No | No | C | 2016-10-12 | E | TBD | E | 2019-04-01 | Assessment | On Track | Under Development - Working Group developing the CP solution | - | No | CP | DCP 283 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 284 | The application of scaling to generation credits in the CDCM | The intent of this CP is to amend the calculation of credits for embedded generation to more closely reflect the benefits they bring to Distribution Network Operators by including an element of scaling. | MVV Environment Services Limited | No | No | No | No | No | C | 2016-10-12 | E | TBD | E | 2019-04-01 | Assessment | On Track | Under Development - Working Group developing the CP solution | - | No | CP | DCP 284 Working Group | ElectraLink | Live | Yes
DCUSA | DCP 285 | Schedule 23, Appendix 1 SLC References | The intent of this change is to remove references to Supply Licence Condition (SLC) 12.16 in Schedule 23, Appendix 1 and replace them with the updated SLCs. | British Gas | No | No | No | No | No | C | 2016-10-12 | E | 2017-01-24 | E | 2017-02-23 | Assessment | On Track | Under Development - legal text being updated | - | No | CP | DCP 285 Change Proposal | ElectraLink | Live | Yes
DCUSA | DCP 286 | Formalising the Theft Steering Group | This change proposes to formally delegate the DCUSA Panel and DCUSA Ltd Board powers in relation to the Theft Risk Assessment Service (TRAS) and Energy Theft Tip Off Line Service (ETTOS) to the Theft Steering Group (TSG) | E.ON UK Plc | No | No | No | No | No | C | 2016-11-09 | E | TBD | E | TBD | Assessment | On Track | Under Development - Definition Stage | - | SPAA | CP | DCP 286 Change Proposal | ElectraLink | Live | Yes
DCUSA | DCP 287 | Generation Credits in the EDCM | The intent of this Change Proposal is to amend the calculation of credits for embedded generation in the EDCM to take account of potential cost savings for DNOs that can be attributed to embedded generation in the areas of transmission exit charges, direct costs, indirect costs and network rates. | MVV Environment Services Limited | No | No | No | No | No | C | 2016-11-11 | E | TBD | E | 2019-04-01 | Assessment | On Track | - | - | No | CP | DCP 287 Change Proposal | ElectraLink | Live | Yes
DCUSA | DCP 288 | Introduction of the Electricity Theft Detection Incentive Scheme | The intent of this Change Proposal (CP) is to introduce an Electricity Theft Detection Incentive Scheme in line with Ofgem’s decision document entitled “Tackling electricity theft – the way forward” published on 4th March 2014 | British Gas | No | No | No | No | No | C | 2016-12-12 | E | TBD | E | TBD | Assessment | On Track | - | - | No | CP | DCP 288 Change Proposal | ElectraLink | Live | Yes
DCUSA | DCP 289 | Creation of Distribution Charging Methodology Development Group | The intent of this CP is to formalise the creation of a new single Standing Issues Working Group for the Use of System charging methodologies and related topics within DCUSA. | South Eastern Power Networks plc | No | No | No | No | No | C | 2016-12-16 | E | TBD | E | TBD | Assessment | On Track | - | - | No | CP | DCP 289 Change Proposal | ElectraLink | Live | Yes
DCUSA | DCP 290 | Housekeeping Change to Update PCDM Model References | The intent of this Change Proposal is to facilitate the updating of the title, model number and issue date of the PDCM as referenced in Schedules 16, 17 and 18, which was not correctly applied in the legal text of DCP234. | South Eastern Power Networks plc | No | No | No | No | No | C | 2017-01-17 | E | TBD | C | 2018-04-01 | Awaiting Implementation | On Track | - | - | No | CP | DCP 290 Change Proposal | ElectraLink | Live | Yes
DCUSA | DCP 291 | Application of Generation Credits to EDCM Customers | The intent of this Change Proposal is to apply EDCM generation credits to all generators whether intermittent or non-intermittent, on the basis that a LRIC/FCP charge 1 exists. | Western Power Distribution (East Midlands) plc | No | No | No | No | No | E | 2017-02-17 | E | TBD | E | 2019-04-01 | Definition | On Track | - | - | No | CP | DCP 291 Change Proposal | ElectraLink | Live | Yes
DCUSA | DCP 292 | Align DCUSA Schedule 15 table 3 to the CDCM tariff structure following the approval DCP 222 ‘Non billing of Excess Reactive Power Charges’ | This CP seeks to amend DCUSA Schedule 15 to reflect the CDCM tariffs introduced as a result of the approval of DCP 222 ‘Non billing of Excess Reactive Power Charges’. | Northern Powergrid (Northeast) Ltd | No | No | No | No | No | E | 2017-02-10 | E | TBD | E | 2017-06-29 | Change Report | On Track | - | - | No | CP | DCP 292 Change Proposal | ElectraLink | Live | Yes
DCUSA | DCP 293 | Charging Methodology Cut-off Date | DCUSA has a requirement for DNOs to provide fifteen months’ notice of changes to Use of System charges. This necessitates DNOs to have complete and final versions of the charging methodologies and a complete and final suite of fully tested charging models (CDCM, EDCM, PCDM and ARP) for the relevant charging year prior to initiating the calculation and validation of revised charges. This change looks to establish a cut-off date for the finalisation of the charging methodologies at 17 months prior to the date that the methodology would become effective. Establishing this cut-off date will provide a 2-month time window for DCUSA to provide charging models and DNOs to test the new charging models and then to calculate, test and approve revised charges. | South Eastern Power Networks plc | No | No | No | No | No | E | 2001-02-14 | E | TBD | E | 2017-10-01 | Definition | On Track | - | - | No | CP | DCP 293 Change Proposal | ElectraLink | Live | Yes
GC | GC0048 | Requirements for Generators - Implementation of European Network Code | Requirements for Generators (RfG) – which sets functional requirements that new generators connecting to the network (both distribution and transmission) will need to meet, as well as responsibilities on TSOs and DNOs. This includes: Fault Ride Through, Fast fault Current Injection, Voltage & Reactive, Compliance and system management. Additional items to be included as this progresses are: Banding Threshold Setting, Frequency response and House Keeping | National Grid | No | No | Yes | No | Yes | C | 2013-07-01 | C | TBD | C | 2018-05-17 | Raised | On Track | This is a workgroup, and it is expected that this workgroup will manage the raising of all additional modifications required to deliver The deadline for EIF is fixed. National Implementation Compliance date is 17/05/2018 | European Regulation/Law | Yes | Joint Working Group | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0048/ | National Grid | Live | Yes
GC | GC0077 | Suppression of Sub-Synchronous Resonance from Series Capacitive Compensation | It is proposed that the Grid Code is changed to provide clarity that Transmission Licensees installing Series Capacitive Compensation devices or HVDC Convertors will ensure that Sub-synchronous Resonance and Sub-synchronous Torsional Interaction risks are appropriately mitigated. | National Grid | No | No | No | No | Yes | C | 2013-08-14 | E | 2017-03-01 | E | 2017-04-01 | Assessment | On Track | - | - | SQSS | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0077/ | National Grid | Live | Yes
GC | GC0079 | GC0035 / GC0079 Frequency Changes during Large Disturbances and their effect on the total system - Phase 1 & 2 | GC0035 / GC0079 Frequency Changes during Large Disturbances and their effect on the total system - Phase 1 & 2 | National Grid | No | No | No | No | Yes | C | 2008-05-21 | E | TBD | E | TBD | Assessment | At Risk | Ongoing for 8 years with with deliberations over funding arrangements to be decided. | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0079/ | National Grid | Live | Yes
GC | GC0086 | Open Governance | This seeks to allow parties other than NGET to raise Modification Proposals to the Grid Code and to introduce a number of principles that currently exist in some of the other industry codes. | National Grid | No | No | No | No | Yes | C | 2014-07-02 | E | 2017-02-01 | E | 2017-03-01 | Assessment | On Track | - | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0086/ | National Grid | Live | Yes
GC | GC0087 | Requirements for Generators Frequency Provisions | Proposals to develop the Frequency Response provisions of the Grid Code under GC0022 did not reach a conclusion. National Grid believes that there are a number of outstanding defects with the Frequency Response provisions of the Grid Code which should be addressed in a new Workgroup. | National Grid | No | No | No | No | Yes | C | 2014-11-04 | E | 2017-07-01 | E | 2017-08-01 | Assessment | On Track | - | GC0022 | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0087/ | National Grid | Live | Yes
GC | GC0090 | HVDC - Implementation of European Network Code | HVDC – sets functional requirements for HVDC connections including offshore HVDC networks which connect Offshore generation schemes. This will include: Fault Ride Through, Voltage & Reactive, Frequency Response, Compliance & House Keeping | National Grid | No | No | Yes | No | Yes | C | 2015-07-01 | C | TBD | C | 2018-09-29 | Raised | On Track | This is a workgroup, and it is expected that this workgroup will manage the raising of all additional modifications required to deliver Deadline for EIF is fixed. National Implementation Compliance date is 29/09/2018 | European Regulation/Law | No | Issues Working Group | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0090/ | National Grid | Live | Yes
GC | GC0091 | Application of the the Demand Connection Code - Implementation of European Network Code | Demand Connection Code (DCC) – which sets out the functional requirement for new demand users and Distribution Network connections, as well as responsibilities on TSOs and DNOs. This will include: Technical requirements, Demand Side Response and housekeeping | National Grid | No | No | Yes | No | Yes | C | 2016-03-01 | C | TBD | C | 2018-09-07 | Raised | On Track | This is a workgroup, and it is expected that this workgroup will manage the raising of all additional modifications required to deliver. Deadline for EIF is fixed. National Implementation Compliance date is 07/09/2018 | European Regulation/Law | Yes | Joint Working Group | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0091/ | National Grid | Live | Yes
GC | GC0095 | GB implementation workgroup for Transmission System Operation Guideline (TSOG) European Network Code | This is a workgroup to deliver the requirements TSOG Implementation - this includes: Blackout State Threshold, Roles an Responsibilities of the SGUs and Operational Testing, Data Exchange, Coordinated Security Analysis, Regional Outage Coordination, Operational Agreements, Reserve Providers | National Grid | No | No | Yes | No | Yes | C | 2016-05-27 | E | TBD | C | 2018-10-01 | Assessment | On Track | All areas of TSOG are curently held within one workgroup, this may change as modification are raised to deliver respective areas are completed There is a range of Entry into Force dates ranging to October 2018 | EU Regulation/Law | Yes | Working Group | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0095/ | National Grid | Live | Yes
GC | GC0096 | Energy Storage | This is a Grid Code Workgroup to consider the appropriate technical requirements for Energy Storage technologies connecting to the Transmission system | National Grid | No | No | No | No | Yes | C | 2016-05-18 | E | 2017-05-01 | E | 2017-06-01 | Assessment | On Track | - | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0096/ | National Grid | Live | Yes
GC | GC0097 | European Energy Balancing Guidelines - Replacement Reserves - TERRE | Compliance with changes introduced from the European Energy Balancing Guidelines assocoaited with Project TERRE | National Grid | No | No | Yes | No | Yes | E | 2016-11-16 | C | TBD | E | 2019-07-01 | Assessment | On Track | This modification maybe required to address changes associated with project TERRE Deadline for EIF is fixed. This mod is set to be implemented Q3 2019. | EU Regulation/Law | Yes | Working Group | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0097/ | National Grid | Live | Yes
GC | Grid Code Potential Change 1 | Implementation of CACM European Network Code | Enable data provision between NGET and other TSOs to align with European requirements (provisional) | National Grid | No | No | Yes | No | Yes | E | 2017-01-01 | C | TBD | E | 2018-01-01 | Upcoming | On Track | This modification may be required to address the requirements of the Common Grid Model This mod is currently set to be raised in Q1 2017 Deadline for EIF is fixed. Compliance for CGM is Jan 2018 - and TBC based on methodologies | European Regulation/Law | Yes | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 2 | European Energy Balancing Guidelines - General Compliance | Compliance with changes introduced from the European Energy Balancing Guidelines | National Grid | No | No | Yes | No | Yes | E | 2017-01-01 | E | TBD | E | 2018-07-01 | Upcoming | On Track | This modification maybe required to address general compliance requirements of the EB GL The mod if currently set to be raised in Q1 2020. Deadline for EIF is fixed. The mod if set to be implemented in Q3 2021. | EU Regulation/Law | Yes | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 3 | European Energy Balancing Guidelines - Manual Frequency Restoration Reserves (mFRR) | Compliance with changes introduced from the European Energy Balancing Guidelines | National Grid | No | No | Yes | No | Yes | E | 2020-01-01 | E | TBD | E | 2021-07-01 | Upcoming | On Track | This modification maybe required to address mFRR requirements of the EB GL This mod is set to be raised in Q1 2020. Deadline for EIF is fixed. This mod is set to be implemented in Q3 2021. | EU Regulation/Law | Yes | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 4 | European Emergency & Restoration Code - System Defence & Restoration Plan | European Emergency & Restoration Code - System Defence and Restoration Plan, resulntant mods dependeant on plan contents | National Grid | No | No | Yes | No | Yes | E | 2017-07-01 | E | TBD | E | 2018-07-01 | Upcoming | On Track | This mod is set to be raised in Q2 2017. This mod is set to be implemente din Q3 2018. | EU Regulation/Law | TBD | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 5 | European RfG Banding and RfG/HVDC requirements | Changes needed resulting from RfG Banding and Fast Fault Current Injection, as well as RfG and HVDC Fault Ride Through | National Grid | No | No | Yes | No | Yes | E | 2017-04-19 | E | TBD | E | 2018-04-01 | Upcoming | On Track | This mod is set to be raised in Q2 2017. This mod is set to be implementedin Q2 2018. | EU Regulation/Law | TBD | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 6 | RfG and HVDC Voltage and Frequency Response requirements | Resultant changes in relation to RfG and HVDC Voltage/Reactive and Frequency Response requirements | National Grid | No | No | No | No | Yes | E | 2017-04-19 | E | TBD | E | 2018-01-01 | Upcoming | On Track | This mod is set to be raised in Q2 2017 Deadline for EIF is fixed. This mod is set to be implemented in Q1 2018. | EU Regulation/Law | TBD | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 7 | RfG and HVDC Compliance and System Management | Compliance and System Management | National Grid | No | No | No | No | Yes | E | 2017-06-21 | E | TBD | E | 2018-01-01 | Upcoming | On Track | This mod is set to be raised in Q2 2017 Deadline for EIF is fixed. This mod is set to be implemented in Q1 2018. | EU Regulation/Law | TBD | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 8 | DCC Technical & Demand Side Response | DCC Technical & Demand Side Response Requirements | National Grid | No | No | No | No | Yes | E | 2017-06-21 | E | TBD | E | 2018-09-01 | Upcoming | On Track | This mod is set to be raised in Q2 2017 Deadline for EIF is fixed. This mod is set to be implemented in Q3 2018. | EU Regulation/Law | TBD | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 9 | Interconnector Data Provision | Interconnector Data Provision to NGET after GB Gate Closure | National Grid | No | No | No | No | Yes | E | 2017-06-21 | E | TBD | E | 2019-01-01 | Upcoming | On Track | This mod is set to be raised in Q2 2017 Deadline for EIF is provisionally Q1 2019 | EU Regulation/Law | TBD | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 10 | Frequency Restoration Reserves | Manual Frequency Restoration Reserves | National Grid | No | No | No | No | Yes | E | 2020-01-01 | E | TBD | E | 2021-10-01 | Upcoming | On Track | This mod is set to be raised in Q1 2020 Deadline for EIF is provisionally Q3 2021 | EU Regulation/Law | TBD | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 11 | European TSOG Implementation -Regional Outage Coordination | European TSOG Implementation -Regional Outage Coordination | National Grid | No | No | No | No | Yes | E | 2018-01-01 | E | TBD | E | 2018-10-01 | Upcoming | On Track | This mod is set to be raised in Q1 2018 Deadline for EIF is provisionally Q4 2018 | EU Regulation/Law | TBD | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 12 | European TSOG - Requirements | TSOG requirements in relation to reserve providers and operational agreements | National Grid | No | No | No | No | Yes | E | 2018-01-01 | E | TBD | E | 2018-10-01 | Upcoming | On Track | This mod is set to be raised in Q1 2018 Deadline for EIF is provisionally Q4 2018 | EU Regulation/Law | TBD | Mod |  | National Grid | Upcoming | Yes
GC | Grid Code Potential Change 13 | Market Suspension | Market Suspension | National Grid | No | No | No | No | Yes | E | 2017-07-01 | E | TBD | E | 2018-10-01 | Upcoming | On Track | This mod is set to be raised in Q3 2017 Deadline for EIF is provisionally Q3 2018 | EU Regulation/Law | TBD | Mod |  | National Grid | Upcoming | Yes
SEC | SECMP0002 | Add New Command to Reset Debt Registers | This proposal seeks to add a new command to allow users to reset any of the debt registers on a meter. | RWE npower | Yes | No | No | No | Yes | C | 2016-02-19 | E | TBD | E | 2018-06-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0002 | Gemserv | Live | No
SEC | SECMP0004 | Inclusion of Device Serial Number data item in the Smart Metering Inventory | Addition of Meter Serial Number to the Smart Metering Inventory to enable mapping between data held in the DCC systems, and industry dataflows. | EDF Energy | Yes | No | No | No | Yes | C | 2016-02-19 | E | TBD | E | 2018-06-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0003 | Gemserv | Live | No
SEC | SECMP0005 | Include Tariff and Register Labels in SMETS2 Devices | Include Tariff Label and Register Labels in smart metering devices and to allow them to be published on the HAN for display to the customer via HAN devices (e.g. IHD). | E.ON | Yes | No | No | No | Yes | C | 2016-03-01 | E | TBD | E | 2018-06-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0005 | Gemserv | Live | No
SEC | SECMP0006 | Specifying the number of digits for device display | Include a specification for the number of digits for devices’ display of meter registers in SMETS2 in relation to the provision of energy measurement information. | SSE | Yes | No | No | No | Yes | C | 2016-03-01 | E | TBD | E | 2018-06-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0006 | Gemserv | Live | No
SEC | SECMP0007 | Firmware updates to mandated HAN devices | This Modification Proposal proposes including the capability to update firmware Over-The-Air (OTA) for mandated HAN devices (IHD / PPMID / HCALCS) via the DCC’s infrastructure. | RWE npower | Yes | No | No | No | Yes | C | 2016-03-01 | E | TBD | E | 2018-06-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0007 | Gemserv | Live | No
SEC | SECMP0008 | Provision of a Service Request error response for quarantined Service Requests | Provide a new DUIS Service Request error response to give DCC Service Users visibility of quarantined Service Requests following a breach of the DCC’s Anomaly Detection Threshold and / or the individual DCC Service User’s Anomaly Detection Threshold. | Scottish Power | Yes | No | No | No | Yes | C | 2016-03-01 | E | TBD | E | 2018-06-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0008 | Gemserv | Live | No
SEC | SECMP0009 | Centralised Firmware Library | Establishment of a repository of firmware images, with access provided to all Parties responsible for the management of SMETS1 and/or SMETS2 meters. | RWE npower | Yes | No | No | No | Yes | C | 2016-03-01 | E | TBD | E | 2018-06-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0009 | Gemserv | Live | No
SEC | SECMP0010 | Introduction of triage arrangements for Communication Hubs | SEC Supplier parties should be permitted to carry out basic ‘triage’ checks on Communications Hubs following their removal from a consumer’s property. | British Gas | Yes | No | No | No | Yes | C | 2016-03-02 | E | TBD | E | 2018-06-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0010 | Gemserv | Live | No
SEC | SECMP0011 | Inclusion of Meter Asset Provider Participant Code (MAP ID) Participant Codes in the Smart Metering Inventory | Addition of Meter Asset Provider Participant Code and Registered Supplier Agents – MOP & MAM Participant Codes to the Smart Metering Inventory to enable the efficient management of electricity and gas meters by: a) tracking energy suppliers use of meters; b) tracking the firmware upgrade of meters; c) tracking the removal of meters | Utility Funding Limited | Yes | No | No | No | Yes | C | 2016-03-22 | E | TBD | E | 2018-06-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0011 | Gemserv | Live | No
SEC | SECMP0012 | Channel selection to support Shared HAN solutions | The proposed modification seeks to amend the SEC and related SEC Subsidiary documents to enable channel selection/masking at the mandated 2.4GHz frequency. | Siemens Plc | Yes | No | No | No | Yes | C | 2016-05-05 | E | TBD | E | 2018-06-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0012 | Gemserv | Live | No
SEC | SECMP0013 | Smart meter device diagnostics and triage | The proposal seeks to amend the SEC and DCC’s systems to provide Suppliers with a means of performing quality assurance and fault diagnostics on SMETS2 devices returned by meter operatives. | E.ON | Yes | No | No | No | Yes | C | 2016-05-04 | E | TBD | E | 2018-06-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0013 | Gemserv | Live | No
SEC | SECMP0015 | GPF timestamp for reading instantaneous Gas values | Instantaneous GSME register values can be read from the Gas Proxy Function. These will not normally be in-line with the readings on the GSME, since the GSME only provides intermittent updates to the GPF, typically once every 30 minutes. Without a timestamp to know when the GSME last updated the GPF, the Supplier cannot know how up to date the information is. | E.ON | Yes | No | No | No | Yes | C | 2016-05-31 | E | TBD | E | 2018-06-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0015 | Gemserv | Live | No
SEC | SECMP0016 | Consideration of "Maximum Credit" value in credit cover calculation | This Modification Proposal seeks to make changes to the SEC Credit Cover Requirement calculation so that it takes into account the credit value specified by an independent credit assessor, which is similar to the approach taken for the Uniform Network Code (UNC). | First Utility Limited | Yes | No | No | No | Yes | C | 2016-06-03 | E | TBD | E | 2017-06-01 | Awaiting Authority Determination | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0016 | Gemserv | Live | No
SEC | SECMP0018 | Standard Electricity Distributor Configuration Settings | Amendments to the Great Britain Companion Specification (GBCS) to specify the standard Electricity Distributor configuration settings to be applied to an electricity smart meter by the Manufacturer. Application of default configuration settings will reduce the need for Electricity Distributors to apply settings immediately after commissioning. | Northern Powergrid | Yes | No | No | No | Yes | C | 2016-06-23 | E | TBD | E | 2018-06-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0018 | Gemserv | Live | No
SEC | SECMP0019 | ALCS Description Labels | This Proposal recommends that there should be some form of guidance / rules (Naming Conventions) / standardisation when defining any of the 5 Auxiliary Load Control Switches (ALCS) or HAN Connected Auxiliary Load Control Switch(es) (HCALCS). | SSE | Yes | No | No | No | Yes | C | 2016-07-14 | E | TBD | E | 2017-11-02 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0019 | Gemserv | Live | No
SEC | SECMP0021 | Increase Other SEC Party representation for TABASC and SSC | The Proposer would like to increase the “Other SEC Party” representation on the SSC to three and on the TABASC to four. | Landis & Gyr | Yes | No | No | No | Yes | C | 2016-10-04 | E | TBD | E | 2017-06-29 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 3 - Self Governance | SECMP0021 | Gemserv | Live | No
SEC | SECMP0023 | Correct Units of Measure for Uncontrolled Gas Flow Rate | Currently GBCS limits the values of the Uncontrolled Gas Flow rate to be in whole numbers of m3. This modification proposes to change that to allow m3 with accuracy to 3 decimal places to be specified. | RWE npower | Yes | No | No | No | Yes | C | 2016-10-26 | E | TBD | E | 2018-06-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0023 | Gemserv | Live | No
SEC | SECMP0024 | Enduring Approach to Communication Hub Firmware Management | The Proposer seeks to develop requirements for an enduring solution for a Supplier-controlled release of firmware to Communication Hubs (CHs). The Proposer’s solution is to develop and implement a CH Firmware Deployment and Activation ‘Safe Launch’ Plan, supported by new DUIS Service Requests. | E.ON | Yes | No | No | No | Yes | C | 2016-10-27 | E | TBD | E | 2018-06-01 | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0024 | Gemserv | Live | No
SEC | SECMP0025 | Electricity Network Party Access to Load Switching Information | This proposal seeks to enable Electricity Network Parties to have access to information from the Smart Metering System relating to load switching carried out by Smart Meters or Smart Meter connected Devices. It also proposes that the Smart Metering System informs Electricity Network Parties when changes are made to existing load switching regimes. | Western Power Distribution | Yes | No | No | No | Yes | C | 2016-11-18 | E | TBD | E | 2018-06-01 | Modification Proposal Submitted | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0025 | Gemserv | Live | No
SEC | SECMP0026 | Changes to the Security Sub-Committee Nomination Process | This modification seeks to alter the current Security Sub-Committee's (SSC) member nomination process in three areas to: require that nominators must hold a relevant senior position within their organisation; grant the SSC authority to reject nominees if they lack relevant security expertise; and require that nominees undergo security vetting. | E.ON | Yes | No | No | No | Yes | C | 2016-12-12 | E | TBD | E | 2017-03-16 | Modification Proposal Submitted | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 3 - Self Governance | SECMP0026 | Gemserv | Live | No
SEC | SECMP0027 | Amending Service Request Forecasting | The Proposer has highlighted that forecasting the number of individual Service Requests is going to be very challenging for DCC Users, especially for top ups. This modification seeks to amend the forecasting rules. | Utilita Energy | Yes | No | No | No | Yes | C | 2016-12-16 | E | TBD | E | TBD | Modification Proposal Submitted | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0027 | Gemserv | Live | No
SEC | SECMP0028 | Prioritising Service Requests | This Modification Proposal seeks to introduce Service Request prioritisation with the rationale that some Service Requests are fundamental to the customer experience of the market and should take priority over other, non-critical Service Requests. | Utilita Energy | Yes | No | No | No | Yes | C | 2016-12-07 | E | TBD | E | TBD | Modification Proposal Submitted | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0028 | Gemserv | Live | No
SEC | SECMP0029 | Business Continuity and Disaster Recovery Testing Amendments | This Modification Proposal seeks to amend the DCC obligations on the Business Continuity and Disaster Recovery to ensure that Service Requests are processed as soon as possible to reduce customer impacts | Utilita Energy | Yes | No | No | No | Yes | C | 2016-12-19 | E | TBD | E | TBD | Modification Proposal Submitted | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 3 - Self Governance | SECMP0029 | Gemserv | Live
SEC | SECMP0030 | Demand Management of DCC Systems | This modification proposes to implement an enduring solution that protects the DCC System when aggregate demand cannot be satisfied simultaneously. This modification proposes establishing appropriate rules to enable the prioritisation of Service Requests and Service Responses across the DCC User Interface and the prioritisation by the DCC of Commands to be sent to Communications Hub Functions and Certificate Signing Request volumes in an equitable, fair and transparent way. Rules by which DCC will actively control Device Alert volumes should also be considered for inclusion in this modification process. | Smart DCC Ltd | Yes | No | No | No | Yes | C | 2017-01-04 | E | TBD | E | TBD | Refinement | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0030 | Gemserv | Live | No
SEC | SECMP0031 | Adding UTRN Functionality to SMETS | SMETS1 Unique Transaction Reference Numbers (UTRNs) can be used for a number of functions beyond adding credit. This Mod seeks to increase the functionality associated to a UTRN in SMETS2 in order to prevent a retrograde step when moving from SMETS1 to SMETS2. | Utilita Energy | Yes | No | No | No | Yes | C | 2017-02-20 | E | TBD | E | TBD | Initial Modification Report | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0031 | Gemserv | Live | No
SEC | SECMP0032 | Prioritising Prepayment Customers in No WAN Situations | This Mod seeks to introduce a requirement on the DCC to prioritise achieving SM WAN coverage in areas where customers signed up to prepayment contracts with their suppliers, where a Communications Hub is installed at a premises but does not connect to SM WAN, and the SM WAN Coverage Database indicated (at any time during the 30 days prior to the date of installation) that the SM WAN is (or would be) available in the area in which the premises is located on the installation date. | Utilita Energy | Yes | No | No | No | Yes | C | 2017-02-20 | E | TBD | E | TBD | Initial Modification Report | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 2 - Authority Determined | SECMP0032 | Gemserv | Live | No
SEC | SECMP0033 | Update to CH Handover Support Materials | This modification seeks to update the Consignment labelling and information table and the SM WAN Coverage Information section in Appendix H ‘CH Handover Support Materials’. This update is to align the ‘CH Handover Support Materials’ document with the implementation of the DCC Solution. | Smart DCC Ltd | Yes | No | No | No | Yes | C | 2017-02-22 | E | TBD | E | TBD | Initial Modification Report | On Track | All estimated implementation dates are the earliest possible implementation dates. These are subject to change. | - | No | Path 3 - Self Governance | SECMP0033 | Gemserv | Live | No
SPAA | CP 14/268 | Introduction of The Gas Theft Incentive Scheme | The intent of this change is to introduce into the SPAA a Gas Theft Incentive Scheme, in line with the principles set out by Ofgem within their decision document entitled ‘Tackling gas theft: the way forward’ published on 26th March 2012. | British Gas | No | No | No | No | No | C | 2014-03-01 | C | n/a | E | TBD | Awaiting implementation | On Track | Confirmation of go-live date required Mod will be implemented 5 WDs after Authority Decision, with the Scheme Year to start on the first day of the calendar month two months after Authority Decision. | Gas Theft | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 15/305 | Additional MDD Rejection Codes for UKLP | Proposal to add additional rejection codes to accommodate requirements identified by Shippers through the Nexus requirements process and consequential changes to UK Link Systems | WWU | No | No | No | No | No | C | 2015-05-01 | C | 2016-07-21 | E | TBD | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus | No | Mod | SPAA | ElectraLink | Live | Yes
SPAA | CP 15/306 | Inclusion of new definition – Project Nexus Implementation Date | Inclusion of definition so change proposal delivery can be linked and aligned to the delivery of Project Nexus | E.ON | No | No | No | No | No | C | 2016-06-01 | C | 2016-07-21 | E | TBD | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus | No | Mod | SPAA | ElectraLink | Live | Yes
SPAA | CP 15/307 | Amendment to the Implementation date of CP14/284 | Amendments of the implementation date for CP14/284 due to its dependency on the delivery of Project Nexus | E.ON | No | No | No | No | No | C | 2015-06-01 | C | 2016-07-21 | E | TBD | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus | No | Mod | SPAA | ElectraLink | Live | Yes
SPAA | CP 15/308 | Removal of Schedule 7 (Cooperative Objections) as a result of Nexus | This change seeks to make Schedule 7 removed from SPAA Documents. As a result of Nexus, LSPs will now be able to use Cancellation Confirmation option instead of Cooperative Objections. The use of this process will prevent ETs being raised | EDF | No | No | No | No | No | C | 2016-03-01 | C | 2016-04-01 | E | TBD | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus | No | Mod | SPAA | ElectraLink | Live | Yes
SPAA | CP 15/317 | Amendment to Schedule 23 to reflect Changes at Project Nexus Implementation | At Project Nexus Implementation the Data Enquiry Service will change as a result of: • additional services being provided and consequently different data being available, • Single Service Provision will enhance data access to provide users of the Data Enquiry Service with greater visibility of Small Transporter Supply Meter Point data. This change documents the changes to Schedule 23 as a result | NGN | No | No | No | No | No | C | 2015-11-01 | C | 2015-12-01 | E | TBD | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus | No | Mod | SPAA | ElectraLink | Live | Yes
SPAA | CP 16/327 | Revision and Implementation of the Gas Theft Detection Incentive Scheme | Support the introduction of a Gas Theft Detection Incentive Scheme by seeking to implement further amendments to the legal drafting for previously Authority approved CP14/268 | British Gas | No | No | No | No | No | C | 2016-06-01 | C | 2016-07-21 | C | 2017-06-05 | Awaiting implementation | On Track | - | Gas Theft | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/329 | Introduction of Schedule 38 and a new defined term in Schedule 29 | This change has been developed by the Schedule 25 Review Group and seeks to introduce a new Schedule in order to place obligations on Suppliers to undertake prepayment assurances measure on non-smart prepayment meters as well as introducing a new defined term in Schedule 29 | Npower | No | No | No | No | No | C | 2016-05-01 | C | 2017-02-01 | C | 2017-02-24 | Awaiting implementation | On Track | - | n/a | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/334 | Introduction of Smart Prepayment Change of Supplier Exceptions Process | This change has been developed by the Smart Prepayment Issues Group (SPIG) to introduce a new Schedule, which sets out a number of Supplier obligations in relation to the smart prepayment Change of Supplier exceptions process. | E.ON | Yes | No | No | No | No | C | 2016-05-01 | C | 2016-10-20 | E | TBD | Awaiting implementation | On Track | Confirmation of authority approval 1 WD after Authority Consent received | n/a | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/336 | Amendments to the SPAA change process v1.1 | This change proposes that the SPAA Change Board is responsible for agreeing the next steps for a Change Proposal or Draft Change Proposal | Wales and West Utilities | No | No | No | No | No | C | 2016-06-01 | C | 2016-10-20 | C | 2017-02-24 | Awaiting implementation | On Track | - | n/a | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/338 | Process and Costs of Providing Additional Hunter Facilities | This change seeks to introduce a process for Suppliers who wish to procure additional Hunter facilities from the TRAS Service Provider and to make those costs transparent to the Supplier community. This change also seeks to introduce specific measures for additional Hunter costs for these Services to be charged to the individual Supplier. | Npower | No | No | No | No | No | C | 2016-05-01 | C | 2016-09-15 | C | 2017-02-24 | Awaiting implementation | On Track | - | TRAS | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/339 | TRAS Amendment of Schedule 34 Appendix 2 | Currently the Programming Manual contained within Schedule 34 Appendix is an outdated version. This CP seeks to update the information with a data items table and reference utilising the most current version of the Service Providers Programming Manuals. | E.ON | No | No | No | No | Yes | C | 2016-05-01 | C | 2016-09-15 | E | TBD | Issued | On Track | Confirmation of authority approval 5WDs after decision to align with DCUSA | TRAS | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/343 | Housekeeping amendment to redundant Schedules | Seeks to amend the covering page of Schedule 7 to state that the schedule is no longer in use. | EDF | No | No | No | No | Yes | C | 2016-06-01 | C | 2016-07-21 | C | TBD | Awaiting implementation | On Track | Confirmation of go-live date required Project Nexus Implementation Date | Nexus | No | Mod | SPAA | ElectraLink | Live | Yes
SPAA | CP 16/344 | Requirement on Gas Transporters to Provide Data to the ETTOS Service Provider | To deliver the ETTOS service, the ETTOS Service Provider requires data from Gas Transporters. This CP places a requirement on Gas Transporters to provide the required data. | E.ON | No | No | No | No | No | C | 2016-06-01 | C | 2016-07-21 | E | TBD | Awaiting implementation | On Track | Confirmation of authority approval 5 Working Days following Authority approval (aligned with the DCUSA change) | TRAS | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/346 | Inclusion of User Allocation Rules for ETTOS Secure Email System (Draft) | ETTOS tip-offs are disseminated to Parties by means of a secure email service. This CP seeks defines rules for allocation of user accounts for the secure email service. | Npower | No | No | No | No | No | C | 2016-07-01 | C | 2016-12-15 | E | 2017-02-24 | Issued in Change Pack | On Track | - | TRAS | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/346 | Inclusion of User Allocation Rules for ETTOS Secure Email System | This seeks to define rules for allocation of user accounts for the secure email service define rules for allocation of user accounts for the secure email service | Npower | No | No | No | No | No | C | 2016-11-01 | C | 2016-12-15 | C | 2017-02-24 | Awaiting implementation | On Track | - | TRAS | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/347 | Amendments to Pre-Payment tariff pages (Draft) | This change proposal seeks to bring in amendments to the use of tariff pages, following CMA remedies required. | Npower | No | No | No | No | No | C | 2016-07-01 | C | n/a | E | TBD | Awaiting implementation | On Track | Confirmation of authority approval 5WD after Authority Consent received | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/349 | Introduction of OAMI into SPAA EC Vires | The Ofgem Approved Meter Installers (OAMI) Scheme is currently managed and overseen by Ofgem. At the April 2017 EC meeting, it was agreed that the Scheme should be incorporated into SPAA governance, with the OAMI Scheme transitioning by April 2017, in line with the expiration of the current Scheme Co-ordinators contract. CP 16/349 will enable the SPAA EC to effectively and efficiently manage the Ofgem Approved Meter Installer Scheme when it is transitioned into SPAA governance, as directed by Ofgem | SSE | No | No | No | No | No | C | n/a | C | n/a | E | TBD | Awaiting implementation | On Track | Confirmation of authority approval 5WD after Authority Consent received | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/349 | Introduction of OAMI into SPAA EC Vires | The Ofgem Approved Meter Installers (OAMI) Scheme is currently managed and overseen by Ofgem. At the April 2017 EC meeting, it was agreed that the Scheme should be incorporated into SPAA governance, with the OAMI Scheme transitioning by April 2017, in line with the expiration of the current Scheme Co-ordinators contract. CP 16/349 will enable the SPAA EC to effectively and efficiently manage the Ofgem Approved Meter Installer Scheme when it is transitioned into SPAA governance, as directed by Ofgem | TBD | No | No | No | No | No | C | 2017-01-01 | C | TBD | E | TBD | Issued in Change Pack | On Track | Modication due to be implemented 5 Working Days after Authority Decision | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/350 | Clarification of TRAS Accession Process | Now that TRAS is in live operation, there are a number of elements that have been identified in the TRAS Schedules, specifically within clause 8 and the definitions section of the SPAA Main Body that should be clarified, amended or included for the efficient operation of TRAS. | British Gas | No | No | No | No | No | C | 2016-11-01 | C | 2016-12-15 | C | 2017-02-24 | Awaiting implementation | On Track |  | TRAS | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/352 | Changes to SLC 30 of SPAA | On 14 June 2016, Ofgem published its decision to modify the Gas Supply Licence (SLC 30. Supply Point Administration Agreement) in order to implement CGR3 Final Proposals. In summary the licence condition changes reflect changes to the Significant Code Review process | Scottish Power | No | No | No | No | No | C | 2016-08-01 | C | 2016-10-20 | C | 2017-02-24 | Awaiting implementation | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/353 | Housekeeping Amendments to the SPAA Main Body | Amendments to the SPAA Main Body by updating existing clause numbering and amending any minor typographical errors within the document following review | Scottish Power | No | No | No | No | Yes | C | 2016-08-01 | C | 2016-10-20 | C | 2017-02-24 | Awaiting implementation | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/354 | Mandate that all Suppliers shall use the DTN for the exchange of RET Flows | This CP has been raised with the intent to make the use of the Data Transfer Network (DTN) mandatory for the exchange for respectively the RET Flow | Scottish Power | No | No | No | No | No | C | 2016-09-01 | C | 2016-10-20 | C | 2017-06-05 | Awaiting implementation | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/355 | Mandate that all Suppliers shall use the DTN for the exchange of SAR Flows | This CP has been raised with the intent to make the use of the Data Transfer Network (DTN) mandatory for the exchange for respectively the SAR Flow | Scottish Power | No | No | No | No | No | C | 2016-09-01 | C | 2016-10-20 | C | 2017-06-05 | Awaiting implementation | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/360 | Schedule 33, Appendix 1 SLC References | The intent of this change is to add Supply Licence Reference (SLCs) 12.A to Schedule 33, Appendix 1 of the SPAA. | British Gas | No | No | No | No | Yes | C | 2016-11-01 | C | 2016-12-15 | C | 2017-02-24 | Deferred | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/363 | Adding Meter Serial Number (MSN) to the Supplier Agreed Read (SAR) flow. | To add MSN to SAR | Utilita | No | No | No | No | No | C | 2016-11-01 | C | 2016-12-15 | C | 2017-06-05 | Awaiting implementation | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/364 | Amendment to Actual Reading Definition | The definition of Actual Reading in SPAA Schedule 27 – Technical Glossary contains capitalised defining for an Automated Meter Reading which is not defined anywhere within the SPAA. This proposal seeks to update this definition to remove incorrect defining. |  | No | No | No | No | Yes | C | 2016-11-01 | C | 2016-12-15 | C | 2017-02-24 | Awaiting implementation | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/365 | Update to MDD A0163- Payment Method Code for smart meter models | This CP seeks to introduce consistent approach to the way ‘A0163’ Payment Method Code field is populated on live MDD for smart meter models. | EDF Energy | No | No | No | No | No | C | 2016-11-01 | C | 2016-12-15 | C | 2017-01-02 | Awaiting implementation | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 16/370A | Alternate: Refining the Needs Codes information | To update the Priority Services Register process between gas market participants to better facilitate Gas licence conditions and where appropriate align with electricity market processes. | SSE | No | No | No | No | No | C | 2017-01-01 | C | 2017-02-01 |  | 2017-06-30 | Issued in Change Pack | On Track |  |  | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/371 | To reference ‘MAP 24’ within Schedule 38 | This CP seeks to amend a reference within Schedule 38. | Gas Plus Supply Limited | No | No | No | No | No | C | 2017-01-01 | C | 2017-02-01 | C | 2017-06-30 | Issued in Change Pack | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/372 | Implementation of the Approved Meter Installer Governance | To implement the Approved Meter Installer governance arrangements as a new SPAA Schedule, as directed by Ofgem. | ESPipelines | No | No | No | No | No | C | 2017-01-01 | C | 2017-02-01 | C | 2017-04-01 | Issued in Change Pack | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/373 | Reordering Schedule 32 | To reorder SPAA Schedule 32 such that it follows in a logical order, as directed by the SPAA EC. | E.ON | No | No | No | No | No | C | 2017-01-01 | C | 2017-02-01 | C | 2017-06-30 | Issued in Change Pack | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/374 | Introducing a funding mechanism into Schedule 32 | To introduce a funding mechanism into SPAA Schedule 32. | Npower | No | No | No | No | No | C | 2017-01-01 | C | 2017-02-01 | C | 2017-09-01 | Issued in Change Pack | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/375 | Removal of reference to commercial disputes from Schedule 32 | To remove references to commercial disputes from SPAA Schedule 32. | British Gas | No | No | No | No | No | C | 2017-01-01 | C | 2017-02-01 | C | 2017-06-30 | Issued in Change Pack | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/376 | Xoserve funding and Governance Impacts | CP 17/376 seeks to set out the consequential changes which are required to the SPAA in light of the forthcoming implementation of UNC modification 0565 | WWU | No | No | No | No | No | C | 2017-01-01 | C | 2017-02-01 | C | 2017-04-01 | Withdrawn | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/377 | Amendments to Prepayment Tariff Pages | To update SPAA Schedule 25 in line with the CMA remedies regarding prepayment Tariff Pages, which will also include two new definitions within the Technical Glossary (Schedule 29). This Change Supersedes CP 16/347 to take into account the additional CMA revisions made. | Npower | No | No | No | No | No | C | 2017-01-01 | C | 2017-02-01 | C | 2017-04-01 | Issued in Change Pack | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/378 | Amendments to Prepayment Tariff Pages | To update SPAA Schedule 25 in line with the CMA remedies regarding prepayment Tariff Pages, which will also include two new definitions within the Technical Glossary (Schedule 29). This Change Supersedes CP 16/347 to take into account the additional CMA revisions made. | Npower | No | No | No | No | No | C | 2017-01-01 | C | 2017-02-01 | E | TBD | Issued in Change Pack | On Track | Modication due to be implemented 5 Working Days after Authority Decision | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/379 | Introduction of an Unidentified Funds Process in Schedule 25 | This change seeks to introduce a process to allocate the monies associated with unidentified prepayment transactions within SPAA Schedule 25. | British Gas | No | No | No | No | No | C | 2017-02-16 | C | 2017-03-14 | E | 2017-06-30 | Issued in Change Pack | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/380 | Amendments to Schedule 32 in relation to the Provision of Services Regulations | This change seeks to updated the initial assessment process for Meter Asset Managers (MAMs) within Schedule 32 such that it is compliant with the Provision of Services Regulations 2009. | ESP | No | No | No | No | No | C | 2017-02-17 | C | 2017-03-14 | E | 2017-07-01 | Issued in Change Pack | On Track | - | - | No | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/381 | Introducing Failed Status in the Asset Status Code (A0037) for In Home Display. | This change seeks to introduce a new status of ‘Failed’ in the IHD Installed Status for Supplier to capture when it has not been possible to provide an IHD to the customer as part of the smart metering installation visit. | EDF | No | No | No | No | No | C | 2017-02-18 | C | 2017-03-14 | E | 2017-11-03 | Issued in Change Pack | On Track | - | - | MRA | Mod | SPAA | ElectraLink | Live | No
SPAA | CP 17/382 | Amendments to Prepayment Tariff Pages – Updated following legal review | The purpose of this CP is to update the SPAA in line with the CMA remedies regarding prepayment Tariff Pages. The drafting associated to this change has been legally reviewed to ensure that it is sufficiently robust, and accurately transposes the CMA obligations into the SPAA. This change seeks to supersede CP 16/347, which has been previously sent back by the Authority; this change also seeks to supersede CP 17/378, which was raised in response to Ofgem’s send back of CP 16/347, and approved at the February 2017 Change Board. Whilst reviewing CP 17/378, industry parties acknowledged that it would be opportune for the drafting of CP 17/378 to be legally reviewed. This CP seeks to implement the updated drafting following legal review. | British Gas | No | No | No | No | No | C | 2017-03-03 | C | 2017-03-15 | E | TBD | Issued in Change Pack | On Track | Urgent The proposed implementation date is 5 working days after Authority approval | CMA | No | Mod | SPAA | ElectraLink | Live | No
SQSS | GSR012 | Treatment of Interconnectors | There are significant new interconnections to external systems currently under construction and more are planned. Interconnectors can result in large changes in flows within short timescales across the transmission system. It is therefore important to understand the implications and means of managing greater interconnection and market coupling with other European nations, including the extent to which interconnector flow can be relied upon to meet demand and avoid constraining generation. | National Grid | No | No | Yes | No | Yes | C | 2010-10-05 | E | TBD | E | TBD | Assessment | At Risk | Workgroup meetings need to re-convene following 1 year hiatus. | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/SQSS/Modifications/GSR012/ | National Grid | Live | Yes
SQSS | GSR014 | Offshore Transformer Requirements | GSR014 was raised to investigate whether the current requirements for two transformers and two substation bays where offshore cables connect to the onshore transmission system is necessary or whether two transformers connected to a single bay or even a single transformer and single bay would be sufficient. | National Grid | No | No | No | No | No | C | 2012-11-19 | E | TBD | E | TBD | Assessment | At Risk | Finalising report | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/SQSS/Modifications/GSR014/ | National Grid | Live | Yes
SQSS | GSR016 | Embedded Generation Scaling | GSR016 was raised to specify how embedded generation should be treated in Chapter 4 MITS studies. The GSR009 modification to the NETS SQSS in 2011 specified certain scaling factors for various types of generation (based on fuel type) with different scaling factors under the economy and security criteria. These scaling factors are only considered for “large” power stations (i.e. generation over 100MW in England and Wales). | National Grid | No | No | No | No | Yes | C | 2013-07-22 | E | TBD | E | TBD | Assessment | On Track | - | - | CUSC | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/SQSS/Modifications/GSR016/ | National Grid | Live | Yes
SQSS | GSR017 | Treatment of Switch Faults in Operational Timescales | Under the current version of the NETS SQSS, switch faults are secured for new generation connections but only with respect to limiting the loss of power infeed to the infrequent infeed loss risk. Switch faults can potentially cause wider system issues such as instability, system splits, cascade tripping and voltage collapse depending on the substation at which they occur, the network running arrangement and the generation and demand levels at the time of the fault. GSR017 will therefore undertake a review of the current NETS SQSS and will determine the need case for securing against the above challenges in the event of switch faults in operational timescales. | National Grid | No | No | No | No | No | C | 2014-02-05 | E | TBD | E | TBD | Raised | On Track | - | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/SQSS/Modifications/GSR017/ | National Grid | Live | Yes
SQSS | GSR018 | Treatment of Sub-Synchronous Oscillations in the NETS SQSS | A number of Transmission Licensees and Transmission Users are in the process of enhancing their networks or connecting generation using Series Capacitor and / or HVDC technology. Both of these types of equipment can cause sub-synchronous oscillations (SSO) to occur by interacting with other User’s equipment in the form of sub-synchronous resonance (SSR) or sub-synchronous torsional interaction (SSTI). The Grid Code Review Panel Paper: “Suppression of Sub-Synchronous Resonance from Series Compensators” (pp13/54) proposed changes to the Grid Code to place obligations on Transmission Licensees to mitigate SSR where Series Compensation is deployed. The Grid Code Review Panel asked that these proposals be given further consideration in light of concerns raised by Transmission Licensees about how and where any SSR related obligations are expressed within the transmission frameworks. The Grid Code Review Panel also asked whether there was a need to capture SSR and SSTI within the NETS SQSS. | National Grid | No | No | No | No | Yes | C | 2014-12-04 | E | TBD | E | TBD | Raised | On Track | - | GC0077 | GC |  | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/SQSS/Modifications/GSR018/ | National Grid | Live | Yes
SQSS | GSR022 | Review of Security and Economy Planned Transfer Conditions | The workgroup considers issues and interactions that arise when applying NETS SQSS Section 4 criteria due to the availability of generation and due to generation technology. | National Grid | No | No | No | No | Yes | C | 2016-06-01 | E | TBD | E | TBD | Raised | On Track | - | - |  |  | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/SQSS/Modifications/GSR022/ | National Grid | Live | Yes
SQSS | SQSS Potential Change 1 | European TSOG -Minimum Required Inertia | Determination of Minimum Required Inertia | National Grid | No | No | No | No | No | E | 2017-10-01 | E | TBD | E | 2018-10-01 | Upcoming | On Track | - | - | TBD | Mod |  | National Grid | Upcoming | Yes
SQSS | SQSS Potential Change 2 | European TSOG Implementation -Regional Outage Coordination | European TSOG Implementation -Regional Outage Coordination | National Grid | No | No | No | No | No | E | 2018-01-01 | E | TBD | E | 2018-10-01 | Upcoming | On Track | - | - | TBD | Mod |  | National Grid | Upcoming | Yes
SQSS | SQSS Potential Change 3 | European TSOG - Requirements | TSOG requirements in relation to reserve providers and operational agreements | National Grid | No | No | No | No | No | E | 2018-01-01 | E | TBD | E | 2018-10-01 | Upcoming | On Track | - | - | TBD | Mod |  | National Grid | Upcoming | Yes
STC | CM059 | Changes to Section C and H following OFGEM Response to Adjudication Request | Correct the Section C Paragraph 5.9.5 for refer to Section H and to update Section H to allow a referable clause to the Authority. | National Grid | No | No | No | No | No | C | 2016-09-21 | E | TBD | E | TBD | Assessment | On Track | - | - | No | Mod | http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/STC/Modifications/CM059/ | National Grid | Live | Yes
STC | STC Potential Change 1 | European TSOG - Multi TSO Training Cooperation | European TSOG - Multi TSO Training Cooperation | National Grid | No | No | Yes | No | Yes | E | 2017-10-01 | E | TBD | C | 2018-10-01 | Upcoming | On Track | - | EU Regulation/Law | No | Mod |  | National Grid | Upcoming | Yes
STC | STC Potential Change 2 | European TSOG Implementation - Data Exchange | European TSOG Implementation - Data Exchange | National Grid | No | No | Yes | No | Yes | E | 2017-10-01 | E | TBD | C | 2018-10-01 | Upcoming | On Track | - | EU Regulation/Law | Yes | Mod |  | National Grid | Upcoming | Yes
STC | STC Potential Change 3 | European TSOG Implementation -Regional Outage Coordination | European TSOG Implementation -Regional Outage Coordination and Security Anaysis | National Grid | No | No | Yes | No | Yes | E | 2018-01-01 | E | TBD | C | 2018-12-01 | Upcoming | On Track | This mod is set to be raised in Q1 2018 | EU Regulation/Law | Yes | Mod |  | National Grid | Upcoming | Yes
UNC | 0565 | Central Data Service Provider: General framework and obligations | This modification identifies the framework and principal obligations and terms under which the Central Data Service Provider (CDSP) will operate under the UNC. It also provides for the creation of a Data Services Contract (DSC) as a UNC ‘code referenced document’. | National Grid Distribution | No | No | No | No | Yes | C | 2015-11-05 | E | 2017-01-31 | E | 2017-04-01 | Ofgem Decision | On Track | No clear recommendation from the UNC Panel - awaiting Ofgem decision on which Alternate should be implemented | Licence - FGO | iGT UNC | Mod | http://www.gasgovernance.co.uk/0565 | Joint Office | LIVE | Yes
UNC | 0565A | Central Data Service Provider: General framework and obligations | This Alternate Modification Proposal is identical to UNC 0565 except for the representation structure in the Data Services Contract structure | E.ON UK | No | No | No | No | Yes | C | 2016-10-10 | E | 2017-01-31 | E | 2017-04-01 | Ofgem Decision | On Track | No clear recommendation from the UNC Panel - awaiting Ofgem decision on which Alternate should be implemented | Licence - FGO | iGT UNC | Mod | http://www.gasgovernance.co.uk/0565 | Joint Office | LIVE | Yes
UNC | 0565B | Central Data Service Provider: General framework and obligations | This Alternate Modification Proposal is identical to UNC 0565 except for the representation structure in the Data Services Contract structure. In short, it adopts the solution for Shipper category idenitifed within 0565A but contains a variation on the proposed arrangements for Transporter voting in 0565. | Scotia Gas Networks | No | No | No | No | Yes | C | 2016-10-26 | E | 2017-01-31 | E | 2017-04-01 | Ofgem Decision | On Track | No clear recommendation from the UNC Panel - awaiting Ofgem decision on which Alternate should be implemented | Licence - FGO | iGT UNC | Mod | http://www.gasgovernance.co.uk/0565 | Joint Office | LIVE | Yes
UNC | 0570 | Obligation on Shippers to provide at least one valid meter reading per meter point into settlement once per annum | This modification proposes to create a condition in the UNC to correspond with the requirement on Suppliers under the Supply Licence (SLC 21B.4) to take a meter reading at least once every year for billing purposes. In the case of the UNC this would be for use within gas industry settlement | Scottish Power | No | No | No | No | Yes | C | 2015-12-03 | E | 2017-05-30 | E | 2017-08-01 | Assessment | On Track | Workgroup assessment timetable has been extended | CMA Order | No | Mod | http://www.gasgovernance.co.uk/0570 | Joint Office | LIVE | Yes
UNC | 0571 | Application of Ratchets Charges to Class 1 Supply Points Only | Recognising the introduction of 4 new classes of Supply Points under Project Nexus and the wider availability of daily read sites with lower AQs, this modification limits the application of Ratchets Charges to Class 1 Supply Points whose operation may be material to the safe operation of the Network. | Gazprom | No | No | No | No | Yes | C | 2015-12-24 | E | 2017-05-30 | E | 2017-08-01 | Assessment | On Track | Workgroup assessment timetable has been extended | - | No | Mod | http://www.gasgovernance.co.uk/0571 | Joint Office | LIVE | Yes
UNC | 0571A | Application of Ratchet Charges to Class 1 Supply Points and Class 2 with an AQ above 73,200kWhs | Recognising the introduction of 4 new classes of Supply Points under Project Nexus and the wider availability of daily read sites with lower AQs, this modification limits the application of Ratchets Charges to Class 2 Supply Points with an AQ above 73,200 kWhs. | E.ON UK | No | No | No | No | Yes | C | 2016-05-05 | E | 2017-05-30 | E | 2017-08-01 | Assessment | On Track | Workgroup assessment timetable has been extended | - | No | Mod | http://www.gasgovernance.co.uk/0571 | Joint Office | LIVE | Yes
UNC | 0587 | Seasonal Energy Balancing Credit Cover | This modification proposes to amend the Energy Balancing Credit Rules so that a User’s credit cover, which is currently set based on the maximum requirement in the past 12 months, is only set based on months in the same season as the current one | Opus Energy | No | No | No | No | Yes | C | 2016-06-06 | C | 2016-11-24 | C | 2017-05-01 | Awaiting Implementation | On Track | Minor changes required - and elective as required | - | No | Mod | http://www.gasgovernance.co.uk/0587 | Joint Office | Closed | No
UNC | 0593 | Provision of access to data for Price Comparison Websites and Third Party Intermediaries | This modification seeks to create provisions in the UNC to permit the release of data to Price Comparison Websites (PCWs) and Third Party Intermediaries (TPIs) to satisfy the CMA Energy Market Investigation requirements. The release of data would be subject to contractual agreement with Transporters that would include validations and be pursuant to data protection principles. It is believed that by providing data directly to such non-Code parties the service provided will improve, leading to more switching with consequential benefits to the competitive marketplace. | Northern Gas Networks | No | No | No | No | Yes | C | 2016-08-08 | E | 2017-03-31 | E | 2017-04-01 | Assessment | On Track | - | - | No | Mod | http://www.gasgovernance.co.uk/0593 | Joint Office | LIVE | Yes
UNC | 0594R | Meter Reading Submission for Advanced & Smart Metering | The rollout of advanced and smart metering in the GB gas market provides an opportunity for more granular consumption data to be provided into central industry systems at marginal cost, which should drive more accurate cost allocation. Currently there are no requirements/obligations for Shippers to provide more frequent meter readings should a Smart/Advanced meter be installed. This Request is to consider options for the provision of data on a more frequent basis to support the Settlement process. It is believed that any proposals should apply to Class 1, 2 and 3 Supply Points; however this would be tested as part of the review. | Gazprom | Yes | No | No | No | No | C | 2016-09-02 |  | n/a |  | n/a | Request | On Track | This is a UNC Request - to review the arrangements for meter reading submission. A modification is one possible output. | None- Review | No | Request | http://www.gasgovernance.co.uk/0594 | Joint Office | LIVE | No
UNC | 0595S | Amendment to the Arrangements between National Grid NTS and GNI at the Moffat IP to Provide for Interruption of Virtual Reverse Flow | This enabling modification seeks to amend the tri-partite Agreement between National Grid, Gas Networks Ireland (GNI UK) – as the owner and operator of the Irish Interconnector - and GNI - as the Transmission System Operator in the Republic of Ireland - to reflect the existing arrangements for interruption (by GNI) of within-day Virtual Reverse Flow (VRF) capacity entitlements. | National Grid NTS | No | No | No | No | Yes | C | 2016-09-02 | C | 2016-11-17 | C | 2016-12-09 | Implemented | On Track | No action to implement since the service was already available in Ireland | - | No | Mod | http://www.gasgovernance.co.uk/0595 | Joint Office | Closed | No
UNC | 0596 | Implementing CGR3 decisions on Significant Code Reviews and self-governance | This modification seeks to implement Ofgem’s decisions in respect of self-governance and SCR process resulting from the Code Governance Review 3 consultation. | Wales & West Utilities | No | No | No | No | Yes | C | 2016-10-07 | E | 2017-01-31 | E | 2017-02-01 | Ofgem Decision | On Track | UNC Panel recommended implementation - awaiting Ofgem decision | CGR3 | No | Mod | http://www.gasgovernance.co.uk/0596 | Joint Office | LIVE | Yes
UNC | 0597 | Rules for the release of incremental capacity at Interconnection Points | This modification seeks to provide a process for acquiring incremental capacity at Interconnection Points that is compliant with the amended EU CAM Code. | National Grid NTS | No | No | Yes | No | Yes | C | 2016-10-10 | E | 2017-03-31 | E | 2017-04-01 | Assessment | On Track | - | EU CAM | No | Mod | http://www.gasgovernance.co.uk/0597 | Joint Office | LIVE | Yes
UNC | 0598 | Amendments to Capacity Allocations Mechanisms to comply with EU Capacity Regulations | This modification seeks to facilitate compliance with the amended CAM Code at Interconnection Points (IP)s by introducing an amended auction calendar and changes to the treatment of capacity at Storage Exit points. | National Grid NTS | No | No | Yes | No | Yes | C | 2016-10-10 | E | 2017-03-31 | E | 2017-04-01 | Assessment | On Track | - | EU CAM | No | Mod | http://www.gasgovernance.co.uk/0598 | Joint Office | LIVE | Yes
UNC | 0599 | Amendments to Capacity Allocations Mechanisms (Interruptible) to comply with EU Capacity Regulations | This modification seeks to facilitate compliance with the amended CAM Code by changing the rules for releasing interruptible capacity at Interconnection Points (IPs). | National Grid NTS | No | No | Yes | No | Yes | C | 2016-10-10 | C | n/a | C | n/a | Withdrawn | On Track | Withdrawn | EU CAM | No | Mod | http://www.gasgovernance.co.uk/0599 | Joint Office | Closed | No
UNC | 0600S | Amend obligation for the acceptance of EPDQD revisions made after D+5 | This modification seeks to amend the requirement in UNC that no revisions can be made to the Entry Point Daily Quantity Delivered (EPDQD) after D+5. The amended text will allow revisions to be made after this date, but any revisions submitted after D+5 will be subject to a reporting obligation. | National Grid NTS | No | No | No | No | Yes | C | 2016-10-10 | E | 2017-03-16 | E | 2017-04-01 | Assessment | On Track | - | - | No | Mod | http://www.gasgovernance.co.uk/0600 | Joint Office | LIVE | Yes
UNC | 0601FT | Revision of National Grid Gas plc’s Individual Network Code to reflect the correct company name | This modification amends the Transporter name in the National Grid Gas plc Individual Network Code from ‘Transco plc’ to ‘National Grid Gas plc’. | National Grid NTS | No | No | No | No | No | C | 2016-11-01 | C | 2016-11-17 | C | 2016-12-09 | Implemented | On Track | - | - | No | Mod | http://www.gasgovernance.co.uk/0601 | Joint Office | Closed | No
UNC | 0602 | Implementation of Non Effective Days and Variant Non-Business Days for Project Nexus Implementation (Project Nexus transitional modification) | This modification identifies arrangements relating to the requirement for ‘non-effective days’ and ‘variant non-Business Days’ to enable an orderly and efficient transition from current UNC arrangements to the UNC regime identified within UNC Modifications 0432, 0434 and 0440. | National Grid Gas Distribution | No | No | No | No | Yes | C | 2016-11-07 | E | 2017-03-31 | E | 2017-04-01 | Assessment | On Track | Project Nexus Steering Group has settled on '9+3' - these mods catch up the UNC (with 0602A adding an alternative view on objections) | Nexus | iGT UNC | Mod | http://www.gasgovernance.co.uk/0602 | Joint Office | LIVE | Yes
UNC | 0602A | Implementation of Non Effective Days and Variant Non-Business Days for Project Nexus Implementation, maintaining two Supply Point Business Days (Project Nexus transitional modification) | This modification identifies arrangements relating to the requirement for ‘non-effective days’ and ‘variant non-Business Days’ to enable an orderly and efficient transition from current UNC arrangements to the UNC regime identified within UNC Modifications 0432, 0434 and 0440. | RWE npower | No | No | No | No | Yes | C | 2016-12-23 | E | 2017-03-31 | E | 2017-04-01 | Assessment | On Track | Project Nexus Steering Group has settled on '9+3' - these mods catch up the UNC (with 0602A adding an alternative view on objections) | Nexus | iGT UNC | Mod | http://www.gasgovernance.co.uk/0602 | Joint Office | LIVE | Yes
UNC | 0603S | Removal of liability for members of Performance Assurance Committee | This modification seeks to to give Performance Assurance Committee (PAC) members protection from legal action by Parties that are affected by their actions or decisions. This protection is limited to decisions made in good faith pursuant to members’ duties. Not having this protection may mean that members do not make difficult decisions and thereby limit the effectiveness of PAC in delivering performance assurance. | Wales & West Utilities | No | No | No | No | Yes | C | 2016-11-08 | C | 2016-12-15 | C | 2017-01-11 | Awaiting Implementation | On Track | Minor change - no action required | - | No | Mod | http://www.gasgovernance.co.uk/0603 | Joint Office | Closed | No
UNC | 0604S | Central Data Services Provider – Arrangements following implementation of Project Nexus | This modification identifies the measures necessary to ensure the FGO arrangements implemented under Modification 0565/A/B are effective upon implementation of Project Nexus, by aligning the services introduced by Modifications 0432, 0434 and 0440 to the new CDSP direct and agency service structure. | National Grid Gas Distribution | No | No | No | No | Yes | C | 2016-11-30 | E | 2017-04-30 | E | 2017-06-01 | Assessment | On Track | - | Licence - FGO | No | Mod | www.gasgovernance.co.uk/0604 | Joint Office | LIVE | Yes
UNC | 0605S | Amendments to TPD Section K - Additional Methods to Procure and Dispose of Operating Margins Gas | This modification seeks to enable National Grid NTS to procure and dispose of Operating Margins Gas in a more efficient and economical way | National Grid NTS | No | No | No | No | Yes | C | 2016-12-02 | E | 2017-03-31 | E | 2017-04-01 | Assessment | On Track | - | - | No | Mod | http://www.gasgovernance.co.uk/0605 | Joint Office | LIVE | Yes
UNC | 0606S | National Grid Gas plc and National Grid Gas Distribution Limited transitional invoicing arrangement post Project Nexus implementation | This modification seeks to provide for a transitional arrangement for the invoicing of certain Transportation Charges by National Grid Gas plc and National Grid Gas Distribution Limited following implementation of Project Nexus. | National Grid Gas Distribution | No | No | No | No | Yes | C | 2016-12-05 | E | 2017-03-30 | E | 2017-06-01 | Assessment | On Track | - | - | No | Mod | http://www.gasgovernance.co.uk/0606 | Joint Office | LIVE | Yes
UNC | 0607S | Amendment to Gas Quality NTS Entry Specification at the St Fergus NSMP System Entry Point | This (enabling) modification seeks to facilitate a change to the current contractual Carbon Dioxide limit at the St Fergus NSMP System Entry Point, through modification of a Network Entry Provision contained within the Network Entry Agreement (NEA) between National Grid Gas plc. and North Sea Midstream Partners Limited (NSMP) in respect of the St Fergus NSMP Sub Terminal. | National Grid Gas Distribution | No | No | No | No | No | C | 2016-12-07 | E | 2017-08-30 | E | 2017-09-01 | Assessment | On Track | - | - | No | Mod | http://www.gasgovernance.co.uk/0607 | Joint Office | LIVE | Yes
UNC | 0609 | Transitional arrangements for gas settlement and replacement of Meter Readings (Project Nexus transitional modification) | This modification identifies arrangements relating to Supply Point classification, energy settlement & reconciliation and replacement of Meter Readings to enable an orderly and efficient transition from current UNC terms to the UNC regime identified within UNC Modification 0432, ‘Project Nexus – Gas Demand Estimation, Allocation, Settlement and Reconciliation reform’ and Modification 0434, ‘Project Nexus – Retrospective Adjustment’. | National Grid Gas Distribution | No | No | No | No | No | C | 2017-01-09 | C | 2017-03-16 | E | TBD | Issued to Workgroup | On Track | - | - | none | Modification | http://www.gasgovernance.co.uk/0609 | Joint Office | LIVE | Yes
UNC | 0608S | Implementation of ‘single service provision’ arrangements for iGT connected system exit points (Project Nexus transitional modification) | This ‘transitional’ modification identifies changes to the UNC to facilitate an orderly transition from the existing arrangements governing unmetered connected Independent Gas Transporter (iGT) systems (Connected Systems Exit Points - CSEPs) to the new ‘single service provision’ UNC framework to be implemented under UNC Modification 0440 ‘Project Nexus – iGT Single Service Provision’. | National Grid Gas Distribution | No | No | No | No | No | C | 2017-01-09 | C | 2017-03-16 | E | TBD | Issued to Workgroup | On Track | - | - | iGT UNC | Self Governance Modification | http://www.gasgovernance.co.uk/0608 | Joint Office | LIVE | Yes
UNC | 0610S | Project Nexus - Miscellaneous Requirements | This modification identifies a series of miscellaneous changes to the UNC which are required under Project Nexus arrangements to be implemented under UNC Modifications 0432, 0434 and 0440. | National Grid Gas Distribution | No | No | No | No | No | C | 2017-01-11 | C | 2017-03-16 | E | TBD | Issued to Workgroup | On Track | - | - | none | Self Governance Modification | http://www.gasgovernance.co.uk/0610 | Joint Office | LIVE | Yes
UNC | 0611 | Amendments to the firm capacity payable price at Interconnection Points | This modification seeks to facilitate compliance with the EU tariff code by making amendments to the payable price at Interconnection Points (IP)s. | National Grid NTS | No | No | No | No | No | C | 2017-02-03 | C | 2017-05-18 | E | TBD | Issued to Workgroup | On Track | - | - | none | Modification | http://www.gasgovernance.co.uk/0611 | Joint Office | LIVE | Yes
UNC | 0612R | Project Management and Assurance provisions for gas industry changes | This Request seeks to consider the potential introduction of provisions to enable the UNC Modification Panel to instigate project management and assurance provisions for complex and/or widely-impacting changes. It is consequential to Ofgem’s Code Governance Phase 3 review and an intermediate step ahead of full implementation of the CMA’s Energy Market Investigation remedies for code governance. | Scotia Gas Networks | No | No | No | No | No | C | 2017-02-06 | C | 2017-09-12 | E | TBD | Issued to Workgroup | On Track | - | - | none | Request | http://www.gasgovernance.co.uk/0612 | Joint Office | LIVE | Yes
UNC | 0609A | Transitional arrangements for gas settlement and replacement of Meter Readings, retaining AQ2017 (Project Nexus transitional modification) | This Alternate modification identifies arrangements relating to Supply Point classification, energy settlement and reconciliation and replacement of Meter Readings to enable an orderly and efficient transition from current UNC terms to the UNC regime identified within UNC Modification 0432, ‘Project Nexus – Gas Demand Estimation, Allocation, Settlement and Reconciliation reform’ and Modification 0434, ‘Project Nexus – retrospective Adjustment’. In addition, it seeks to ensure that the AQ2017 process emains in place until the final decision is taken on the go-live of Project Nexus. | British Gas | No | No | No | No | No | C | 2017-02-08 | C | 2017-03-16 | E | TBD | Issued to Workgroup | On Track | - | - | none | Modification | http://www.gasgovernance.co.uk/0609 | Joint Office | LIVE | Yes
Note on P7: All estimated implementation dates are the earliest possible implementation dates. These are subject to change.