## Introduction
Cross Code European Network Codes Implementation Plan
Background
On 3 March 2011, the European Third Energy Package came into effect with the aim of developing a more harmonised European energy market. This legislation required the development of European Network Codes (ENCs), which would apply across Europe and take precedence over existing national arrangements. The introduction of the ENCs will have a far reaching impact on the GB electricity industry, with changes required to grid connections, markets and system operation.
Objective
Whilst the final ENCs are expected to enter into force in 2017, implementation activities in GB will continue for a number of years. In order for Code Administrators to be able to project manage the required changes these network codes and guidelines will introduce, this document provides the following end to end project plan.
What does the project plan do?
The project plan is designed as a tool with a filter function, to enable the user to select information and tailor it any given audience. Information can be filtered by any variation of the following categories; Code, change reference, ENC, milestones, the date the change was raised, change decision date, implementation date, state of progression (i.e. upcoming, raised, assessment, awaiting implementation etc.), and known dependencies.
Principles
Please be aware that project plan and assessment has been developed on the principle of minimal change to meet compliance, for example to avoid rewriting the newly introduced ENC requirements into the GB Codes.
Please see the summary for the network codes and impacts on the GB Codes below:
| EU Codes and Guidelines | Abbreviations | Description | Status
Connection Codes
| Requirements for Generators | RfG | Harmonise and update technical connection requirements for all types of generators from 800W upward. | Adopted
| Demand Connection Code | DCC | Connection of industrial loads and DSOs, and sets out requirements which will apply to the demand side of the power system. | Adopted
| Network Code on High-Voltage Direct Current Connections | HVDC | Rules for the use of HVDC technology included between synchronous area and embedded systems. | Adopted
Market Codes
| Forward Capacity Allocation | FCA | Couples existing European electricity forward markets to create a pan-European internal market by harmonising market rules for calculating and allocating capacity in the forward market. | Adopted
| Capacity Allocation and Congestion Management | CACM | Rules for allocating capacity in day-ahead and intra-day timeframe, calculating the levels of availability cross border, allocating and recovering costs. | Adopted
| Network Code on Electricity Balancing | EB GL | Rules for cross border exchange of reserves and balancing energy | Pending
System Operator Codes
| Transmission System Operation Guideline | TSOG | Setting minimum system security, operational planning and frequency management standards. | Pending
| Network Code on Emergency and Restoration | NC ER | Harmonisation of system defence and restoration procedures during severe events. | Pending
Need more information?
For more information regarding a specific change, please contact the responsible Code Administrator:
ELEXON |  | Balancing and Settlement Code (BSC)
Energy Networks Association |  | Distribution Code (DCode)
National Grid |  | Connection and Use of System Code (CUSC)
Grid Code (GC)
System Operator – Transmission Owner Code (STC)
What is the publication schedule?
Last Wednesday of every month |  | ELEXON circulate the spreadsheet from the previous month, for NGET and ENA to redline to highlight any updates
First Wednesday of every month |  | NGET and ENA redlines the spreadsheet to highlight any updates, and return the redlined spreadsheet to ELEXON
Second Wednesday of every month |  | ELEXON publishes the updated Forward Work Plan on the 'EU Legislation' page of the ELEXON website, and circulate the link to NGET and ENA.
Document management
Version History: ENC Implementation Plan V1.0 FINAL
This plan offers a best view as the August 2017 updates, as of 6 September 2017.

## Project Plan
Project Plan
The project plan is designed as a tool with a filter function, to enable the user to select information and tailor it towards a given audience. Please note that udpates for July 2017, are highlighted in red.
Code | Change Ref | Title | Timeline Ref | S | Raised | S | Imp Decision | S | Imp Date | Assessment Duration | Implementation Duration | Progression State | Commentary | ENC
SQSS | GSR012 | Treatment of Interconnectors | SQSS - GSR012 | C | 2010-10-05 | E | TBD | E | TBD |  |  | Assessment | Workgroup meetings need to re-convene following 1 year hiatus. This change will appear on the plan when the Workgroup reconvenes.
Milestone | CACM came into force | CACM came into force | CACM came into force | C | 2015-08-01 |  | 2015-08-02 | - | N/A | 1 |  | Confirmed |  | CACM
BSC | P329 | Changes to REMIT inside information reporting | BSC - P329 | C | 2015-11-25 | C | 2016-04-19 | C | 2017-06-29 | 146 | 436 | Implemented | P329 aligned the BSC and BMRS with the Regulation on Wholesale Energy Markets Integrity and Transparency (REMIT) common schemas for inside information web feeds, required by the Agency for the Cooperation of Energy Regulators (ACER). To achieve this, the REMIT inside information data submitted by participants and reported by the BMRS will need to cover the output requirements of ACER. In addition to the ACER requirements, P329 enables the submission of outage profile information to BMRS. BSC Parties will be ultimately responsible for both accuracy and timeliness of their REMIT messages. | REMIT
GC | GC0091 | Application of the the Demand Connection Code - Implementation of European Network Code | GC - GC0091 | C | 2016-03-01 | E | TBD | E | TBD | 1 |  | Raised | This modification was originally set up as an issue Group. This has been requested to be withdrawn at the August Grid Code panel but cannot be formally withdrawn until GC0104 equivalent is raised on the D-Code on 7th September. | DCC
BSC | P342 | Change to Gate Closure for Energy Contract Volume Notifications | BSC - P342 | C | 2016-05-25 | E | 2016-12-08 | C | 2017-11-02 | 197 | 329 | Awaiting Implementation | P342 will introduce a new deadline for the purpose of submitting Energy Contract Volume Notification (ECVNs) and Metered Volume Reallocation Notifications (MVRNs) for each Settlement Period. This new contract notification deadline would be decoupled from Gate Closure, and would be set 60 minutes after the start of the relevant Settlement Period. This Modification may be of interest to future ENC Modifications | -
GC | GC0095 | GB implementation workgroup for Transmission System Operation Guideline (TSOG) European Network Code | GC - GC0095 | C | 2016-05-27 | E | TBD | E | TBD | 1 |  | Raised | This modification was set up as an issue group. This will be withdrawn and new modifications raised. | TSOG
BSC | P344 | Project TERRE implementation into GB market arrangements | BSC - P344 | C | 2016-06-01 | C | 2017-09-21 | E | 2018-09-01 | 477 | 345 | Assessment | Project TERRE is currently set to go-live in ~Feb to April 2019.. | EB GL
GC | GC0097 | European Energy Balancing Guidelines - Replacement Reserves - TERRE | GC - GC0097 | C | 2016-11-16 | E | TBD | E | 2019-07-01 | 957 |  | Raised | This modification maybe required to address changes associated with project TERRE. Deadline for EIF is fixed. This mod is set to be implemented Q3 2019. | EB GL
Dcode | DCRP1701 | Entry into Force of the EU Network Code “Transmission System Operational Guideline | Dcode - DCRP1701 | E | 2016-12-08 | E | 2017-04-28 | E | 2017-05-01 | 141 | 3 | Implemented | The GB Distribution Code requires two minor modifications to DOC5 and DOC7 to ensure it is compliant with the EU Network Code “Transmission System Operation Guidelines” (TSOG). The TSOG is expected to enter into force in early summer 2017 and some parts of it are effective immediately. On the 28/04/2017 the Authority published its decision and approve the modification. The modification was implemented on 01/05/2017. | TSOG
CUSC | CMP279 | Housekeeping modification to amend typographical errors in the CMP272 legal text | CUSC - CMP279 | E | 2017-04-19 | C | 2017-04-28 | E | 2017-05-31 | 9 | 33 | Implemented | This modification was implemented in the CUSC on the 31 May 2017
GC | GC0098 | Using GB Grid Code data to construct the EU Common Grid Model in accordance with Regulation (EU) 2015/1222 (CACM) and Regulation (EU) 2016/1719 (FCA). | GC - GC0098 | E | 2017-05-30 | E | 2017-08-02 | E | 2017-08-23 | 64 | 21 | Raised | This modification may be required to address the requirements of the Common Grid Model. Deadline for EIF is fixed. Compliance for CGM is Jan 2018 - and TBC based on methodologies | CACM/FCA
GC | GC0100 | European RfG Banding and RfG/HVDC requirements | GC - GC0100 | C | 2017-05-30 | E | TBD | E | 2018-04-01 | 306 |  | Raised | This mod is set to be implemented in Q2 2018. | RfG/HV DC
GC | GC101 | RfG and HVDC Voltage and Frequency Response requirements | GC - GC101 | C | 2017-05-30 | E | TBD | E | 2018-01-01 | 216 |  | Raised | Deadline for EIF is fixed. This mod is set to be implemented in Q1 2018. | RfG/HVDC
GC | GC0099 | Establishing a common approach to interconnector scheduling consistent with the single intraday market coupling processes set out within Regulation (EU) 2015/1222 (CACM) | GC - GC0099 | E | 2017-05-30 | E | 2017-06-21 | E | 2017-07-19 | 22 | 28 | Raised | Deadline for EIF is provisionally Q1 2019 | CACM
BSC | P356 | Time of Interconnector Data Submission | BSC - P356 | E | 2017-06-01 | E | 2018-03-01 | E | 2018-06-01 | 273 | 92 | Upcoming | P356 was raised by National Grid on 3 July 2017. The Modification will align the BSC with Grid Code Modification GC0099, which seeks to introduce the interconnector scheduled transfer process to the Grid Code. This is in order to establish common, cross-code provisions which are compatible with both the EU single intraday market coupling processes, and GB and EU balancing processes. This Modification was previously "BSC Potential Change 1" | CACM
Dcode | GC100 | To Implement within the Dcode the Frequency Response requirements contained within the EU Network Code - Requirements for Generators | Dcode - Dcode Potential Change 5 | E | 2017-06-08 | E | TBD | E | TBD | 1 |  | Raised | This modification will cater for the application of voltage / reactive power capability requirements to Power Generating Modules. | RFG
Dcode | GC101 | To Implement within the Dcode the Reactive Power and Voltage Control requirements contained within the EU Network Code - Requirements for Generators | Dcode - Dcode Potential Change 6 | E | 2017-06-08 | E | TBD | E | TBD | 1 |  | Raised | This modification will cater for the application of voltage / reactive power capability requirements to Power Generating Modules which are of Type B or above within the Dcode. | RFG
Dcode | GC100 | To Implement within the Dcode the Fault Ride Through requirements contained within the EU Network Code - Requirements for Generators | Dcode - GC100 | E | 2017-06-08 | E | TBD | E | TBD | 1 |  | Raised | This modification will cater for the application of voltage / reactive power capability requirements to Power Generating Modules which are of Type B or above within the Dcode. This change will appear on the plan when a raise date is known. | RFG
GC | Grid Code Potential Change 2 | European Energy Balancing Guidelines - General Compliance | GC - Grid Code Potential Change 2 | E | 2017-06-21 | E | TBD | E | 2018-07-01 | 375 |  | Upcoming | This modification maybe required to address general compliance requirements of the EB GL. The mod if currently set to be raised in Q1 2020. Deadline for EIF is fixed. The mod if set to be implemented in Q3 2021. | EB GL
GC | GC0102 | RfG and HVDC Compliance and System Management | GC - GC0102 | E | 2017-06-21 | E | TBD | E | 2018-01-01 | 194 |  | Raised | Deadline for EIF is fixed. This mod is set to be implemented in Q1 2018. | RfG/HVDC
Dcode | GC101 | To Implement within the Dcode the Fast Fault Current Injection requirements contained within the EU Network Code - Requirements for Generators | Dcode - Dcode Potential Change 3 | E | 2017-06-30 | E | TBD | E | TBD | 1 |  | Raised | This modification will cater for the application of Fast Fault Current Injection requirements to Power Generating Modules. | RfG
GC | Grid Code Potential Change 4 | European Emergency & Restoration Code - System Defence & Restoration Plan | GC - Grid Code Potential Change 4 | E | 2017-07-01 | E | TBD | E | 2018-07-01 | 365 |  | Upcoming | This mod is set to be raised in Q2 2017. This mod is set to be implemente din Q3 2018. | NC ER
GC | Grid Code Potential Change 13 | Market Suspension | GC - Grid Code Potential Change 13 | E | 2017-07-01 | E | TBD | E | 2018-10-01 | 457 |  | Upcoming | This mod is set to be raised in Q3 2017. Deadline for EIF is provisionally Q3 2018 | NC ER
GC | GC0103 | The introduction of harmonised Applicable Electrical Standards in GB to ensure compliance with the EU Connection Codes | GC - 103 | C | 2017-07-27 | E | TBD | E | TBD | 1 |  | Raised | This modification proposal is intended to harmonise technical standards across GB and where applicable would also align these with the ENCs
GC | GC104 | DCC Technical & Demand Side Response | GC - 104 | E | 2017-08-16 | E | TBD | E | 2018-09-01 | 381 |  | Raised | This mod is the last of the Grid Code mods to implement EU Connection Codes into GB. Address the final technical requirements of DCC not covered in GC0100 and GC102. Deadline for EIF is fixed. This mod is set to be implemented in Q3 2018. | DCC
GC | Grid Code Potential Change 14 | EB GL General Compliance | GC - Grid Code Potential Change 14 | E | 2017-09-01 | E | TBD | E | TBD | 1 |  | Upcoming |  | EB GL
GC | Grid Code Potential Change 15 | Manual Frequency Restoration Reserves | GC - Grid Code Potential Change 15 | E | 2017-09-01 | E | TBD | E | TBD | 1 |  | Upcoming |  | EB GL
GC | Grid Code Potential Change 16 | Regional Outage Co-ordination and Security Analysis | GC - Grid Code Potential Change 16 | E | 2017-09-01 | E | TBD | E | TBD | 1 |  | Upcoming
GC | Grid Code Potential Change 17 | TSOG Requirements in Relation to Reserve Providers and Operational Agreements | GC - Grid Code Potential Change 17 | E | 2017-09-01 | E | TBD | E | TBD | 1 |  | Upcoming |  | TSOG
GC | Grid Code Potential Change 18 | System Defence and Restoration Plans | GC - Grid Code Potential Change 18 | E | 2017-09-01 | E | TBD | E | TBD | 1 |  | Upcoming |  | NC ER
GC | Grid Code Potential Change 19 | Market Suspension | GC - Grid Code Potential Change 19 | E | 2017-09-01 | E | TBD | E | TBD | 1 |  | Upcoming |  | NC ER
Milestone | TSOG entry into force | TSOG entry into force | TSOG entry into force | E | 2017-09-01 | E | 2017-09-02 | E | N/A | 1 |  | Assumed |  | TSOG
Dcode | GC104 | Implementation of the requirements of the European Network Code - Demand Connection | Dcode - GC104 | E | 2017-09-07 | E | TBD | E | TBD | 1 |  | Raised | This modification will cater for the introduction of the new ER G99 which will replace ER G59 for all new geneartaion connections from May 2019. This change will appear on the plan when a raise date is known. | DCC
Milestone | NC ER comes into force | NC ER comes into force | NC ER comes into force | E | 2017-10-01 | E | 2017-10-02 | - | N/A | 1 |  | Assumed | - | NC ER
CUSC | CUSC Potential Change 1 | European Energy Balancing Guidelines - Replacement Reserves | CUSC - CUSC Potential Change 1 | E | 2017-10-01 | E | TBD | E | 2018-10-01 | 365 |  | Upcoming | This mod is set to be raised in Q4 2017. This mod is set to be implemented in Q4 2018. | EB GL
STC | STC Potential Change 1 | European TSOG - Multi TSO Training Cooperation | STC - STC Potential Change 1 | E | 2017-10-01 | E | TBD | C | 2018-10-01 | 365 |  | Upcoming | - | TSOG
STC | STC Potential Change 2 | European TSOG Implementation - Data Exchange | STC - STC Potential Change 2 | E | 2017-10-01 | E | TBD | E | 2018-10-01 | 365 |  | Upcoming | - | TSOG
BSC | BSC Potential Change 2 | Imbalance Price (without derogation) | BSC - BSC Potential Change 2 (without derogation) | E | 2017-10-01 | E | 2018-06-01 | E | 2018-11-01 | 243 | 153 | Upcoming | It is assumed that NGET and ELEXON will apply for a derogation for Article 55. If a derogation is granted, this Modification will be included within the scope of Potential Modification 11 "Harmonised Imbalance Settlement". | EB GL
BSC | BSC Potential Change 3 | Inclusion of Imbalance Adjustments (without derogation) | BSC - BSC Potential Change 3 (without derogation) | E | 2017-10-01 | E | 2018-04-01 | E | 2018-11-01 | 182 | 214 | Upcoming | It is assumed that NGET and ELEXON will apply for a derogation forArticle 49. If a derogation is granted, this Modification will be raised on ~June 2019. | EB GL
Milestone | EB GL entry into force | EB GL entry into force | EB GL entry into force | E | 2017-12-01 | E | 2017-12-02 | - | N/A | 1 |  | Assumed | - | EB GL
Milestone | Assignment of EB GL where needed | Assignment of EB GL where needed | Assignment of EB GL where needed | E | 2017-12-01 | E | 2017-12-02 | - | N/A | 1 |  | Assumed | - | EB GL
Milestone | Application for Exemption from 15 min Settlement | Application for Exemption from 15 min Settlement | Application for Exemption from 15 min Settlement | E | 2017-12-01 | E | 2017-12-02 | - | N/A | 1 |  | Assumed | - | EB GL
Milestone | Backstop date for Derogation from Article 49 and 55 | Backstop date for Derogation from Article 49 and 55 | Backstop date for Derogation from Article 49 and 55 | E | 2017-12-01 | E | 2017-12-02 | - | N/A | 1 |  | Assumed | - | EB GL
BSC | BSC Potential Change 4 | Align BSC with the Authority's oversight obligation | BSC - BSC Potential Change 4 | E | 2017-12-01 | E | 2018-06-01 | E | 2018-11-01 | 182 | 153 | Upcoming | Assignment by BEIS/Ofgem and decisions by Ofgem on how it wishes to approach this requirement | EB GL
GC | Grid Code Potential Change 11 | European TSOG Implementation -Regional Outage Coordination | GC - Grid Code Potential Change 11 | E | 2018-01-01 | E | TBD | E | 2018-10-01 | 273 |  | Upcoming | This mod is set to be raised in Q1 2018. Deadline for EIF is provisionally Q4 2018 | TSOG
GC | Grid Code Potential Change 12 | European TSOG - Requirements | GC - Grid Code Potential Change 12 | E | 2018-01-01 | E | TBD | E | 2018-10-01 | 273 |  | Upcoming | This mod is set to be raised in Q1 2018. Deadline for EIF is provisionally Q4 2018 | TSOG
STC | STC Potential Change 3 | European TSOG Implementation -Regional Outage Coordination | STC - STC Potential Change 3 | E | 2018-01-01 | E | TBD | E | 2018-12-01 | 334 |  | Upcoming | This mod is set to be raised in Q1 2018 | TSOG
Milestone | NGET suspension/restoration proposals | NGET proposals for suspension and restoration | NGET proposals for suspension and restoration | E | 2018-10-01 | E | 2018-10-02 | - | N/A | 1 |  | Assumed | - | EB GL
BSC | BSC Potential Change 7 | Project TERRE 2 | BSC - BSC Potential Change 7 | E | 2018-10-01 | E | 2019-07-01 | E | 2020-03-01 | 273 | 244 | Upcoming | This Modification will be raised to implement outstanding activities from Project TERRE | EB GL
BSC | BSC Potential Change 9 | NGET proposal on specific products | BSC - BSC Potential Change 9 | E | 2018-11-01 | E | 2019-06-01 | E | 2019-11-07 | 212 | 159 | Upcoming | If NGET make a proposal on specific products, an assessment will be required to ensure that the understanding of specific products aligns with the BSC. If understanding of specific products in the TSO proposal, differs from the BSC, this Modification will be raised to align the BSC with the proposal. | EB GL
BSC | BSC Potential Change 10 | Market Suspension and Restoration Arrangement | BSC - BSC Potential Change 10 | E | 2018-11-01 | E | 2019-08-01 | E | 2020-03-01 | 273 | 213 | Upcoming | If NGET makes proposals for rules concerning the suspension and restoration of market activities; and the rules for balancing energy and imbalance settlement during market suspension, that differ from the BSC, this Modification will be raised to align the BSC with the proposals. | NC ER
BSC | BSC Potential Change 5 | Amendments to Imbalance Price | BSC - BSC Potential Change 5 | E | 2018-12-01 | E | 2019-06-01 | E | 2020-06-01 | 182 | 366 | Upcoming | If TSO Proposal for activation purpose do not align with the BSC, this Modification will be raised to amend the imbalance price calculation | EB GL
BSC | BSC Potential Change 6 | Align BSC with the TSO's Terms and Conditions | BSC - BSC Potential Change 6 | E | 2018-12-01 | E | 2019-04-01 | E | 2019-11-07 | 121 | 220 | Upcoming | If NGET write Ts & Cs in a way that differs from the Ts & Cs of the BSC, this Modification will be raised to align the BSC with the Ts & Cs of the TSO. | EB GL
BSC | BSC Potential Change 8 | Unintended exchanges of energy | BSC - BSC Potential Change 8 | E | 2018-12-01 | E | 2019-06-01 | E | 2019-11-07 | 182 | 159 | Upcoming | Certainty on whether this Mod is required, is based on the provision of information from NGET, on what will be proposed. | EB GL
Milestone | EB GL provisions apply | EB GL provisions apply (assumed) | EB GL provisions apply (assumed) | E | 2018-12-01 | E | 2018-12-02 | - | N/A | 1 |  | Assumed | - | EB GL
BSC | BSC Potential Change 13 | Project TERRE 3 | BSC - BSC Potential Change 13 | E | 2019-01-01 | E | 2019-11-01 | E | 2020-02-27 | 304 | 118 | Upcoming | This Modification will be raised to implementation outstanding activities from P344 'Project TERRE' | EB GL
Milestone | UK leaves EU | UK leaves EU | UK leaves EU | E | 2019-03-29 | E | 2019-03-30 | - | N/A | 1 |  | Confirmed | GB Legislation for Assignment (would need to changed first, to allow us to be assigned. BEIS will need to write consultation) Derogation requires a contract with NGET, Ofem would need to issue a consultation before this is agreed.
BSC | BSC Potential Change 11 | Harmonised Imbalance Settlement (Includes Mod 2 with derogation) | BSC - BSC Potential Change 11 (Inc Mod 2 with derogation) | E | 2019-06-01 | E | 2020-01-01 | E | 2020-12-01 | 214 | 335 | Upcoming | This Modification will be raised to align the BSC with NGETs proposals to harmonise the main features of imbalance settlement. If a derogation for EB GL Article 55, the Article 55 requirements that define the scope of Potential Modification 2 'Imbalance Price' will be included within the scope of this Modification. | EB GL
BSC | BSC Potential Change 12 | Project mFRR | BSC - BSC Potential Change 12 | E | 2019-06-01 | E | 2021-01-01 | E | 2021-11-01 | 580 | 304 | Upcoming | This Modification will be raised, as an extension of the principles introduced under P344 'Project TERRE' | EB GL
BSC | BSC Potential Change 3 | Inclusion of Imbalance Adjustments (with derogation) | BSC - BSC Potential Change 3 (with derogation) | E | 2019-06-01 | E | 2020-01-01 | E | 2020-11-01 | 214 | 305 | Upcoming | It is assumed that NGET will apply for a derogation for EB GL Article 49. If a derogation is granted, this Modification will be raised in ~June 2019 | EB GL
Milestone | Backstop date for RR standard products | Backstop date for RR standard products | Backstop date for RR standard products | E | 2019-12-01 | E | 2019-12-02 | - | N/A | 1 |  | Assumed |  | EB GL
GC | Grid Code Potential Change 3 | European Energy Balancing Guidelines - Manual Frequency Restoration Reserves (mFRR) | GC - Grid Code Potential Change 3 | E | 2020-01-01 | E | TBD | E | 2021-07-01 | 547 |  | Upcoming | This modification maybe required to address mFRR requirements of the EB GL. This mod is set to be raised in Q1 2020. Deadline for EIF is fixed. This mod is set to be implemented in Q3 2021. | EB GL
GC | Grid Code Potential Change 10 | Frequency Restoration Reserves | GC - Grid Code Potential Change 10 | E | 2020-01-01 | E | TBD | E | 2021-10-01 | 639 |  | Upcoming | This mod is set to be raised in Q1 2020. Deadline for EIF is provisionally Q3 2021 | EB GL
CUSC | CUSC Potential Change 2 | European Energy Balancing Guidelines - Manual Frequency Restoration Reserves (mFRR) | CUSC - CUSC Potential Change 2 | E | 2020-07-01 | E | TBD | E | 2021-07-01 | 365 |  | Upcoming | This mod is set ot be raised Q3 2020.This mod is set to be implemented in Q3 2021 | EB GL
Milestone | The earliest decision on bidding zone change | Earliest decision on bidding zone change | Earliest decision on bidding zone change | E | 2020-07-01 | E | 2020-07-02 | - | N/A | 1 |  | Assumed | - | CACM
Milestone | Backstop date for hamonised Imbalance Settlement | Backstop date for harmonised Imbalance Settlement | Backstop date for harmonised Imbalance Settlement | E | 2020-12-01 | E | 2020-12-02 | - | N/A | 1 |  | Confirmed | - | EB GL
Milestone | Implementation date for any bidding zone change | Implementation date for any bidding zone change | Implementation date for any bidding zone change | E | 2021-07-01 | E | 2021-07-02 | - | N/A | 1 |  | Assumed | - | CACM
Milestone | Backstop date for FRR standard products | Backstop date for FRR standard products | Backstop date for FRR standard products | E | 2021-12-01 | E | 2021-10-02 | - | N/A | -60 |  | Assumed | - | EB GL
Dcode | GC100/101/102 | Implementation of the new Engineering Recommendation G98 | Dcode - GC100/101/102 | E | TBD | E | TBD | E | TBD |  |  | Upcoming | This modification will cater for the introduction of the new ER G98 which will replace ERG83 for all new geneartaion connections from May 2019. This change will appear on the plan when a raise date is known. | RFG
Dcode | GC101/101/102 | Implementation of the new Engineering Recommendation G99 | Dcode - GC101/101/102 | E | TBD | E | TBD | E | TBD |  |  | Upcoming | This modification will cater for the introduction of the new ER G99 which will replace ER G59 for all new geneartaion connections from May 2019. This change will appear on the plan when a raise date is known. | RFG
Dcode | Dcode Potential Change 9 | Implementation of the Transmission System Operators Guidelines | Dcode - Dcode Potential Change 9 | E | TBD | E | TBD | E | TBD |  |  | Upcoming | This modification will cater for the introduction of the new ER G99 which will replace ER G59 for all new geneartaion connections from May 2019. This change will appear on the plan when a raise date is known. | RFG