## Introduction
Cross Code European Network Codes Implementation Plan
Background
On 3 March 2011, the European Third Energy Package came into effect with the aim of developing a more harmonised European energy market. This legislation required the development of European Network Codes (ENCs), which would apply across Europe and take precedence over existing national arrangements. The introduction of the ENCs will have a far reaching impact on the GB electricity industry, with changes required to grid connections, markets and system operation.
Objective
Whilst the final ENCs are expected to enter into force in 2017, implementation activities in GB will continue for a number of years. In order for Code Administrators to be able to project manage the required changes these network codes and guidelines will introduce, this document provides the following end to end project plan.
What does the project plan do?
The project plan is designed as a tool with a filter function, to enable the user to select information and tailor it any given audience. Information can be filtered by any variation of the following categories; Code, change reference, ENC, milestones, the date the change was raised, change decision date, implementation date, state of progression (i.e. upcoming, raised, assessment, awaiting implementation etc.), and known dependencies.
Principles
Please be aware that project plan and assessment has been developed on the principle of minimal change to meet compliance, for example to avoid rewriting the newly introduced ENC requirements into the GB Codes.
Please see the summary for the network codes and impacts on the GB Codes below:
| EU Codes and Guidelines | Abbreviations | Description | Status
Connection Codes
| Requirements for Generators | RfG | Harmonise and update technical connection requirements for all types of generators from 800W upward. | Adopted
| Demand Connection Code | DCC | Connection of industrial loads and DSOs, and sets out requirements which will apply to the demand side of the power system. | Adopted
| Network Code on High-Voltage Direct Current Connections | HVDC | Rules for the use of HVDC technology included between synchronous area and embedded systems. | Adopted
Market Codes
| Forward Capacity Allocation | FCA | Couples existing European electricity forward markets to create a pan-European internal market by harmonising market rules for calculating and allocating capacity in the forward market. | Adopted
| Capacity Allocation and Congestion Management | CACM | Rules for allocating capacity in day-ahead and intra-day timeframe, calculating the levels of availability cross border, allocating and recovering costs. | Adopted
| Network Code on Electricity Balancing | EB GL | Rules for cross border exchange of reserves and balancing energy | Pending
System Operator Codes
| Transmission System Operation Guideline | SOGL | Setting minimum system security, operational planning and frequency management standards. | Adopted
| Network Code on Emergency and Restoration | NC ER | Harmonisation of system defence and restoration procedures during severe events. | Pending
Need more information?
For more information regarding a specific change, please contact the responsible Code Administrator:
ELEXON |  | Balancing and Settlement Code (BSC)
Energy Networks Association |  | Distribution Code (DCode)
National Grid |  | Connection and Use of System Code (CUSC)
Grid Code (GC)
System Operator – Transmission Owner Code (STC)
What is the publication schedule?
Last Wednesday of every month |  | ELEXON circulate the spreadsheet from the previous month, for NGET and ENA to redline to highlight any updates
First Wednesday of every month |  | NGET and ENA redlines the spreadsheet to highlight any updates, and return the redlined spreadsheet to ELEXON
Second Wednesday of every month |  | ELEXON publishes the updated Forward Work Plan on the 'EU Legislation' page of the ELEXON website, and circulate the link to NGET and ENA.
Document management
Version History: ENC Implementation Plan - Oct 17 V1.0 FINAL
This plan offers a best view as the October 2017 updates, as of 1 November 2017.

## Project Plan
Project Plan
The project plan is designed as a tool with a filter function, to enable the user to select information and tailor it towards a given audience. This plan includes all live and upcoming changes. Please note that udpates for October 2017, are highlighted in red.
Code | Change Ref | Title | Timeline Ref | Raise Date Status | Raise Date | Imp Date Status | Imp Date | Implementation Duration | Progression State | Commentary | ENC
|  |  | TODAY | Confirmed | 2017-11-01 | Estimated | 2017-11-02 | 1 | Assessment | Workgroup meetings need to re-convene following 1 year hiatus. This change will appear on the plan when the Workgroup reconvenes.
Milestone | CACM came into force | CACM came into force | Milestone - CACM came into force | Confirmed | 2015-08-01 | - | - | 1 | Confirmed | - | CACM
GC | GC0091 | Application of the the Demand Connection Code - Implementation of European Network Code | GC - GC0091 | Confirmed | 2016-03-01 | Estimated | TBD | 1 | Awaiting Withdrawal | This modification was originally set up as an issue Group. This has been requested to be withdrawn at the August Grid Code panel and September Distribution Code Panel. This Modification is still open and will close once the Distribution Code raise their respective Modification | DCC
BSC | P342 | Change to Gate Closure for Energy Contract Volume Notifications | BSC - P342 | Confirmed | 2016-05-25 | Confirmed | 2017-11-02 | 526 | Awaiting Implementation | This Modification would introduce a new deadline for the purpose of submitting Energy Contract Volume Notifications (ECVNs) and Metered Volume Reallocation Notifications (MVRNs) for each Settlement Period. This new contract notification deadline would be decoupled from Gate Closure, and would be at the start of the relevant Settlement Period (Alternative Modification). | -
BSC | P344 | Project TERRE implementation into GB market arrangements | BSC - P344 | Confirmed | 2016-06-01 | Estimated | 2018-09-01 | 822 | Assessment | Project TERRE is currently set to go-live in Feb to April 2019.. | EB GL
GC | GC0097 | European Energy Balancing Guidelines - Replacement Reserves - TERRE | GC - GC0097 | Confirmed | 2016-11-16 | Estimated | 2019-07-01 | 957 | Raised | This modification maybe required to address changes associated with project TERRE. Deadline for EIF is fixed. This mod is set to be implemented Q3 2019. | EB GL
BSC | P354 | Use of ABSVD for non-BM Balancing Services at the metered (MPAN) level | BSC - P354 | Confirmed | 2017-01-11 | Estimated | 2019-02-28 | 778 | Assessment | P354 proposes to allow the SO to provide ABSVD at the MSID level to the Settlement Administration Agent (SAA) who will allocate this to the appropriate Supplier BM Unit. This solution would avoid non-BM participants receiving a second income stream (imbalance revenue). | -
Dcode/GC | GC100 | GC0100 EU Connection Codes GB Implementation – Mod 1 | Dcode/GC - GC 100 | Confirmed | 2017-05-30 | Estimated | 2018-03-01 | 275 | Raised | This modification will set out within the Grid and Dist Code and the new Engineering Recommendations G98 and G99 the following compliance obligations in the EU Connection Codes: 1. Scope and applicability of the RfG, DCC and HVDC requirements for GB users 2. Set the x4 Type (A-D) MW banding levels for GB, as required in RfG 3. Set the GB Fast Fault Current Injection parameters, as set out in RfG 4. Set the GB Fault Ride Through requirements, as set out in RfG and HVDC NCs. A Joint Grid and Dist Panel 15 day workgroup Public consultation opened on 11 September and will close on 2 October. Details of the consultation can be found here - http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0100/ | RfG/HVDC
Dcode/GC | GC101 | GC0101 EU Connection Codes GB Implementation – Mod 2 | Dcode/GC - GC 101 | Confirmed | 2017-05-30 | Estimated | 2018-03-01 | 275 | Raised | This modification (2/4) will set out within the Grid Dist Code and the new Engineering Recommendatiions G98 and G99 the following compliance obligations in the EU Connection Codes: 1. Set the Voltage & Reactive requirement in GB, as required in RfG and HVDC 2. Set the Frequency requirements in GB, as required in RfG and HVDC A Joint Grid and Dist Panel 15 day workgroup Public consultation opened on 11 September and will close on 2 October. Details of the consultation can be found here - http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0101/ | RfG/HVDC
GC | GC0098 | Using GB Grid Code data to construct the EU Common Grid Model in accordance with Regulation (EU) 2015/1222 (CACM) and Regulation (EU) 2016/1719 (FCA). | GC - GC0098 | Confirmed | 2017-05-30 | Estimated | 2017-11-01 | 155 | Raised | This modification may be required to address the requirements of the Common Grid Model. Deadline for EIF is fixed. Compliance for CGM is Jan 2018 - and TBC based on methodologies | CACM/FCA
GC | GC0099 | Establishing a common approach to interconnector scheduling consistent with the single intraday market coupling processes set out within Regulation (EU) 2015/1222 (CACM) | GC - GC0099 | Confirmed | 2017-05-30 | Estimated | 2017-11-01 | 155 | Raised | Deadline for EIF is provisionally Q1 2019 | CACM
BSC | P356 | Time of Interconnector Data Submission | BSC - P356 | Confirmed | 2017-06-01 | Estimated | 2018-06-01 | 365 | Assessment | P356 was raised by National Grid on 3 July 2017. The Modification will align the BSC with Grid Code Modification GC0099, which seeks to introduce the interconnector scheduled transfer process to the Grid Code. This is in order to establish common, cross-code provisions which are compatible with both the EU single intraday market coupling processes, and GB and EU balancing processes. | CACM
Dcode/GC | GC102 | GC0102 EU Connection Codes GB Implementation – Mod 3 | Dcode/GC - GC102 | Confirmed | 2017-06-30 | Estimated | 2018-04-01 | 275 | Raised | This modification (3/4) will set out within the Grid and Dist Code and G98 and G99 the following compliance obligations in the EU Connection Codes: 1. Set the System Management parameters, as set out in RfG and HVDC 2. Set the Compliance requirements, as set out in RfG, DCC and HVDC | RFG
GC | GC0103 | The introduction of harmonised Applicable Electrical Standards in GB to ensure compliance with the EU Connection Codes | GC - 103 | Confirmed | 2017-07-27 | Estimated | TBD | 1 | Raised | This modification proposal is intended to harmonise technical standards across GB and where applicable would also align these with the ENCs | -
GC | GC104 | DCC technical requirements, compliance and DSR | GC - 104 | Confirmed | 2017-08-16 | Estimated | 2018-07-01 | 319 | Raised | This mod is the last of the Grid Code mods to implement EU Connection Codes into GB and covers all the remaining requirements of DCC not coverd in GC 100. This mod is set to be implemented in Q3 2018. | DCC
Dcode/GC | GC104 | Implementation of the requirements of the European Network Code - Demand Connection | Dcode - GC104 | Confirmed | 2017-09-07 | Estimated | TBD | 1 | Raised | This modification will cater for the introduction of the new ER G99 which will replace ER G59 for all new geneartaion connections from May 2019. | DCC
BSC | P360 | Making the BSC’s imbalance price compliant with the European Balancing Guideline | BSC - P360 (without Art. 55 derogation) | Confirmed | 2017-09-07 | Estimated | 2018-11-01 | 420 | Assessment | P360 was raised by National Grid on 7 September 2017. The modification seeks to implement changes to the BSC, to ensure compliance with EB GL Article 55. A derogation from Article 55 is currently being sought. Should a derogation be granted, this Modification will likely be withdrawn. | EB GL
Milestone | SOGL came into force | SOGL came into force | Milestone - SOGL: came into force | Confirmed | 2017-09-14 | Estimated | N/A | 1 | Confirmed | The Transmission System Operation Guideline (SOGL) entered into force 14 September 2017 | SOGL
Dcode/GC | Dcode-GC0106 | European SOGL Implementation - Data Exchange | Dcode-GC0106 | Confirmed | 2017-10-18 | Estimated | 2018-10-01 | 348 | Raised | Raised at October GC panel, joint working with Dcode. This Modification was previously STC Potential Change 2, and continues the work undertaken by GC0095. | SOGL
STC | STC Potential Change 2 | European SOGL Implementation - Data Exchange | STC - SOGL: Implementation - Data Exchange | Estimated | 2017-12-01 | Estimated | 2018-10-01 | 304 | Upcoming | - | SOGL
Milestone | NC ER comes into force | NC ER comes into force | Milestone - NC ER: comes into force | Estimated | 2017-12-01 | - | - | 1 | Assumed | - | NC ER
GC | Grid Code Potential Change 4 | European Emergency & Restoration Code - System Defence & Restoration Plan | GC - NC ER: System Defence & Restoration Plan | Estimated | 2017-12-01 | Estimated | 2018-12-01 | 365 | Upcoming | This mod is set to be raised in Q4 2017. This mod is set to be implemented in Q4 2018. | NC ER
GC | Grid Code Potential Change 13 | Market Suspension | GC - NC ER: Market Suspensions | Estimated | 2017-12-01 | Estimated | 2018-10-01 | 304 | Upcoming | This mod is set to be raised in Q4 2017. Deadline for EIF is provisionally Q4 2018 | NC ER
Milestone | EB GL entry into force | EB GL entry into force | Milestone - EB GL: Entry into force | Estimated | 2017-12-01 | - | - | 1 | Assumed | - | EB GL
Milestone | Application for Exemption from 15 min Settlement | Application for Exemption from 15 min Settlement | Milestone - EB GL: Application for Exemption from 15 min Settlement | Estimated | 2017-12-01 | - | - | 1 | Assumed | - | EB GL
Milestone | Assignment of EB GL where needed | Assignment of EB GL where needed | Milestone - EB GL: Assignment | Estimated | 2017-12-01 | - | - | 1 | Assumed | - | EB GL
Milestone | Backstop date for Derogation from Article 49 and 55 | Backstop date for Derogation from Article 49 and 55 | Milestone - EB GL: Backstop date for derogation from Art. 49 and 55 | Estimated | 2017-12-01 | - | - | 1 | Assumed | - | EB GL
BSC | BSC Potential Change 3 | Inclusion of Imbalance Adjustments (without Article 49 derogation) | BSC - EB GL: Inclusion of Imbalance Adjustments (without Art. 49 derogation) | Estimated | 2017-12-01 | Estimated | 2018-11-01 | 335 | Upcoming | It is assumed that NGET and ELEXON will apply for a derogation forArticle 49. If a derogation is granted, this Modification will be raised in June 2019. | EB GL
BSC | BSC Potential Change 4 | Align BSC with the Authority's oversight obligation | BSC - EB GL: Align BSC with the Authority's oversight obligation | Estimated | 2017-12-01 | Estimated | 2018-11-01 | 335 | Upcoming | Assignment by BEIS and decision by Ofgem on how it wishes to approach this requirement | EB GL
CUSC | CUSC Potential Change 1 | European Energy Balancing Guidelines - Replacement Reserves | CUSC - EB GL: Replacement Reserves | Estimated | 2017-12-01 | Estimated | 2018-10-01 | 304 | Upcoming | This mod is set to be raised in Q4 2017. This mod is set to be implemented in Q4 2018. | EB GL
GC | Grid Code Potential Change 15 | Manual Frequency Restoration Reserves | GC - EB GL: Manual Frequency Restoration Reserves | Estimated | 2017-12-01 | Estimated | TBD | 1 | Upcoming | - | EB GL
GC | Grid Code Potential Change 16 | Regional Outage Co-ordination and Security Analysis | GC - Regional Outage Co-ordination and Security Analysis | Estimated | 2017-12-02 | Estimated | TBD | 1 | Upcoming | - | SOGL
GC | Grid Code Potential Change 11 | European SOGL Implementation - Regional Outage Coordination | GC - SOGL: Regional Outage Coordination | Estimated | 2018-01-01 | Estimated | 2019-12-01 | 699 | Upcoming | This mod is set to be raised in Q1 2018. Deadline for EIF+12 months | SOGL
GC | Grid Code Potential Change 12 | European SOGL - Requirements | GC - SOGL: Requirements | Estimated | 2018-01-01 | Estimated | 2019-12-01 | 699 | Upcoming | This mod is set to be raised in Q1 2018. Deadline for EIF+12 months | SOGL
STC | STC Potential Change 3 | European SOGL Implementation -Regional Outage Coordination | STC - SOGL: Regional Outage Coordination | Estimated | 2018-01-01 | Estimated | 2018-12-01 | 334 | Upcoming | This mod is set to be raised in Q1 2018 | SOGL
BSC | BSC Potential Change 5 | Amendments to Imbalance Price | BSC - EB GL: Amendments to Imbalance Price | Estimated | 2018-12-01 | Estimated | 2020-06-01 | 548 | Upcoming | If TSO Proposal for activation purpose do not align with the BSC, this Modification will be raised to amend the imbalance price calculation | EB GL
BSC | BSC Potential Change 6 | Align BSC with the TSO's Terms and Conditions | BSC - EB GL: Align BSC with the TSO's T&Cs | Estimated | 2018-12-01 | Estimated | 2019-11-07 | 341 | Upcoming | If NGET write Ts & Cs in a way that differs from the Ts & Cs of the BSC, this Modification will be raised to align the BSC with the Ts & Cs of the TSO. | EB GL
Milestone | UK leaves EU | UK leaves EU | Milestone: UK leaves EU | Confirmed | 2019-03-29 | - | - | 1 | Confirmed | - | -
BSC | BSC Potential Change 3 | Inclusion of Imbalance Adjustments (with Article 49 derogation) | BSC - EB GL: Inclusion of Imbalance Adjustments (with Art. 49 derogation) | Estimated | 2019-06-01 | Estimated | 2020-11-01 | 519 | Upcoming | It is assumed that NGET will apply for a derogation for EB GL Article 49. If a derogation is granted, this Modification will be raised in June 2019 | EB GL
BSC | BSC Potential Change 11 | Harmonised Imbalance Settlement (with Article 55 derogation) | BSC - EB GL: Harmonised Imbalance Settlement (with Art. 55 derogation) | Estimated | 2019-06-01 | Estimated | 2020-12-01 | 549 | Upcoming | This Modification will be raised to align the BSC with NGETs proposals to harmonise the main features of imbalance settlement. If a derogation for EB GL Article 55, it is likely that P360 will be withdrawn and the work to date will be included within this Modification. | EB GL
BSC | BSC Potential Change 12 | Project MARI | BSC - EB GL: Project MARI | Estimated | 2019-06-01 | Estimated | 2021-11-01 | 884 | Upcoming | This Modification will be raised, as an extension of the principles introduced under P344 'Project TERRE' | EB GL
Milestone | Backstop date for RR standard products | Backstop date for RR standard products | Milestone - EBGL: Backstop date for RR standard products | Estimated | 2019-12-01 | - | - | 1 | Assumed | - | EB GL
GC | Grid Code Potential Change 2 | European Energy Balancing Guidelines - General Compliance | GC - EB GL: General Compliance | Estimated | 2020-01-01 | Estimated | 2021-07-01 | 547 | Upcoming | This modification maybe required to address general compliance requirements of the EB GL. The mod if currently set to be raised in Q1 2020. Deadline for EIF is fixed. The mod is set to be implemented in Q3 2021. | EB GL
GC | Grid Code Potential Change 3 | European Energy Balancing Guidelines - Manual Frequency Restoration Reserves (mFRR) | GC - EB GL: mFRR | Estimated | 2020-01-01 | Estimated | 2021-07-01 | 547 | Upcoming | This modification maybe required to address mFRR requirements of the EB GL. This mod is set to be raised in Q1 2020. Deadline for EIF is fixed. This mod is set to be implemented in Q3 2021. | EB GL
GC | Grid Code Potential Change 10 | Frequency Restoration Reserves | GC - EB GL: FRR | Estimated | 2020-01-01 | Estimated | 2021-07-01 | 547 | Upcoming | This mod is set to be raised in Q1 2020. Deadline for EIF is provisionally Q3 2021 | EB GL
Milestone | The earliest decision on bidding zone change | Earliest decision on bidding zone change | Milestone - Earliest decision on bidding zone change | Estimated | 2020-07-01 | - | - | 1 | Assumed | - | CACM
CUSC | CUSC Potential Change 2 | European Energy Balancing Guidelines - Manual Frequency Restoration Reserves (mFRR) | CUSC - EB GL: mFRR | Estimated | 2020-07-01 | Estimated | 2021-07-01 | 365 | Upcoming | This mod is set ot be raised Q3 2020.This mod is set to be implemented in Q3 2021 | EB GL
Milestone | Backstop date for hamonised Imbalance Settlement | Backstop date for harmonised Imbalance Settlement | Milestone - Backstop date for harmonised Imbalance Settlement | Estimated | 2020-12-01 | - | - | 1 | Assumed | - | EB GL
Milestone | Implementation date for any bidding zone change | Implementation date for any bidding zone change | Milestone - Implementation date for any bidding zone change | Estimated | 2021-07-01 | - | - | 1 | Assumed | - | CACM
Milestone | Backstop date for FRR standard products | Backstop date for FRR standard products | Milestone - Backstop date for FRR standard products | Estimated | 2021-12-01 | - | - | 1 | Assumed | - | EB GL

## Closed changes
Closed changes
This list includes changes that have been implemented, withdrawn, in hiatus or are no longer required. Please note that udpates for October 2017, are highlighted in red.
Code | Change Ref | Title | Timeline Ref | S | Raised | S | Imp Date | Implementation Duration | Progression State | Commentary | ENC
SQSS | GSR012 | Treatment of Interconnectors | SQSS - GSR012 | C | 2010-10-05 | E | TBD | 1 | Hiatus | Workgroup meetings need to re-convene following 1 year hiatus. This change will appear on the plan when the Workgroup reconvenes.
CUSC | CMP279 | Housekeeping modification to amend typographical errors in the CMP272 legal text | CUSC - CMP279 | E | 2017-04-19 | E | 2017-05-31 | 42 | Implemented | This modification was implemented in the CUSC on the 31 May 2017
Dcode | DCRP1701 | Entry into Force of the EU Network Code “Transmission System Operational Guideline | Dcode - DCRP1701 | E | 2016-12-08 | E | 2017-05-01 | 144 | Implemented | The GB Distribution Code requires two minor modifications to DOC5 and DOC7 to ensure it is compliant with the EU Network Code “Transmission System Operation Guidelines” (TSOG). The TSOG is expected to enter into force in early summer 2017 and some parts of it are effective immediately. On the 28/04/2017 the Authority published its decision and approve the modification. The modification was implemented on 01/05/2017. | SOGL
BSC | P329 | REMIT | BSC - REMIT | C | 2015-11-25 | C | 2017-06-29 | 582 | Implemented | P329 aligned the BSC and BMRS with the Regulation on Wholesale Energy Markets Integrity and Transparency (REMIT) common schemas for inside information web feeds, required by the Agency for the Cooperation of Energy Regulators (ACER). To achieve this, the REMIT inside information data submitted by participants and reported by the BMRS will need to cover the output requirements of ACER. In addition to the ACER requirements, P329 enables the submission of outage profile information to BMRS. BSC Parties will be ultimately responsible for both accuracy and timeliness of their REMIT messages. | REMIT
STC | STC Potential Change 1 | European TSOG - Multi TSO Training Cooperation | STC - STC Potential Change 1 | E | 2017-10-01 | C | 2018-10-01 | 0 | Not required | The SOGL article 63 is an SO only article focusing on operational tasks performed by SOs. No additional training obligation between the SO and TO roles is deemed necessary as part of SOGL implementation and hence no change to the STC is required | SOGL
GC | Grid Code Potential Change 17 | SOGL Requirements in Relation to Reserve Providers and Operational Agreements | GC - Grid Code Potential Change 17 | E | 2017-12-01 | E | TBD | 0 | Not required |  | SOGL
BSC | BSC Potential Change 7 | Project TERRE 2 | BSC - BSC Potential Change 7 | E | 2018-10-01 | E | 2020-03-01 | 0 | Not required | This Modification will be raised to implement any outstanding activities from Project TERRE | EB GL
BSC | BSC Potential Change 9 | NGET proposal on specific products | BSC - BSC Potential Change 9 | E | 2018-11-01 | E | 2019-11-07 | 0 | Not required | If NGET make a proposal on specific products, an assessment will be required to ensure that the understanding of specific products aligns with the BSC. If understanding of specific products in the TSO proposal, differs from the BSC, this Modification will be raised to align the BSC with the proposal. | EB GL
BSC | BSC Potential Change 10 | Market Suspension and Restoration Arrangement | BSC - BSC Potential Change 10 | E | 2018-11-01 | E | 2020-03-01 | 0 | Not required | If NGET makes proposals for rules concerning the suspension and restoration of market activities; and the rules for balancing energy and imbalance settlement during market suspension, that differ from the BSC, this Modification will be raised to align the BSC with the proposals. | NC ER
BSC | BSC Potential Change 8 | Unintended exchanges of energy | BSC - BSC Potential Change 8 | E | 2018-12-01 | E | 2019-11-07 | 0 | Not required | Certainty on whether this Mod is required, is based on the provision of information from NGET, on what will be proposed. | EB GL
BSC | BSC Potential Change 13 | Project TERRE 3 | BSC - BSC Potential Change 13 | E | 2019-01-01 | E | 2020-02-27 | 0 | Not required | This Modification will be raised to implementation outstanding activities from P344 'Project TERRE' | EB GL
GC | GC0095 | GB implementation workgroup for Transmission System Operation Guideline (TSOG) European Network Code | GC - GC0095 | C | 2016-05-27 | E | TBD | 0 | Withdrawn | This modification was set up as an issue group. This was historcially given a Modification reference prior to Open Governance and actually served as an issues group. The change has now been withdrawn, and the new Modification which has arisen from the TSOG guidelines is GC0106 SOGL. | SOGL